## Prioritization List (hidden)
Project Number | Project Name | PM | Product Family |  | Current Phase | ROW Acquisition 1 - 10 | ROEs | Current ROW Status | ROW Complete Date | ROW Status | CN Start Date | Ad Date | Total Adopted Budget | Current EAC | Funding Status | Baseline Status | Baselined? | Grant Status | Grant Obligation Date (if applicable) | Permit Status | Project Notes
1129588 | 2020 Bridge Priority Maintenance | Roark | Bridge | 6 | Status is varied for program work |  |  |  |  | Various for program work | Various dates for program work | In-house | 5225961 | 7761399.3046 | Funding identified |  | No |  |  | Various for program work
1130991 | Drainage Preservation - Division Drainage | Shular/Quach | Drainage | 6 | Status is varied for program work | [5 empty] | Various dates for program work | In-house | #N/A | #N/A | Funding identified | #N/A | #N/A
1136576 | 2019/20 School Zone Safety - School Safety Program | Hafele | Traffic Control/Safety | 6 | Status is varied for program work | 3 |  |  |  | 3/8/21 - 1 TCE required for 8th Ave project. Team requesting to finalize process, Maura to follow up this week. | Various dates for program work | In-house | 248509.87 | 224135.6 | Funding identified |  | No
1136633 | Patton Bridge Repair | Jiang | Bridge | 5 | Substantially Complete | [5 empty] | February 2021 | July 2020 | 620000 | 115422.22 | Funding identified |  | No
1136631 | Judd Creek Bridge #3184 Load Upgrade/Repair | O'Day | Bridge | 5 | Substantially Complete | [5 empty] | March 2021 | August 2020 | 100000 | 93832.79 | Funding identified |  | No
1137996 | 2020 Pavement Preservation - Countywide | Moore | Pavement | 5 | Substantially Complete | [5 empty] | June 2020 | March 2020 | 5195706 | 5920885.71 | Funding identified | 4444263.9775 | Yes
1136001 | S 277th St. Bridge #3126 - Bridge Safety Program | Premachandra | Bridge | 5 | Substantially Complete | 99 | 99 |  |  | Working within the ROW | July 2021 | April 2021 | 0.04 | 2555316.0528 | Funding identified | 1953030.6524 | Yes | No grant | n/a | Corps permit - submit 1/8/21
1135997 | Coal Creek Bridge #3035A - Bridge Safety Program | Martin | Bridge | 4 | Implementation |  |  | 3/8/21 - awaiting certification | 2021-03-10 | WSDOT R/W Certification received 3/10/21 | September 2021 | May 2021 | 0.07 | 6619816.296 | Funding identified | 5534359.8348 | Yes | Federal Local Bridge Program (FLBP) grant |  | Milestone provided to ART was P.D. permits issued by Feb 2021, they have not met their commitment
1136233 | Lake Joy Culvert Replacement - Fish Passage Program (Consultant) | Quach | Drainage | 5 | Substantially Complete | 1 |  |  |  | ROEs received. 2 drainage easements and 2 TCEs (3 owners). Goal to send ROW plan to Real Estate Services by end of 2020. | July 2021 | In-house | 262000 | 1925321.87 | Funding identified |  | No |  |  | JARPA and ACOE required.
1125758 | West Snoqualmie Valley Culvert Replacement | Cassidy | Drainage | 4 | Implementation |  |  |  |  | ROEs in progress per Rachel B | August 2020 | In-house | 961421 | 599463.84 | Funding identified |  | No
1139815 | 356th Drive SE Slide - Emergency Repair | Truong | Drainage | 4 | Implementation | [5 empty] | September 2020 | Emergency Declaration 2020 | 3000000 | 2736005.94 | Funding identified |  | No
1136580 | S 360th St - School Safety Program - School Pathway Project | Ashti | Roadside | 4 | Implementation | 2 |  |  |  | Easement acquisition for 1 parcel in process (Ms. Earls) | May 2022 | March 2022 | 208300 | 258894.068 | CN not funded |  | Yes |  |  | Permits not complete | Ccombined contract
1136085 | 2019/20 Guardrail Preservation - Traffic Safety Program/Countywide | Mott | Roadside | 5 | Substantially Complete | [5 empty] | February 2021 | October 2020 | 4100000 | 3598914.55 | Funding identified | 4520001.008 | Yes
1136646 | 42nd Ave S - School Safety Program - School Pathway Project | Ashti | Roadside | 4 | Implementation |  |  |  |  | All ROW and ROE complete | October 2020 | June 2020 | 99700 | 110016.43 | Funding identified |  | No |  |  |  | combined contract
1136582 | S 298th St - School Safety Program - School Pathway Project | Ashti | Roadside | 4 | Implementation |  |  |  |  | All ROW and ROE complete | October 2020 | June 2020 | 120000 | 102250.95 | Funding identified |  | No |  |  |  | combined contract
1137862 | 2020 High Friction Surface Treatment | Linders | Traffic Control/Safety | 4 | Implementation |  |  |  |  | No ROE or ROW needs | TBD 2022 | June 2021 | 537400 | 3053659.6293 | Funding identified | 3139019.2148 | Yes |  |  | Construction Hours Variance – anticipated to be complete 2/1/2021
1129714 | NE Stillwater Hill Rd Reconstruction | Linders | Traffic Control/Safety | 5 | Substantially Complete |  |  |  |  | ROE expires 1/2021. 9 ARDS sent (received 8, need 1 but owner is unresponsive and cannot be found. Moving forward with 8 ARDs); expire 10/2021 | July 2021 | March 2021 | 845190 | 4270387.5293 | Funding identified | 5049999.4596 | Yes |  |  | C&G - anticipated to be complete 1/1/21 NPDES permit - anticipated to be compete 1/1/2021
1131157 | High Collision Sightline Improvements S 360 St & 32 Ave S - Traffic Safety Program | Ashti | Traffic Control/Safety | 4 | Implementation | 2 |  |  |  | Easement acquisition for 1 parcel in process (Ms. Earls) | May 2022 | March 2022 | 150000 | 171863.6 | Funding identified |  | Yes |  |  | Permits not complete | combined contract
1135999 | Upper Tokul Creek Bridge #271B - Bridge Safety Program | Martin | Bridge | 3 | Final Design | 2 |  |  |  | ROW plans and legal desc sent to ROW team 12/9/20 - ROW review in process, waiting on KC ROW team | April 2022 | February 2022 | 0.04 | 5045999.6746 | Funding identified |  | Yes | No grant |  | In initial phases of permit process
1135998 | Ames Lake Trestle Bridge #1320A - Bridge Safety Program | Truong | Bridge | 3 | Final Design | 3 |  |  |  | draft ROW plans anticipated to be completed by March 2021 | June 2023 | March 2023 | 0.07 | 10111246.4549 | Funding identified | 10165177.4481 | Yes | Applying for federal bridge program grant (due feb 2021) for CN | tbd | NEPA Completion anticipated by July 2021. BA is exempt as bridge is considered Structurally Deficient
1136000 | Baring Bridge #509A - Bridge Safety Program | Truong | Bridge | 3 | Final Design | 4 |  |  |  | Waiting for final project footprint to determine ROW needs - anticipated Q1 2021 | April 2024 | November 2023 | 0.04 | 13144595.6684 | Funding identified |  | No |  |  | Waiting for final project footprint to determine permiting needs - anticipated Q1 2021
1138914 | Fifteen Mile Creek Bridge #493C | Jose | Bridge | 3 | Final Design |  | 1 |  |  | 5 ROE's were requested. Need to complete cultural survey. 5 potential parcels total, 4 TCEs and 1 PE KC Survey will prepare ROW plan ROW will need to be certified | January 2023 | November 2022 | 0.08 | 5471258.3527 | Funding identified |  | No | Fed Local Bridge Program |  | BA (biological analysis) required - may take up to two years, to be completed in-house. In intial phases of permit process | ROW consultant
1127589 | NE 165th St Flood Risk Reduction | Karinen | Drainage | 3 | Final Design |  |  |  |  | 1 two-year ROE resigned granted expiring from August 2021. No easements required | TBD | In-house | 760146 | 811593.11 | Funding identified |  | No |  |  | Roads permitting work required - Clearing and Grading Permit and Shorelines Permit anticipated to be complete April 2021
1132710 | Sahalee at 4800 blk | Shular | Drainage | 3 | Final Design |  |  |  |  | ROEs granted. 2 drainage easements required. ROW plan sent to Leslie (date?) | June 2022 | In-house | 100000 | 341170.88 | Funding identified |  | No |  |  | ACOE and HPA required
1131511 | Sahalee at 4600 blk | Shular | Drainage | 3 | Final Design |  |  |  |  | ROEs granted. 2 drainage easements required. ROW plan sent to Leslie (date?) | August 2022 | In-house | 160000 | 362498.05 | Funding identified |  | No |  |  | ACOE and HPA required Rec'd HPA 6/21 - expires 10/21
1138339 | S 106th St (18th Ave S) | Shular | Drainage | 3 | Final Design | 3 |  |  |  | ROEs need to be renewed. 5 drainage easements. ROW plan sent to Real Property 7/31/20 (plan undergoing revisions) | August 2022 | In-house | 151000 | 413592 | Funding identified |  | No
1131672 | Petrovitsky Road at 20300 Blk | Mitchell | Drainage | 3 | Final Design | [5 empty] | Not Scheduled | Ad not scheduled | 91200 | 175322.83 | Funding identified |  | No
1131671 | Petrovitsky Road at 151st Ave SE | Mitchell | Drainage | 3 | Final Design | [5 empty] | Not Scheduled | Ad not scheduled | 102800 | 248469.71 | Funding identified |  | No
1131526 | Petrovitsky Road and 134th Ave SE | Mitchell | Drainage | 3 | Final Design |  | 1 |  |  |  | May 2024 | March 2024 | 530700.26 | 5325001.279 | CN not funded |  | No
1136238 | NE 24th St - Fish Passage Program (In-house) | Quach | Drainage | 3 | Final Design |  |  |  |  | All ROEs received. 3 TCEs - sent to Real Estate Services on 11/20/19 | July 2023 | In-house | 57000 | 913608.1271 | CN not funded |  | No | Applied for FEMA Building Resilient Intratructre and Community grant in November 2020, invited to update application for reconsideration in December 2020. |  | JARPA and ACOE required
1130710 | 380 Place at SR 164 Culvert Replacement - Flood Control District | Lyou | Drainage | 3 | Final Design | 4 |  |  |  | ROEs not currently required. 3 TCEs required. Low value property, opportunity for admin offer | June 2022 | March 2022 | 590000 | 996484.7967 | CN not funded | 1001250.3936 | Yes
1136235 | Avondale Culvert Replacemnet - Bear Creek Basin | Mitchell | Drainage | 3 | Final Design | [5 empty] | 2023 | Ad not scheduled | 332000 | 2309147.7407 | CN not funded |  | No
1129595 | Old Cascade Miller River Bridge West | Lyou | Drainage | 3 | Final Design | 2 |  |  |  | ROE request sent to Real Property 9/30/20 - pending Current assessed value of properties - 13k. Consultant hired for 60k. 13 parcels total | July 2022 | May 2022 | 2300000 | 2254358.4047 | Funding identified | 2299999.89 | Yes
1129596 | Old Cascade Miller River Bridge East | Lyou | Drainage | 3 | Final Design | 2 |  |  |  | ROE request sent to Real Property 9/30/20 - pending Current assessed value of properties - 13k. Consultant hired for 60k. 13 parcels total | July 2022 | May 2022 | 2750000 | 2719436.9767 | Funding identified | 2750000.51 | Yes
1136236 | 165th Culvert Replacement - Bear Creek Basin | Mitchell | Drainage | 3 | Final Design | [5 empty] | Not Scheduled | Ad not scheduled | 332000 | 658688.35 | CN not funded |  | No
1136232 | 128th Culvert Replacement - Bear Creek Basin | Mitchell | Drainage | 3 | Final Design | [5 empty] | Not Scheduled | Ad not scheduled | 332000 | 896682.59 | CN not funded |  | No
1136419 | SE 432nd St - Fish Passage Program (In-house) | Shular | Drainage | 3 | Final Design |  |  |  |  | 7 TCEs and 6 drainage easements needed (sent ROW plan to Real Estate Services 8/3/20) | 2023 | In-house | 57000 | 1101340.1614 | CN not funded |  | No |  |  | JARPA and ACOE required
1129599 | Renton Ave Phase III Sidewalk | Sahagun | Traffic Control/Safety | 3 | Final Design | 4 |  |  |  | ROE no longer required. 9 parcels requiring acquisition and TCE 3/8/21 - updating AOS | June 2022 | April 2022 | 2854412 | 2798477.2227 | CN not funded | 3399999.3319 | Yes | WSDOT Ped & Bike Grant unofficialy approved - 1.9m CN | Approximated at August 2021 | C&G and Seattle Street Improvement Permit anticipated complete 4/21/21
1136086 | 218th Ave SE Reconstruction | Sahagun | Traffic Control/Safety | 3 | Final Design |  |  |  |  | 3/8/21 - Waiting for survey for ROW plan (ARDs and TCEs). Will need a quick turnaround after plan complete. | May 2022 | February 2022 | 877846 | 5468484.2546 | Funding identified |  | No
1134081 | Redmond Ridge NE Roundabout | Sahagun | Traffic Control/Safety | 3 | Final Design | 1 |  |  |  | 4 2-year ROEs expiring btwn Feb 2021 and April 2021. 4 parcels (deed takes and utility easements); sent final signed ROW plans to Property Services 4/6/20, anticipated complete 3/31/21. | June 2022 | April 2022 | 1200000 | 1457608.8067 | Funding identified | 1379999.52 | Yes |  |  | C&G exempt
1131235 | S 360 St & Military Road Roundabout - Traffic Safety Program | Karinen | Traffic Control/Safety | 3 | Final Design |  | 1 |  |  | 8 (of 10, 2 were nonresponsive) two-year ROEs granted expiring from January 2020 to March 2020. 6/8/2021 – anticipated date for receiving signed ROW plans from Survey and sending a copy to Property Services. Acquisition anticipated to be complete 12/26/2022 | August 2023 | June 2023 | 4150000 | 4181199.9672 | Funding identified |  | No | Applied for TIB CN grant (2023, 2.7 m request). Per Macile 1/4/20, unlikey to be awarded |  | Not known
1138337 | Fish Hatchery Bridge #61B Emergent Repair | Roark | Bridge | 5 | Substantially Complete | 1 |  |  |  | No ROEs identified 2 TCEs on two parcels (3/8/21 - need update on status, can an AOS be completed this year?) | July 2021 | In-house | 80000 | 43933.48 | Funding identified |  | No
1138913 | Boise X Connection #3055A | O'Day | Bridge | 2 | Preliminary Design |  |  |  |  | ROE - one private property owner and Parks (KC Parks entrance approval requested by Maura on 10/27/20 and ROE was signed February 2021) ROW will need to be certified | February 2024 | October 2023 | 0.06 | 2971062.1711 | Funding identified |  | No | Fed Local Bridge Program |  | In intial phases of permit process
1130706 | NE 8th Lake Allen Outlet | Lyou | Drainage | 2 | Preliminary Design |  |  |  |  | ROE request sent to Real Property on 11/3/20; required to initiate project survey and is pending. | 2022 | In-house | 400000 | 19365.28 | Funding identified |  | No
1136237 | S 370th St - Fish Passage Program (In-house) | Lyou | Drainage | 2 | Preliminary Design |  |  |  |  | One ROE set to expire 2/19/21. One ROE request sent to Real Property Jan 2019 - pending | Not Scheduled | In-house | 57000 | 13851.96 | CN not funded |  | No
1136239 | 317th and Thomas - Fish Passage Program (In-house) | Quach | Drainage | 2 | Preliminary Design |  |  |  |  | All ROEs obtained. 3 drainage easements and 3 TCEs (3 owners). ROW plan in progress (not sent to Real Property) | Not Scheduled | In-house | 57000 | 975352.1199 | CN not funded |  | No | Applied for FEMA Hazard Mitigation Grant Program November 2020. will be notified after 1/29/21 if approved to send to FEMA for approval. Estimated 900-1m project cost |  | JARPA and ACOE required
1136229 | 180th at 408th - Fish Passage Program (Consultant) | Mitchell | Drainage | 2 | Preliminary Design | [5 empty] | Not Scheduled | Ad not scheduled | 292000 | 704656.0738 | CN not funded |  | No
1136234 | Woodinville Duvall Rd - Fish Passage Program (Consultant) | Shular | Drainage | 2 | Preliminary Design |  |  |  |  | 2 drainage easements and 2 TCE’s (2 owners) - ROW plans not sent to Real Estate Services | June 2023 | May 2023 | 322000 | 1769920.73 | Funding identified |  | No |  |  | JARPA and ACOE required
1136231 | 185th at 179th - Fish Passage Program (Consultant) | Mitchell | Drainage | 2 | Preliminary Design | [5 empty] | 2023 | Ad not scheduled | 122000 | 1147132.7994 | CN not funded |  | No
1140906 | 240th at 156th |  | Drainage | 2 | Preliminary Design |  | 2 |  |  | Requested ROEs 3/8/21 | Not Scheduled | In-house
1141625 | SE Kent-Kangley Rd at Landsburg Roundabout - Traffic Safety Program | Linders | Traffic Control/Safety | 3 | Final Design |  |  |  |  | ROE expires 5/2021. 3-4 Pes needed for final fix | July 2022 | May 2022 | #N/A | #N/A | Funding identified | #N/A | No |  |  | Not known
1129598 | Issaquah-Hobart at May Valley Roundabout - Traffic Safety Program/Flood Control District | Sahagun | Traffic Control/Safety | 2 | Preliminary Design |  |  |  |  | 13 2-year ROEs expiring btwn Feb 2021 to Feb 2022. Acquisition needs not known | June 2024 | April 2024 | 755000 | 669943.52 | Funding identified |  | No |  |  | Not known
1134080 | NE Woodinville Duvall at West Snoqualmie Valley NE | Linders | Traffic Control/Safety | 2 | Preliminary Design |  |  |  |  | Not known | Not Scheduled | Ad not scheduled | 150000 | 412629.5891 | Funding identified |  | No |  |  | Not known
1138330 | Covington Way SE Intersection Improvements Study - Traffic Safety Program | Linders | Traffic Control/Safety | 3 | Final Design |  |  |  |  | ROE request sent to Real Property for 6 parcels 6/17/20 - pending. 2 current ROEs expire 3/11/2021. No known acquisition at this time | May 2023 | March 2023 | 100000 | 794129.6844 | Funding identified |  | No |  |  | Not known
1138918 | 16th Ave SW Ped Improvements | Mott | Traffic Control/Safety | 3 | Final Design |  |  |  |  | Anticipating ROW requests to Real Property team in Feb 2021 (TCE or PE), may be up to 12 areas/parcels. Any TCEs must be active until March 2023 | Summer 2024 | Spring 2023 | 958000 | 976312.183 | Funding identified |  | No |  |  | Need Clearing and Grading permit | grant requires ad by March 2022
1141001 | Tolt Bridge Slide Repair 1834A NE | Roark | Bridge | 2 | Preliminary Design |  | 2 |  |  | 1 property owner (the State); likely TCE or easement. 1 ROE needed to access parcel to complete survey basemapping | March 2023 | June 2023 |  | 792842 |  |  | No | No 180 day Temp ER funds from FHWA | PE: Sept 2020; CE: Jul 2022 |  | Will be in quick response master. Need to set up project number
1140858 | 244th Emergency Slide Project | Karinen | Roadside | 2 | Preliminary Design |  |  |  |  | No ROE or acquisition needs known at this time | June 2023 | April 2023 | 200000 | 3.7m | Funding identified |  | No | No 180 day Temp ER funds from FHWA. PE Obligation work sent 11/23/20. | PE/ROW: Nov 2020; CE: Apr 2022. | Clearing and Grading | Will be in quick response master. Need to set up project number
1130709 | SE 384th St | Lyou | Drainage | 1 | Planning | [5 empty] | TBD | Ad not scheduled |  |  |  |  | No | CRAB grant for PE&CN - submitted final app in Aug 2020. Notify Q1 2021. Project cost estimated 1.2m
1139716 | Langston at South 124th | Mitchell | Drainage | 2 | Preliminary Design | [5 empty] | October 2022 | September 2022 | 778416 | 8375.41 | Funding identified |  | No
1136230 | Fairwood E of 151st Culvert - Fish Passage Program (Consultant) | Berryessa (WLRD) | Drainage | 2 | Preliminary Design | [5 empty] | CN not scheduled | In-house | 10000 | 1407.61 | CN not funded |  | No
1129590 | Avondale Rd NE at Cottage Lake Elementary School Left-Turn Lane and Sidewalk Improvements | Karinen | Traffic Control/Safety | #N/A | #N/A |  |  |  |  | 10/4/2019 Request for access sent to Property Services. Request is for access to King County R/W which is behind private fence. 4 requests for access signed - no time limit given to property owner. No acquisition anticipated | #N/A | #N/A | 7877167 | 8271762.9344 | Funding identified |  | No |  |  | Clearing and Grading may be needed
1138947 | 284th Culvert Replacement - Fish Passage Program (in-house) | Shular | Drainage | 2 | Preliminary Design |  |  |  |  | ROE request in process for 2 owners. 2 TCEs (ROW plan in progress, not sent to Real Estate yet) | July 2022 | In-house |  |  | Funding identified |  | No |  |  | JARPA and ACOE required
1140905 | 17401 at 240th |  | Drainage | 2 | Preliminary Design |  | 3 |  |  | Requested Roes 3/8/21 | Not Scheduled | Ad not scheduled
tbd | E Reinig Rd Culvert Replacement | tbd - Jon Cassidy | Drainage | 0 | Preliminary Design | [5 empty] | 45200 | Ad not scheduled |  |  |  |  | #N/A | CRAB grant for PE&CN - submitted final app in Aug 2020. Notify Q1 2021. Project cost estimated 1.6m
tbd | Beall Rd SW | tbd - Jon Cassidy | Drainage | 0 | Preliminary Design | [5 empty] | 45200 | Ad not scheduled |  |  |  |  | #N/A | CRAB grant for PE&CN - submitted final app in Aug 2020. Notify Q1 2021. Project cost estimated 750k
tbd | SE Green Valley Rd and 218th Ave SE Intersection Improvement | tbd | Traffic Control/Safety | 0 | Preliminary Design | [5 empty] | 45200 | Ad not scheduled |  |  |  |  | #N/A | STP - FHWA Funds - already in TIP and can then obligate in 2021 | PE: Oct 2021; CE: 2024
1136709 | Traffic Calming - Traffic Safety Program |  | Traffic Control/Safety | 0 | #N/A | [5 empty] | #N/A | #N/A | 100000 | 21152.26 | Funding identified |  | No
1136716 | Transverse Rumble Strips - Traffic Safety Program |  | Traffic Control/Safety | 0 | #N/A | [5 empty] | #N/A | #N/A | 168000 | 3204.42 | Funding identified |  | No
1136711 | Roadway Lighting - Traffic Safety Program |  | Traffic Control/Safety | 0 | #N/A | [5 empty] | #N/A | #N/A | 375000 | 379083.76 | Funding identified |  | No
1136712 | Radar Speed Signs - Traffic Safety Program |  | Traffic Control/Safety | 0 | #N/A | [5 empty] | #N/A | #N/A | 150000 | 72329.68 | Funding identified |  | No
1136715 | Left Turn Phasing - Traffic Safety Program |  | Traffic Control/Safety | 0 | #N/A | [5 empty] | #N/A | #N/A | 200000 | 144228.55 | Funding identified |  | No
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data from Prism (Lifetime Appropriation)
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data from Prism (EAC Current)
Note on P1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data pulled from Ad Coordination list
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prism data export (EAC Gate 3)
Note on R1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prism data export (EAC Gate 3)

## Sheet2
Project Number | Project Name | Product Family | Current Phase | Baseline
1136000 | Baring Bridge #509A - Bridge Safety Program | Bridge | Final Design | No
1136453 | Fish Hatchery Bridge #61B Emergent Repair | Bridge | Final Design | No
1138914 | Fifteen Mile Creek Bridge #493C | Bridge | Final Design | No
1125758 | West Snoqualmie Valley Culvert Replacement | Drainage | Implementation | Not Baselined
1139815 | 356th Drive SE Slide - Emergency Repair | Drainage | Implementation | Not Baselined
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prism data export (EAC Gate 3)

## Sheet1
Phase | Number |  | Name | Section/Unit/Subunit | Has Gate 3 Save
DESIGN | 1129595 | Final Design | RSD OLD CASCADE/MILLER BR WEST | DRN,RSD | Yes
DESIGN | 1129596 | Final Design | RSD OLD CASCADE/MILLER BR EAST | BRG,EP | Yes
DESIGN | 1129599 | Final Design | RSD RENTON AVE PH III SIDEWALK | PMD,TRF | Yes
DESIGN | 1129714 | Implementation | RSD NE STILLWATER HILL RD | PAV,CIP | Yes
IMPLEMENT | 1111819 |  | RSD C W DRAINAGE PRESERVATION | DRN,RSD | No
DESIGN | 1130710 | Final Design | RSD FC 380 PL @SR-164 CDR | DRN,FLD | Yes
CLOSEOUT | 1116885 |  | RSD WOODINVILLE DUVALL ITS | PMD,TRF | No
CLOSEOUT | 1124986 |  | RSD CW HRRRP | PMD,TRF | No
IMPLEMENT | 1125758 |  | RSD W SNOQ VLY RD/NE124-W/D RD | DRN,RSD | No
DESIGN | 1131157 | Implementation | RSD HGH COLLSN SIGHTLINE IMPV | PMD,TRF | Yes
IMPLEMENT | 1127273 |  | RSD FAILED ENV & HVAC REHAB | FAC,REH | Yes
DESIGN | 1134081 | Final Design | RSD REDMOND RIDGE DR NE RNDABT | PMD,RND | Yes
CLOSEOUT | 1127590 |  | RSD 212 AV SE FLD RSK RDUCTN | DRN,RSD | No
IMPLEMENT | 1129582 |  | RSD EMERGENT NEED 3855 | FIN,CIP | No
IMPLEMENT | 1129583 |  | RSD GRANT CONTINGENCY 3855 | FIN,CIP | No
IMPLEMENT | 1129584 |  | RSD CWP QUICK RESPONSE | FIN,CIP | No
IMPLEMENT | 1129585 |  | RSD CWP ROADWAY PRESERVATION | PAV,CIP | No
IMPLEMENT | 1129586 |  | RSD CWP DRAINAGE PRESERVATION | DRN,RSD | No
DESIGN | 1135046 | #N/A | RSD MAINT HDQTRS BLDG D REHAB | FAC,REH | Yes
IMPLEMENT | 1129588 |  | RSD CWP BRIDGE PRIORITY MAINT | BRG,BPM | No
IMPLEMENT | 1129590 |  | RSD CWP HIGH COLLISION SAFETY | PMD,TRF | No
IMPLEMENT | 1129591 |  | RSD CWP SCHOOL ZONE SAFETY | PMD,TRF | No
IMPLEMENT | 1129592 |  | RSD EMERGENT NEED 3865 | FIN,CIP | No
IMPLEMENT | 1129593 |  | RSD GRANT CONTINGENCY 3865 | FIN,CIP | No
DESIGN | 1135997 | Implementation | RSD COAL CREEK BRG 3035A REPL | Not Assigned | Yes
DESIGN | 1135998 | Final Design | RSD AMES LK TRS BRG 1320A REPL | Not Assigned | Yes
DESIGN | 1135999 | Final Design | RSD UPR TOKUL CK BRG 271B REPL | Not Assigned | Yes
DESIGN | 1136001 | Implementation | RSD 277TH ST BRG 3126 REPL | Not Assigned | Yes
DESIGN | 1136580 | Implementation | RSD S 360TH ST SCHOOL PTHWY | PMD,TRF | Yes
DESIGN | 1137862 | Implementation | RSD 2020 HGH FRCTN SFC TRTMT | PMD,TRF | Yes
IMPLEMENT | 1129716 |  | RSD DIVISION 1 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129717 |  | RSD DIVISION 2 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129718 |  | RSD DIVISION 3 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129720 |  | RSD DIVISION 4 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129721 |  | RSD DIVISION 5 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129722 |  | RSD DIVISION 6 DRAINAGE | DRN,RSD | No
IMPLEMENT | 1129723 |  | RSD DIVISION 1 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129724 |  | RSD DIVISION 2 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129725 |  | RSD DIVISION 3 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129726 |  | RSD DIVISION 4 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129727 |  | RSD DIVISION 5 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129728 |  | RSD DIVISION 6 SHOULDERING | DRN,RSD | No
IMPLEMENT | 1129841 |  | RSD CIP OVERSIGHT 3855 | FIN,CIP | No
IMPLEMENT | 1130303 |  | RSD CIP OVERSIGHT 3865 | FIN,CIP | No
DESIGN | Test-RSD | #N/A | Test | BRG,BPM | Yes
IMPLEMENT | 1130707 |  | RSD FC 162 AVE SE @ SE 166 CT | DRN,FLD | Yes
CLOSEOUT | 1130708 |  | RSD FC DAVID POWELL RD RPR | DRN,FLD | Yes
CLOSEOUT | 1130962 |  | RSD BLK DMND-RVNSDL RD SLD RPR | FIN,CIP | No
CLOSEOUT | 1131132 |  | RSD 2017-18 NEW GRDL CONSTRUCT | PMD,RD | Yes
IMPLEMENT | 1131162 |  | RSD HGH COLLSN SIGNAL MOD | PMD,TRF | No
CLOSEOUT | 1131163 |  | RSD HGH FRICTION SURF TMT | PMD,TRF | Yes
HOLD | 1131236 |  | RSD S LANGSTON RD&59 AV RNDABT | PMD,RND | No
IMPLEMENT | 1131333 |  | RSD CWP FLOOD CONTROL DISTRICT | DRN,FLD | No
CLOSEOUT | 1131387 |  | RSD 2017 CW PVMNT PRESERVATION | PAV,CIP | Yes
CLOSEOUT | 1131508 |  | RSD DIV 4 FACLTY IMPRVMT 17-18 | FAC,REH | No
IMPLEMENT | 1131557 |  | RSD 17-18 SCHOOL ZONE SAFETY | PMD,TRF | No
IMPLEMENT | 1131582 |  | RSD NE WD/DVL CULVERT REPL | FIN,CIP | Yes
DESIGN | 1127271 | #N/A | RSD PRESTON MAINT FACILITY | FAC,NEW | No
CLOSEOUT | 1131693 |  | RSD UNION HILL@225 BOXCULVRT | DRN,RSD | Yes
DESIGN | 1127589 | Final Design | RSD 165 ST FLD RSK RDUCTN | DRN,RSD | No
PREDESIGN | 1129598 |  | RSD ISS HBRT RD@MAY VLLY IMPRV | PMD,RND | No
PLANNING | 1130705 |  | RSD FC SNQ VLY MJR FL MIT STDY | DRN,FLD | No
CLOSEOUT | 1132958 |  | RSD 15 MILE BRDG #1384A LOAD | FIN,CIP | No
CLOSEOUT | 1133219 |  | RSD VASHON HWY SW PAVE PRES | PAV,CIP | Yes
CLOSEOUT | 1133220 |  | RSD 2018 CNTYWDE PAVE PRES | PAV,CIP | Yes
CLOSEOUT | 1133413 |  | RSD SE SAWYER RDG OVERLAY | PAV,CIP | No
CLOSEOUT | 1133440 |  | RSD MOUNT VIEW RD REPAIR | FIN,CIP | No
CLOSEOUT | 1133600 |  | RSD FC FIFTEEN ML CR BRG #493C | DRN,FLD | No
CLOSEOUT | 1133757 |  | RSD 2018 BITUM SURF TREATMENT | PAV,CIP | Yes
CLOSEOUT | 1133864 |  | RSD NE NVLTY HILL RD TRAIL | FIN,CIP | No
PLANNING | 1130706 |  | RSD FC NE8ST@ALLEN LAKE OUTLET | DRN,FLD | No
DESIGN | 1131235 | Final Design | RSD S 360ST&MILITARY RD RNDABT | PMD,RND | No
DESIGN | 1131511 | Final Design | RSD SAHALEE WY NE 46000 BLK | DRN,RSD | No
IMPLEMENT | 1134082 |  | RSD FACILITIES LED CONVERSION | FAC,REH | No
DESIGN | 1131526 | Final Design | RSD SE PTRVSKY & 134 A SE | DRN,RSD | No
IMPLEMENT | 1134093 |  | RSD CWP TRAFFIC SAFETY | PMD,TRF | No
LAND | 1135042 |  | RSD VASHON MAINT FACILITY REPL | FAC,NEW | No
LAND | 1135043 |  | RSD NE MAINT FACILITY REPL | FAC,NEW | No
DESIGN | 1131671 | Final Design | RSD SE PTRVSKY @ 151ST A SE | DRN,RSD | No
IMPLEMENT | 1135045 |  | RSD CWP CLVRT RPLCMT FISH PASS | DRN,FPP | No
DESIGN | 1131672 | Final Design | RSD SE PTRVSKY @20300BLK | DRN,RSD | No
IMPLEMENT | 1135073 |  | RSD CWP 2019-20 BRIDGE SAFETY | BRG,BSP | No
PLANNING | 1132446 |  | RSD S LANGSTN RD@132ST DRG IMP | DRN,RSD | No
PREDESIGN | 1132448 |  | RSD SW 108ST@10 AVE SW DRG IMP | DRN,RSD | No
PREDESIGN | 1132523 |  | RSD GREEN RVR RD S28728 DR IMP | DRN,RSD | No
DESIGN | 1132710 | Final Design | RSD DRAIN IMP SAHALEE-4800 | DRN,RSD | No
CLOSEOUT | 1136084 |  | RSD 2019-20 NEW GRDRAIL CONST | PMD,RD | Yes
IMPLEMENT | 1136085 |  | RSD 2019-20 GUARDRAIL PRESRVTN | PMD,RD | Yes
PLANNING | 1134079 |  | RSD KENTKANGLEY LNDSBRG RNDABT | PMD,RND | No
PLANNING | 1134080 |  | RSD WDDUV SNOQ VALLEY IMPROVE | PMD,RD | No
PLANNING | 1134083 |  | RSD COVINGTON WAY SE IMPROVE | PMD,RD | No
PLANNING | 1135044 |  | RSD PRSTN MAINT FACILTY BLDOUT | FAC,NEW | No
DESIGN | 1136000 | Final Design | RSD BARING BRG 509A REPL | Not Assigned | No
DESIGN | 1136086 | Final Design | RSD 218TH AV SE RECONSTRUCTION | PAV,CIP | No
DESIGN | 1136228 | #N/A | RSD PET RD AT 134TH CULVERT | DRN,FPP | No
PREDESIGN | 1136229 |  | RSD 180TH AT 408TH CULVERT | DRN,FPP | No
PLANNING | 1136230 |  | RSD FAIRWOOD E OF 151 CULVERT | DRN,FPP | No
PREDESIGN | 1136231 |  | RSD 185TH AT 179TH CULVERT | DRN,FPP | No
DESIGN | 1136232 | Final Design | RSD 18430 NE 128TH WY CULVERT | DRN,FPP | No
DESIGN | 1136233 | Final Design | RSD LAKE JOY AT 118TH CULVERT | DRN,FPP | No
PREDESIGN | 1136234 |  | RSD WD DUV AT 172ND CULVERT | DRN,FPP | No
IMPLEMENT | 1136241 |  | RSD 28278 GREEN RVR RD CULVERT | DRN,FPP | No
IMPLEMENT | 1136351 |  | RSD CURB RAMP REPLACEMENT 3855 | PAV,CIP | No
IMPLEMENT | 1136352 |  | RSD 2019 CNTYWDE PAVE PRES | PAV,CIP | Yes
DESIGN | 1136235 | Final Design | RSD AVONDALE AND 144TH CULVERT | DRN,FPP | No
DESIGN | 1136236 | Final Design | RSD 165TH AND 176TH CULVERT | DRN,FPP | No
IMPLEMENT | 1136576 |  | RSD 19-20 SCHOOL ZONE SAFETY | PMD,TRF | No
PREDESIGN | 1136237 |  | RSD S 370TH ST CULVERT | DRN,FPP | No
DESIGN | 1136238 | Final Design | RSD 33609 NE 24TH ST CULVERT | DRN,FPP | No
IMPLEMENT | 1136631 |  | RSD JUDD CK BRD 3184 RPR | FIN,CIP | No
PLANNING | 1136239 |  | RSD 317TH AND THOMAS CULVERT | DRN,FPP | No
DESIGN | 1136419 | Final Design | RSD SE 432ND ST CULVERT | DRN,FPP | No
IMPLEMENT | 1136709 |  | RSD TRAFFIC CALMING | PMD,TRF | No
IMPLEMENT | 1136711 |  | RSD ROADWAY LIGHTING | PMD,TRF | No
PLANNING | 1136453 |  | RSD FSH HTCH BRG 61B APRCH RPR | BRG,BPM | No
IMPLEMENT | 1136715 |  | RSD LEFT TURN PHASING | PMD,TRF | No
IMPLEMENT | 1136716 |  | RSD TRANSVERSE RUMBLE SIGNS | PMD,TRF | No
DESIGN | 1136582 | Implementation | RSD S 298TH ST SCHOOL PTHWY | PMD,TRF | No
DESIGN | 1136633 | Implementation | RSD PATTON BRD 3015 BKT RPR | FIN,CIP | No
DESIGN | 1136646 | Implementation | RSD 42ND AVE S SCHOOL PTHWY | PMD,TRF | No
PLANNING | 1136712 |  | RSD RADAR SPEED SIGNS | PMD,TRF | No
IMPLEMENT | 1137509 |  | RSD DOCKTON SEAWALL RPR | FIN,CIP | No
CLOSEOUT | 1137572 |  | RSD REDMOND RIDGE DR NE XNG | FIN,CIP | No
HOLD | 1137577 |  | RSD 304 ST HAUL RD MITGN | FIN,CIP | No
IMPLEMENT | 1137584 |  | RSD MIDDLE FORK RD RPR | FIN,CIP | No
IMPLEMENT | 1137752 |  | RSD FLMNG GYSR BRG 3024 PNTG | BRG,BPM | No
CLOSEOUT | 1137860 |  | RSD 2019 DVD PWLL RD RPR 36621 | FIN,CIP | No
PLANNING | 1136931 |  | RSD SCALE DBASE RPLCMNT | FIN,CIP | No
IMPLEMENT | 1137996 |  | RSD 2020 CNTYWDE PAVE PRES | PAV,CIP | Yes
HOLD | 1138326 |  | RSD 2020 BRIDGE WASHING | BRG,BPM | No
PLANNING | 1136932 |  | RSD BIZDOC MAP VLT RPLCMNT | FIN,CIP | No
PLANNING | 1136933 |  | RSD CUTRL RES DBASE RPLCMNT | FIN,CIP | No
PLANNING | 1137364 |  | RSD WSDE HWY SW DEGRADATN | FIN,CIP | No
IMPLEMENT | 1138763 |  | RSD 2019-20 GUARDRAL PRSRVTN 2 | PMD,RD | No
CLOSEOUT | 1138769 |  | RSD BERRYDALE OX #3086 DECK | BRG,BPM | No
CLOSEOUT | 1138770 |  | RSD DEEP CREEK #364 DECK RPR | BRG,BPM | No
PREDESIGN | 1138330 |  | RSD CVGTN SWYR SGHTLN IMPR | PMD,TRF | No
DESIGN | 1138337 | #N/A | RSD FC FSH HTCHRY BRG 61B RPR | DRN,FLD | No
DESIGN | 1138339 | Final Design | RSD FC S 106 ST DRAINAGE IMPRV | DRN,FLD | No
PREDESIGN | 1138913 |  | RSD BOISE X BRDG #3055A REPL | Not Assigned | No
PREDESIGN | 1138914 |  | RSD FIFTN MILE CRK#493C B REP | Not Assigned | No
PREDESIGN | 1138918 |  | RSD 16TH AVE PED IMPRVMNTS | PMD,TRF | No
PREDESIGN | 1138947 |  | RSD 284TH AVE S 46913 CULVERT | DRN,FPP | No
IMPLEMENT | 1139147 |  | RSD CWP ADA PROGRAM | PAV,CIP | No
IMPLEMENT | 1139236 |  | RSD JUDD CK BRG 3184 RECONT | BRG,BPM | No
PLANNING | 1139144 |  | RSD SE REINIG RD DRNG IMPR CUL | DRN,RSD | No
PLANNING | 1139145 |  | RSD SE GRN VLLY & 218 AVE INT | PMD,RD | No
PLANNING | 1139146 |  | RSD RAINIER S & LKRDG DR INT | PAV,CIP | No
PREDESIGN | 1139286 |  | RSD CWP BRIDGE LOAD UPGRD SFTY | BRG,BSP | No
PREDESIGN | 1139716 |  | RSD S LANGSTN RD@125TH DRG IM | DRN,RSD | No
DESIGN | 1139744 | #N/A | RSD 4-CREEK-RANCH 5044 DECK | BRG,BPM | No
IMPLEMENT | 1139815 |  | RSD 356TH DR SE WINTER 2020 | FIN,CIP | No
NOT SET | 1139749 | #N/A | RSD MMS REPLACEMENT | Not Assigned | No
NOT SET | 1139810 | #N/A | RSD BEALL RD SW RESTOR CULVERT | Not Assigned | No
NOT SET | 1139811 | #N/A | RSD SE384TH DRNG IMPRV CULVERT | Not Assigned | No
PLANNING | 1140858 |  | RSD 244TH AVE NE WINTER 2020 | FIN,CIP | No
PREDESIGN | 1140905 |  | RSD 17401 SE 240 ST SE CULVERT | DRN,FPP | No
PLANNING | 1140906 |  | RSD 156TH SE- SE 240TH CULVERT | DRN,FPP | No
IMPLEMENT | 1141250 |  | RSD 21-22 SCHOOL ZONE SAFETY | PMD,TRF | No
PLANNING | 1141001 |  | RSD NETOLT RD RP WINTER2020 | FIN,CIP | No
DESIGN | 1141044 | #N/A | RSD 2021 CNTYWDE PAVE PRES | PAV,CIP | No
DESIGN | 1141111 | #N/A | RSD 2019-20 GUARDRAL PRSRVTN 3 | PMD,RD | No
NOT SET | 1141401 | #N/A | RSD ROADWAY LIGHTING 2 | PMD,TRF | No
NOT SET | 1141464 | #N/A | RSD BRG LD UP SFTY FSBLTY STDY | BRG,BSP | No
IMPLEMENT | 1141580 |  | RSD 21 HRP AMES LK CARNATION F | PAV,CIP | No
IMPLEMENT | 1141581 |  | RSD 21 HRP ALPENTAL ACCESS RD | PAV,CIP | No
NOT SET | 1141505 | #N/A | RSD 21 BPM RAGNGRVBR1008G RAIL | BRG,BPM | No
IMPLEMENT | 2020-001 |  | DRN DIV DRN | DRN,RSD | No
IMPLEMENT | 2020-002 |  | DRN DIV SHOULDER | DRN,RSD | No
NOT SET | 1141507 | #N/A | RSD 21 BPM WHITNEYBR2025 OVRLY | BRG,BPM | No
NOT SET | 1141509 | #N/A | RSD 21 BPM CEDAR RIVER BRIDGES | BRG,BPM | No
PREDESIGN | 1141625 |  | RSD SE KENT-KANGLEY @LANDSBURG | PMD,TRF | No
PLANNING | 2020-003 |  | PAV Pres Sub | PAV,CIP | No
PLANNING | 2020-004 |  | BRG BPM list | BRG,BPM | No
PLANNING | 2020-005 |  | HIGH COLLISION | PMD,TRF | No
PLANNING | 2020-006 |  | SCHOOL SAFETY | PMD,TRF | No
PLANNING | 2020-007 |  | TRAFFIC SAFETY | PMD,TRF | No
PLANNING | 2021001 |  | RSD AVONDALE RD COTTG LK ELEMT | PMD,TRF | No
PLANNING | 2021002 |  | RSD 21 HRP PLACEHOLDER | PAV,CIP | No
PLANNING | 2021003 |  | RSD 22 HRP PLACEHOLDER | PAV,CIP | No
PLANNING | 2021004 |  | RSD 218 AVE RECON PLACEHOLDER | DRN,RSD | No
PLANNING | 2021005 |  | RSD 2022 CNTYWDE PAVE PRES PLACEHOLDER | PAV,CIP | No
COMPLETE | 1026676 |  | RSD ROOFING ENERGY EFFICIENCY | Not Assigned | No
PLANNING | 2021006 |  | RSD 21 GUARDRAIL PRES PLACEHOLDER | PMD,RD | No
PLANNING | 2021007 |  | RSD 22 GUARDRAIL PRES PLACEHOLDER | PMD,RD | No
NOT SET | 1026677 | #N/A | RSD RNTN BLDG BOND DEBT RTRMT | Not Assigned | No
NOT SET | 1026678 | #N/A | RSD CAP PROJ O S RENTON CIP | Not Assigned | No
NOT SET | 1026726 | #N/A | RSD INFORMATION TECH PROJECTS | Not Assigned | No
NOT SET | 1026727 | #N/A | RSD 100 AV NE NE 132 NE 137 | Not Assigned | No
NOT SET | 1026728 | #N/A | RSD SAFER WILDLIFE COMM MBLTY | Not Assigned | No
NOT SET | 1026729 | #N/A | RSD NOVELTY HL RD ITS ENHNCMT | Not Assigned | No
COMPLETE | 1026732 |  | RSD PATTERSON CREEK BRG #180L | Not Assigned | No
NOT SET | 1026730 | #N/A | RSD NOVELTY HILL RD AVON 238 | Not Assigned | No
NOT SET | 1026731 | #N/A | RSD LK ALICE RD SE CLVRT RPLC | Not Assigned | No
NOT SET | 1026734 | #N/A | RSD PRESTON FC RD SE SLIDE RP | Not Assigned | No
NOT SET | 1026735 | #N/A | RSD W SNOQUALMIE VALLEY RD NE | Not Assigned | No
NOT SET | 1026736 | #N/A | RSD 324 AV NE CULVERT RPLCMNT | Not Assigned | No
NOT SET | 1026737 | #N/A | RSD S 277 ST ITS 55AV S SR167 | Not Assigned | No
NOT SET | 1026738 | #N/A | RSD S STAR LK RD MIL RD 42 AV | Not Assigned | No
NOT SET | 1026739 | #N/A | RSD SOUTH PARK BRG | Not Assigned | No
NOT SET | 1026740 | #N/A | RSD 16A SW ITS SW RXBRY SW116 | Not Assigned | No
NOT SET | 1026742 | #N/A | RSD MILITARY RD S&S 342 ST | Not Assigned | No
NOT SET | 1026789 | #N/A | RSD ALVORD T BRG #3130 DEM | Not Assigned | No
NOT SET | 1026790 | #N/A | RSD NEWAUKUM CRK BRG RPLCMNT | Not Assigned | No
NOT SET | 1026791 | #N/A | RSD SE SUMMIT LANDSBURG RD | Not Assigned | No
NOT SET | 1026792 | #N/A | RSD NEWAUKUM CR BRG #3042 | Not Assigned | No
NOT SET | 1026793 | #N/A | RSD GRN VLY BR-E/O 180 AV NE | Not Assigned | No
NOT SET | 1026794 | #N/A | RSD SE 424 ST BRG RPLCMNT | Not Assigned | No
NOT SET | 1026795 | #N/A | RSD 15 MILE CRK BRG RPLCMENT | Not Assigned | No
NOT SET | 1026796 | #N/A | RSD CIP BOND DEBT PAYMENT | Not Assigned | No
NOT SET | 1026797 | #N/A | RSD HUD DEBT SERVICE PAYMENTS | Not Assigned | No
NOT SET | 1026801 | #N/A | RSD CW GUARDRAIL PROGRAM ADMIN | PMD,TRF | No
NOT SET | 1026802 | #N/A | RSD 2010 C W GUARDRAIL PROJCT | PMD,TRF | No
NOT SET | 1026803 | #N/A | RSD FINANCIAL ADMIN MRSDR1 | FIN,CIP | No
NOT SET | 1026804 | #N/A | RSD PROPERTY SALE COMP PROJ | FIN,CIP | No
NOT SET | 1026805 | #N/A | RSD WA DOT ENCUMBRANCE REVIEW | FIN,CIP | No
NOT SET | 1026853 | #N/A | RSD BRIDGE PRIORITY MTCE ADMIN | Not Assigned | No
NOT SET | 1027150 | #N/A | RSD 2009 NORTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1027151 | #N/A | RSD 2010 NORTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1027152 | #N/A | RSD 2010 SOUTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1027153 | #N/A | RSD 2011 C W OVERLAY PS AND E | PAV,CIP | No
NOT SET | 1027154 | #N/A | RSD ADA PROGRAM ADMIN | PMD,RD | No
NOT SET | 1027155 | #N/A | RSD 2011 ADA-NORTH OVERLAY | PMD,RD | No
NOT SET | 1027156 | #N/A | RSD 2011 ADA-SOUTH OVERLAY | PMD,RD | No
NOT SET | 1027157 | #N/A | RSD 2011 ADA PROGRAM PS&E | PMD,RD | No
COMPLETE | 1027160 |  | RSD BRG PRIORITY MAINTNCE | Not Assigned | No
NOT SET | 1027158 | #N/A | RSD CW ROADWAY PRESERVATION | PAV,CIP | No
NOT SET | 1027159 | #N/A | RSD ADA COMPLIANCE | PMD,RD | No
NOT SET | 1027161 | #N/A | RSD CLEAR ZONE SAFETY PROGRAM | PMD,TRF | No
NOT SET | 1027162 | #N/A | RSD PERMIT MNTRNG&REMEDIATION | Not Assigned | No
NOT SET | 1047572 | #N/A | RSD FAY ROAD RETAINING WALL | Not Assigned | No
NOT SET | 1047573 | #N/A | RSD S 360 ST/SR161-32 AVE S | Not Assigned | No
NOT SET | 1047575 | #N/A | RSD GRN VLLY BR/202P-212AV SE | Not Assigned | No
NOT SET | 1047576 | #N/A | RSD 2011 C/W GUARDRAIL PRJECT | PMD,TRF | No
COMPLETE | 1111172 |  | RSD FACIL PRESERVATION C/WIDE | FAC,REH | No
NOT SET | 1111170 | #N/A | RSD COTTAGE LK CRK BRDGE #240A | Not Assigned | No
NOT SET | 1111171 | #N/A | RSD FACILITIES MASTER PLAN | Not Assigned | No
NOT SET | 1111173 | #N/A | RSD W SNOQ VAL ROADWY REPAIR | Not Assigned | No
NOT SET | 1111174 | #N/A | RSD MILLER RIVER BRDGE REPLCMT | Not Assigned | No
NOT SET | 1111175 | #N/A | RSD KENT KNGLEY RD CLVRT REPL | Not Assigned | No
NOT SET | 1111176 | #N/A | RSD NOVELTY RD AT TRILOGY ADA | PMD,RD | No
NOT SET | 1111177 | #N/A | RSD ISSAQUAH HOBART RD SE | Not Assigned | No
NOT SET | 1111178 | #N/A | RSD UPPER PRESTON RD SE&SE97th | Not Assigned | No
NOT SET | 1111179 | #N/A | RSD DRAINAGE PRESERVATION | DRN,RSD | No
NOT SET | 1111817 | #N/A | RSD SOUTH RGNL MAINT FACILITY | Not Assigned | No
NOT SET | 1111818 | #N/A | RSD 2011 NORTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1111820 | #N/A | RSD PEASLEY CANYON RD AT PC WA | Not Assigned | No
NOT SET | 1111821 | #N/A | RSD 2012 C/W OVERLAY PS&E | PAV,CIP | No
NOT SET | 1111822 | #N/A | RSD RCAMM RDS COMP ASSET AND M | Not Assigned | No
NOT SET | 1111823 | #N/A | RSD 2011 SOUTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1111824 | #N/A | RSD PRESTON FC AT SE HIGH PT | Not Assigned | No
NOT SET | 1111825 | #N/A | RSD RENTON AV SDWLK 75-76 AV | FIN,CIP | No
NOT SET | 1114398 | #N/A | RSD BEAR CREEK BRIDGE #480A | Not Assigned | No
NOT SET | 1114399 | #N/A | RSD AVONDALE RD ITS PHASE 1 | Not Assigned | No
NOT SET | 1114655 | #N/A | RSD W AMES LK DR DRNG IMPVMNTS | DRN,RSD | No
NOT SET | 1114656 | #N/A | RSD CORNELL AVE DRNG IMPRVMNTS | DRN,RSD | No
NOT SET | 1114657 | #N/A | RSD SE408&292AV DRNG IMPVMNTS | DRN,RSD | No
NOT SET | 1114659 | #N/A | RSD DRNG DSGN NE8B/T245P&24800 | DRN,RSD | No
NOT SET | 1114660 | #N/A | RSD DRNG DSGN 3919 S 301 PL | DRN,RSD | No
COMPLETE | 1114791 |  | RSD ROADS-RENTON FACILITY | FIN,CIP | No
NOT SET | 1114789 | #N/A | RSD PROPERTY SALE TRANS COSTS | Not Assigned | No
NOT SET | 1114790 | #N/A | RSD ESS STAFF CONVERSION TRNG | FIN,CIP | No
NOT SET | 1114793 | #N/A | RSD SKYKOMISH SHOP REPAIRS | Not Assigned | No
NOT SET | 1114794 | #N/A | RSD BEACON COAL MINE RD S | PMD,TRF | No
NOT SET | 1114795 | #N/A | RSD BANDARET BRIDGE #493B | Not Assigned | No
NOT SET | 1114796 | #N/A | RSD SE 277 ST BRIDGE #3126 | Not Assigned | No
NOT SET | 1114797 | #N/A | RSD SE 408 ST&292 AVE SE DRNG | DRN,RSD | No
NOT SET | 1114798 | #N/A | RSD COUNTYWIDE OVERLAY ADMIN | PAV,CIP | No
NOT SET | 1114799 | #N/A | RSD ASSET MGMT ASSESSMENT | FIN,CIP | No
NOT SET | 1114800 | #N/A | RSD DOCKTON/ELLISPORT-PORTAGE | FIN,CIP | No
NOT SET | 1114801 | #N/A | RSD GORUSECH RD SLIDE REPAIR | FIN,CIP | No
NOT SET | 1114802 | #N/A | RSD 17 AV SE/SE 100-SW 104 ST | Not Assigned | No
NOT SET | 1114803 | #N/A | RSD MONEY CREEK SCOUR REPAIR | Not Assigned | No
NOT SET | 1114804 | #N/A | RSD RENTON AV S RKRY/SDWLK RPR | FIN,CIP | No
NOT SET | 1114877 | #N/A | RSD DRNG DSGN SW 112&25 AV SW | DRN,RSD | No
NOT SET | 1114878 | #N/A | RSD DRNG DSGN 28841 164 AV SE | DRN,RSD | No
NOT SET | 1114879 | #N/A | RSD DRNG FISH NE165W/O176AV NE | DRN,RSD | No
NOT SET | 1114880 | #N/A | RSD DRNG FISH 20229 NE 198 ST | DRN,RSD | No
NOT SET | 1114881 | #N/A | RSD DRNG FISH SE NWPT E/O152AV | DRN,RSD | No
NOT SET | 1114883 | #N/A | RSD DRNG FISH26428SE KNT-KNGLY | DRN,RSD | No
NOT SET | 1115087 | #N/A | RSD ISSAQUAH NSPAR CONTRBUTION | FIN,CIP | No
NOT SET | 1115090 | #N/A | RSD JUANITA-WOODNVL/NE 160 ITS | Not Assigned | No
NOT SET | 1115091 | #N/A | RSD 100 AV NE ITS/NE132-NE145 | Not Assigned | No
NOT SET | 1115092 | #N/A | RSD MILITARY RD S & S 272 ST | Not Assigned | No
NOT SET | 1115099 | #N/A | RSD MIDDLE FORK SNOQ RIVER RD | Not Assigned | No
NOT SET | 1115104 | #N/A | RSD 2012 C/W GUARDRAIL PROJECT | PMD,TRF | No
NOT SET | 1115106 | #N/A | RSD 2012 NORTH COUNTY OVERLAY | PAV,CIP | No
NOT SET | 1115107 | #N/A | RSD 2012 SOUTH COUNTY OVERLAY | PAV,CIP | No
CANCELLED | 1115237 |  | RSD CW NEAL RD BRIDGE #249C | Not Assigned | No
NOT SET | 1115114 | #N/A | RSD AVONDALE ITS PHASE 2 | Not Assigned | No
NOT SET | 1115235 | #N/A | RSD CW NEAL BRIDGE #249B | Not Assigned | No
NOT SET | 1115238 | #N/A | RSD 312 AVE SE BRIDGE #228F | Not Assigned | No
NOT SET | 1115244 | #N/A | RSD 2012 ADA-NORTH OVERLAY | PMD,RD | No
NOT SET | 1115245 | #N/A | RSD 2012 ADA-SOUTH OVERLAY | PMD,RD | No
NOT SET | 1115246 | #N/A | RSD 2012 ADA PROGRAM-PS&E | PMD,RD | No
NOT SET | 1115252 | #N/A | RSD SE MID FORK SNOQ RIVER RD | Not Assigned | No
NOT SET | 1115255 | #N/A | RSD NE WD/DVL RD@W SNOQ VLY RD | Not Assigned | No
NOT SET | 1115260 | #N/A | RSD BEAR CREEK BRIDGE #333A | Not Assigned | No
NOT SET | 1115264 | #N/A | RSD KENT-BLACK DIAMND&SE292 ST | Not Assigned | No
NOT SET | 1115298 | #N/A | RSD DRNG FISH KERRISTON RD | DRN,RSD | No
NOT SET | 1115299 | #N/A | RSD DRNG DSGN140P NE N/O 16116 | DRN,RSD | No
NOT SET | 1115300 | #N/A | RSD DRNG DSGN SE ISS/FC&DUTHIE | DRN,RSD | No
NOT SET | 1115301 | #N/A | RSD DRNG DSGN 10800 103 AV SW | DRN,RSD | No
NOT SET | 1115302 | #N/A | RSD DRNG DSGN 10800 VASHON HWY | DRN,RSD | No
NOT SET | 1115303 | #N/A | RSD DRNG DSGN 52A S N/O #36622 | DRN,RSD | No
NOT SET | 1115304 | #N/A | RSD DRNG DSGN SE472 E/O #26126 | DRN,RSD | No
NOT SET | 1115305 | #N/A | RSD DRNG FISH 16215 NE 124 ST | DRN,RSD | No
NOT SET | 1115306 | #N/A | RSD DRNG DSGN NE124 W/O 164AV | DRN,RSD | No
NOT SET | 1115307 | #N/A | RSD DRNG DSGN 7240 S 135 ST | DRN,RSD | No
NOT SET | 1115308 | #N/A | RSD DRNG DSGN 13703 SW POHL RD | DRN,RSD | No
NOT SET | 1115309 | #N/A | RSD DRNG DSGN VASHON HWY&SW112 | DRN,RSD | No
NOT SET | 1115310 | #N/A | RSD DRNG VSHN B/T SW112&11018 | DRN,RSD | No
NOT SET | 1115311 | #N/A | RSD DRNG DSGN VSHN HWY@ #11018 | DRN,RSD | No
NOT SET | 1115312 | #N/A | RSD DRNG 45 AV B/T #28125&S282 | DRN,RSD | No
NOT SET | 1115314 | #N/A | RSD DRNG BD-RVNSDL S/O 267A SE | DRN,RSD | No
NOT SET | 1115316 | #N/A | RSD DRNG LKRDG B/T OKWD&11005 | DRN,RSD | No
NOT SET | 1115317 | #N/A | RSD DRNG S LAUREL B/T7589&7615 | DRN,RSD | No
NOT SET | 1115319 | #N/A | RSD DRNG CNSTR S SUNNYCREST RD | DRN,RSD | No
NOT SET | 1115320 | #N/A | RSD DRNG DIXON B/T OKWD&#10831 | DRN,RSD | No
NOT SET | 1115321 | #N/A | RSD DRNG DIXON B/T OKWD&#10631 | DRN,RSD | No
NOT SET | 1115322 | #N/A | RSD DRNG DIXON B/T 10891&10837 | DRN,RSD | No
NOT SET | 1115323 | #N/A | RSD DRNG FOREST AV S&S RUSTIC | DRN,RSD | No
NOT SET | 1115324 | #N/A | RSD DRNG FOREST N/O CRSTWD DR | DRN,RSD | No
NOT SET | 1115325 | #N/A | RSD DRNG FOREST B/T RUSTIC&SUN | DRN,RSD | No
NOT SET | 1115355 | #N/A | RSD DRNG 16506 TIGER MTN RD SE | DRN,RSD | No
NOT SET | 1115369 | #N/A | RSD DRNG TIGER MTN RD&SE 162 P | DRN,RSD | No
NOT SET | 1115379 | #N/A | RSD DRNG 13362 198 AVE NE | DRN,RSD | No
NOT SET | 1115380 | #N/A | RSD DRNG TIGER MTN RD@SE 162 P | DRN,RSD | No
NOT SET | 1115381 | #N/A | RSD DRNG 176 AVE NE&NE 195 ST | DRN,RSD | No
NOT SET | 1115382 | #N/A | RSD DRNG NE UNION HL E/O 247AV | DRN,RSD | No
NOT SET | 1115383 | #N/A | RSD DRNG 17407 155 AVE SE | DRN,RSD | No
NOT SET | 1115384 | #N/A | RSD DRNG NE 100 E/O W SNOQ VLY | DRN,RSD | No
NOT SET | 1115385 | #N/A | RSD DRNG 23020 148 AVE SE | DRN,RSD | No
NOT SET | 1115386 | #N/A | RSD DRNG 268 AV SE S/O SE 411 | DRN,RSD | No
NOT SET | 1115387 | #N/A | RSD DRNG 23621 VASHON HWY S | DRN,RSD | No
NOT SET | 1115388 | #N/A | RSD DRNG SE 187 PL&134 AV SE | DRN,RSD | No
NOT SET | 1115389 | #N/A | RSD DRNG 344 AV NE N/O NE 20 | DRN,RSD | No
NOT SET | 1115390 | #N/A | RSD DRNG SW250WYB/T12002&12128 | DRN,RSD | No
NOT SET | 1115391 | #N/A | RSD DRNG S RUSTIC RD @ #6928 | DRN,RSD | No
NOT SET | 1115392 | #N/A | RSD DRNG CORNELL AV&S SNNYCRST | DRN,RSD | No
NOT SET | 1115393 | #N/A | RSD DRNG 17420 158 AVE SE | DRN,RSD | No
NOT SET | 1115455 | #N/A | RSD SOUTH PK BRIDGE DEMOLITION | Not Assigned | No
NOT SET | 1115473 | #N/A | RSD STOSSEL BRDG#1023A STRNGNG | Not Assigned | No
NOT SET | 1115521 | #N/A | RSD C/W BRIDGE WASHING | Not Assigned | No
NOT SET | 1115566 | #N/A | RSD DUVALL SLOUGH BRDG #1136B | Not Assigned | No
NOT SET | 1115607 | #N/A | RSD W SNOQ VY NE NE124-W/D RD | Not Assigned | No
NOT SET | 1115642 | #N/A | RSD 2012 ADA PROGRAM ADMIN | PMD,RD | No
NOT SET | 1115643 | #N/A | RSD 2012 ADA COUNTYWIDE PS&E | PMD,RD | No
NOT SET | 1115644 | #N/A | RSD 2012 ADA C/W IMPLMNTATION | PMD,RD | No
NOT SET | 1115670 | #N/A | RSD DRNG ORILLIA RD N/O 42AV S | DRN,RSD | No
NOT SET | 1115671 | #N/A | RSD DRNG 10826 RAINIER AVE S | DRN,RSD | No
NOT SET | 1115786 | #N/A | RSD DRNG 196AV SE/#41128-41232 | DRN,RSD | No
NOT SET | 1115789 | #N/A | RSD DRNG 212 AVE SE N/O #37308 | DRN,RSD | No
NOT SET | 1115792 | #N/A | RSD 2012 MAINT DIV 1 O/L PREP | PAV,CIP | No
NOT SET | 1115793 | #N/A | RSD 2012 MAINT DIV 2 O/L PREP | PAV,CIP | No
NOT SET | 1115794 | #N/A | RSD 2012 MAINT DIV 3 O/L PREP | PAV,CIP | No
NOT SET | 1115795 | #N/A | RSD 2012 MAINT DIV 4 O/L PREP | PAV,CIP | No
NOT SET | 1115820 | #N/A | RSD SE NWPRT WY/165P SE-SE42PL | Not Assigned | No
NOT SET | 1115821 | #N/A | RSD DOCKTON ROAD PRESERVATION | Not Assigned | No
NOT SET | 1115840 | #N/A | RSD DRNG S LKRDG/RAINIER-DIXON | DRN,RSD | No
NOT SET | 1115841 | #N/A | RSD DRNG 7728 S LAKERIDGE DR | DRN,RSD | No
NOT SET | 1115850 | #N/A | RSD COUNTYWIDE HMA OVERLAY | PAV,CIP | No
NOT SET | 1116037 | #N/A | RSD 1 PERCENT FOR ART | Not Assigned | No
NOT SET | 1116468 | #N/A | RSD DRNG RPLC 16707 TIGER MTN | DRN,RSD | No
NOT SET | 1116494 | #N/A | RSD DRNG SE 135 ST&184 AVE SE | DRN,RSD | No
NOT SET | 1116495 | #N/A | RSD DRNG CULVRT CRESCENT DR SW | DRN,RSD | No
COMPLETE | 1116541 |  | RSD 181 AV SE&CVNGTN SAWYER RD | Not Assigned | No
NOT SET | 1116496 | #N/A | RSD DRNG W/O 20062 SE 232 ST | DRN,RSD | No
COMPLETE | 1116543 |  | RSD 78 AVE S/S 126-RENTON AV S | Not Assigned | No
NOT SET | 1116540 | #N/A | RSD CAREY CREEK @ 276 AVE SE | Not Assigned | No
NOT SET | 1116542 | #N/A | RSD SE COVINGTON SAWYER ROAD | Not Assigned | No
NOT SET | 1116544 | #N/A | RSD 284 AVE SE BRIDGE #3049 | Not Assigned | No
COMPLETE | 1116547 |  | RSD RENTON AV S/68 AV-74 AV S | Not Assigned | No
NOT SET | 1116545 | #N/A | RSD BERRYDALE OVERCRSNG#3086OX | Not Assigned | No
NOT SET | 1116546 | #N/A | RSD SW CEMETERY RD/BEALL RD SW | Not Assigned | No
NOT SET | 1116623 | #N/A | RSD RAGING RIVER BRIDGE #1008G | Not Assigned | No
NOT SET | 1116637 | #N/A | RSD PROP SALES COMPL PROJ CN | FIN,CIP | No
NOT SET | 1116638 | #N/A | RSD WSDOT COMPL PROJ CN | FIN,CIP | No
NOT SET | 1116639 | #N/A | RSD FINANCE ADM COMPL PROJ CN | FIN,CIP | No
NOT SET | 1116640 | #N/A | RSD PROP SALES COMPL PROJ PRS | FIN,CIP | No
NOT SET | 1116641 | #N/A | RSD WSDOT COMPL PROJ PRS | FIN,CIP | No
NOT SET | 1116642 | #N/A | RSD FINANCE ADM COMPL PROJ PRS | FIN,CIP | No
NOT SET | 1116643 | #N/A | RSD PROP SALES COMPL PROJ MTC | FIN,CIP | No
NOT SET | 1116651 | #N/A | RSD WSDOT COMPL PROJ MTC | FIN,CIP | No
NOT SET | 1116652 | #N/A | RSD FINANCE ADM COMPL PROJ MTC | FIN,CIP | No
NOT SET | 1116804 | #N/A | RSD CONTRACTOR INT PYMTS ABT | FIN,CIP | No
NOT SET | 1116806 | #N/A | RSD ESS CIP TRKNG TOOL DVLPMNT | FIN,CIP | No
NOT SET | 1116870 | #N/A | RSD LANDSBURG BRDG S APPROACH | Not Assigned | No
COMPLETE | 1116888 |  | RSD SW ROXBURY/28 AV-30 AV SW | PMD,TRF | No
NOT SET | 1116886 | #N/A | RSD TATE CREEK BRIDGE #122N | Not Assigned | No
NOT SET | 1116887 | #N/A | RSD 14 AV SW/SW 110-SW 114 ST | Not Assigned | No
NOT SET | 1116894 | #N/A | RSD DRNG MTCE RPR 204 PL NE | DRN,RSD | No
NOT SET | 1116938 | #N/A | RSD NE 124 ST ITS PHASE II | Not Assigned | No
NOT SET | 1116945 | #N/A | RSD ISSQ-HBRT RD SE/15 ML BRDG | Not Assigned | No
NOT SET | 1116956 | #N/A | RSD NE WOOD-DVL@AVONDALE RD NE | Not Assigned | No
NOT SET | 1117147 | #N/A | RSD WESTSIDE HWY SHOULDER PREP | PMD,TRF | No
NOT SET | 1117165 | #N/A | RSD DRNIMPRV-6 AV SW S/O SW102 | DRN,RSD | No
NOT SET | 1117166 | #N/A | RSD DRNIMPRV-18627 MAXWELL SE | DRN,RSD | No
NOT SET | 1117245 | #N/A | RSD DRNIMPRV-SE LK DOROTHY RD | DRN,RSD | No
NOT SET | 1117246 | #N/A | RSD DRNIMPRV-S342B/T44AV&4225 | DRN,RSD | No
NOT SET | 1117247 | #N/A | RSD DRNIMPRV-SE KERRISTON RD | DRN,RSD | No
NOT SET | 1117248 | #N/A | RSD DRNIMPRV-SE MAY VLY&176 AV | DRN,RSD | No
NOT SET | 1117249 | #N/A | RSD DRNIMPRV-15A SW&SW RXBY ES | DRN,RSD | No
NOT SET | 1117250 | #N/A | RSD DRNIMPRV-15A SW&SW RXBY WS | DRN,RSD | No
NOT SET | 1117251 | #N/A | RSD DRNIMPRV-17306 TIGER MT RD | DRN,RSD | No
NOT SET | 1117252 | #N/A | RSD DRNIMPRV-16 AV SW&SW106 ST | DRN,RSD | No
NOT SET | 1117253 | #N/A | RSD DRNIMPRV-TIGER MTN RD SE | DRN,RSD | No
NOT SET | 1117254 | #N/A | RSD DRNIMPRV-204PL NE S/O 6019 | DRN,RSD | No
NOT SET | 1117830 | #N/A | RSD SCOUR RPRS BRDGS 3066&3068 | Not Assigned | No
NOT SET | 1117869 | #N/A | RSD MRSDR1-SE 408 ST BRDG 3056 | FIN,CIP | No
NOT SET | 1117870 | #N/A | RSD MRSDR1 RESERVED ONE MAINT | FIN,CIP | No
NOT SET | 1118099 | #N/A | RSD 2012 GO BONDS | Not Assigned | No
NOT SET | 1118131 | #N/A | RSD OPER TO CIP EXPEND CORRECT | DRN,RSD | No
NOT SET | 1118226 | #N/A | RSD LK ALICE RD OVERFLOW PIPE | FIN,CIP | No
NOT SET | 1118634 | #N/A | RSD C/W OVERLAY ADMINISTRATION | PAV,CIP | No
NOT SET | 1118635 | #N/A | RSD NE 124 ST OVERLAY | PAV,CIP | No
NOT SET | 1118636 | #N/A | RSD S 288 STREET OVERLAY | PAV,CIP | No
NOT SET | 1118637 | #N/A | RSD ISSAQUAH-HBRT RD OVERLAY | PAV,CIP | No
NOT SET | 1118638 | #N/A | RSD SE MAY VALLEY ROAD OVERLAY | PAV,CIP | No
NOT SET | 1118664 | #N/A | RSD SPPARO TO CIP EXPEND CORR | FIN,CIP | No
NOT SET | 1118689 | #N/A | RSD COAL CRK BRIDGE #3035A RPR | Not Assigned | No
NOT SET | 1118796 | #N/A | RSD EMER RPR 269WY/NE116-272NE | FIN,CIP | No
NOT SET | 1119111 | #N/A | RSD CAP PROJ OS O/L & DRAINAGE | FIN,CIP | No
NOT SET | 1119296 | #N/A | RSD 2013 DIV 1 DRAINAGE PRESRV | DRN,RSD | No
NOT SET | 1119297 | #N/A | RSD 2013 DIV 2 DRAINAGE PRESRV | DRN,RSD | No
NOT SET | 1119298 | #N/A | RSD 2013 DIV 3 DRAINAGE PRESRV | DRN,RSD | No
NOT SET | 1119299 | #N/A | RSD 2013 DIV 4 DRAINAGE PRESRV | DRN,RSD | No
NOT SET | 1119414 | #N/A | RSD C/W DRAINAGE PRES PRGM ADM | DRN,RSD | No
NOT SET | 1120153 | #N/A | RSD 2013 COUNTYWIDE GUARDRAIL | PMD,TRF | No
NOT SET | 1120167 | #N/A | RSD 2013 ADA PTRVSKY RETRO IMP | PMD,RD | No
NOT SET | 1120168 | #N/A | RSD 2013 ADA PTRVSKY RTRO PS&E | PMD,RD | No
NOT SET | 1120169 | #N/A | RSD 2013 ADA S 288 RETRO IMP | PMD,RD | No
NOT SET | 1120170 | #N/A | RSD 2013 ADA S 288 RETRO PS&E | PMD,RD | No
NOT SET | 1120319 | #N/A | RSD O/L PREP ISSQ-HOBART RD SE | PAV,CIP | No
NOT SET | 1120320 | #N/A | RSD O/L PREP SE MAY VALLEY RD | PAV,CIP | No
NOT SET | 1120321 | #N/A | RSD OVERLAY PREP NE 124TH ST | PAV,CIP | No
NOT SET | 1120322 | #N/A | RSD OVERLAY PREP S 288TH ST | PAV,CIP | No
NOT SET | 1120867 | #N/A | RSD BARING BRG#509A TIMBER RPR | Not Assigned | No
NOT SET | 1121109 | #N/A | RSD SWIP VASHON HY SEAWALL RPR | DRN,RSD | No
NOT SET | 1121138 | #N/A | RSD 2013 OVERLAY S 288 ST ADA | PAV,CIP | No
NOT SET | 1121139 | #N/A | RSD 2013 OVERLAY NE 124 ST ADA | PAV,CIP | No
NOT SET | 1121140 | #N/A | RSD 2013 OVERLAY ISSQ-HBRT ADA | PAV,CIP | No
NOT SET | 1121141 | #N/A | RSD 2013 O/L SE MAY VALLEY ADA | PAV,CIP | No
NOT SET | 1121203 | #N/A | RSD C/W HPG STRMWTR RTRFT PRGM | DRN,RSD | No
NOT SET | 1121224 | #N/A | RSD RIVERBEND 444 AV SE&SE 151 | DRN,RSD | No
NOT SET | 1121428 | #N/A | RSD CLOUGH CRK STREAM IMPRVMNT | DRN,RSD | No
NOT SET | 1121437 | #N/A | RSD LK DOROTHY BRDG DECK REHAB | Not Assigned | No
NOT SET | 1121601 | #N/A | RSD NE 80 FARM DITCHES DRNG | DRN,RSD | No
NOT SET | 1121699 | #N/A | RSD PRESTON-FC RD GRNDWTR C/O | DRN,RSD | No
NOT SET | 1121701 | #N/A | RSD NE STOSSEL CRK DRNG IMPRV | DRN,RSD | No
COMPLETE | 1121897 |  | RSD BRAC FOSS RVR BRDG #2605A | Not Assigned | No
NOT SET | 1121702 | #N/A | RSD NE MONEY CRK RD DRNG IMPRV | DRN,RSD | No
COMPLETE | 1121899 |  | RSD BRAC BRISSACK BRDG #1116A | Not Assigned | No
COMPLETE | 1121900 |  | RSD BRAC MONEY CRK BRDG #506A | Not Assigned | No
NOT SET | 1121776 | #N/A | RSD KERRISTON RD DRNG IMPRVMNT | DRN,RSD | No
NOT SET | 1121898 | #N/A | RSD BRAC LK DOROTHY BRDG #359B | Not Assigned | No
NOT SET | 1121901 | #N/A | RSD BRAC STOSSEL BRIDGE #1023A | Not Assigned | No
NOT SET | 1122199 | #N/A | RSD PATTERSON CK BRDG 180L ART | FIN,CIP | No
NOT SET | 1122200 | #N/A | RSD NEWAUKUM CK BRDG 3040A ART | FIN,CIP | No
NOT SET | 1122309 | #N/A | RSD 2014 COUNTYWIDE GUARDRAIL | PMD,TRF | No
NOT SET | 1122327 | #N/A | RSD N FORK BRG #1221 SCOUR RPR | FIN,CIP | No
NOT SET | 1122354 | #N/A | RSD KERRISTON RD CULVERT IMPV | DRN,RSD | No
NOT SET | 1122355 | #N/A | RSD CEDAR GROVE WTR QLTY IMPRV | DRN,RSD | No
NOT SET | 1122356 | #N/A | RSD AVONDALE RD WTR QLTY IMPVR | DRN,RSD | No
NOT SET | 1122727 | #N/A | RSD 2014 DRAINAGE PRES PRG ADM | DRN,RSD | No
NOT SET | 1122728 | #N/A | RSD 2014 DIV 1 DRNG PRES PRGM | DRN,RSD | No
NOT SET | 1122729 | #N/A | RSD 2014 DIV 2 DRNG PRES PRGM | DRN,RSD | No
NOT SET | 1122730 | #N/A | RSD 2014 DIV 3 DRNG PRES PRGM | DRN,RSD | No
NOT SET | 1122731 | #N/A | RSD 2014 DIV 4 DRNG PRES PRGM | DRN,RSD | No
NOT SET | 1122907 | #N/A | RSD SE JONES RD DRNG IMPRVMNTS | DRN,RSD | No
NOT SET | 1122908 | #N/A | RSD NUDIST CAMP CRK STRM IMPV | DRN,RSD | No
NOT SET | 1122909 | #N/A | RSD PEASLEY CNYN DRNG IMPRVMNT | DRN,RSD | No
NOT SET | 1122910 | #N/A | RSD NORTH FORK RD DRNG IMPRVMT | DRN,RSD | No
NOT SET | 1122911 | #N/A | RSD MIDDLE FORK DRNG IMPRVMENT | DRN,RSD | No
COMPLETE | 1123047 |  | RSD 2014 ADA PROGRAM PS&E | PMD,RD | No
NOT SET | 1122912 | #N/A | RSD WILDERNESS RIM DRNG IMPVMT | DRN,RSD | No
NOT SET | 1122928 | #N/A | RSD ELK RUN BUYOUT | Not Assigned | No
NOT SET | 1123183 | #N/A | RSD DOCKTON ROAD DRNG IMPRVMNT | DRN,RSD | No
NOT SET | 1123184 | #N/A | RSD BLK DMD-RAVENSDALE RD DRNG | DRN,RSD | No
NOT SET | 1123319 | #N/A | RSD 2014 C/W HT MIX ASPHLT O/L | PAV,CIP | No
COMPLETE | 1123718 |  | RSD SE MAY VALLEY RD EMERG RPR | FIN,CIP | No
COMPLETE | 1123719 |  | RSD W SNOQ VLLY EMER SLIDE RPR | FIN,CIP | No
NOT SET | 1123351 | #N/A | RSD SE DAVID POWELL RD DRG IMP | DRN,RSD | No
NOT SET | 1123362 | #N/A | RSD WASHOUT RPR MAXWELL RD | FIN,CIP | No
NOT SET | 1123787 | #N/A | RSD CIP CONST BR 3 TEMPLATE | Not Assigned | No
COMPLETE | 1123869 |  | RSD GREEN RVR RD EMERG SLD RPR | FIN,CIP | No
NOT SET | 1123800 | #N/A | RSD CIP PRES BR 3 TEMPLATE | Not Assigned | No
NOT SET | 1123801 | #N/A | RSD CIP MAINT BR 3 TEMPLATE | Not Assigned | No
NOT SET | 1123870 | #N/A | RSD ISSQ CRK BRIDGE #1741A RPR | Not Assigned | No
NOT SET | 1123871 | #N/A | RSD CHERRY VLY TRSL BR267X O/L | Not Assigned | No
NOT SET | 1123872 | #N/A | RSD DUVALL BRDG #1136 A&B RPR | Not Assigned | No
NOT SET | 1123878 | #N/A | RSD 2014 O/L PREP SE 240 ST | PAV,CIP | No
NOT SET | 1123879 | #N/A | RSD 2014 O/L PREP 276 AVE SE | PAV,CIP | No
NOT SET | 1123880 | #N/A | RSD 2014 O/L PREP SE 416 ST | PAV,CIP | No
NOT SET | 1123881 | #N/A | RSD 2014 O/L PRP PRESTON-FC RD | PAV,CIP | No
NOT SET | 1123882 | #N/A | RSD 2014 O/L PRP SE204/LK YNGS | PAV,CIP | No
NOT SET | 1123883 | #N/A | RSD 2014 OL PRP A-BD GRN RV BR | PAV,CIP | No
NOT SET | 1123884 | #N/A | RSD 2014 OL PRP AUB-BD LK HOLM | PAV,CIP | No
NOT SET | 1123885 | #N/A | RSD 2014 O/L PREP SE244/152AVE | PAV,CIP | No
NOT SET | 1123905 | #N/A | RSD 2014 O/L PRP W SNOQ VLY RD | PAV,CIP | No
NOT SET | 1124001 | #N/A | RSD CLEAR ZONE SAFETY | PMD,TRF | No
NOT SET | 1124061 | #N/A | RSD 148 AV SE RD RECONSTRCTION | Not Assigned | No
NOT SET | 1124072 | #N/A | RSD SUMMIT PIT RELOCATION CIP | Not Assigned | No
NOT SET | 1124103 | #N/A | RSD GREEN RIVER RD SLD RPR IPR | FIN,CIP | No
COMPLETE | 1124491 |  | RSD 2015/16 RDWY LGT LED CONV | Not Assigned | No
NOT SET | 1124135 | #N/A | RSD SE 456 WY WASHOUT W/O 212 | DRN,RSD | No
NOT SET | 1124419 | #N/A | RSD ELK RUN BUY OUT | Not Assigned | No
NOT SET | 1124602 | #N/A | RSD 2014 BEAVER DECEIVER | DRN,RSD | No
NOT SET | 1124637 | #N/A | RSD KELLY RD BRG 5007 RAIL RPR | Not Assigned | No
NOT SET | 1124657 | #N/A | RSD NE 127 ST CULVERT RPLCMNT | DRN,RSD | No
NOT SET | 1124658 | #N/A | RSD NE UNION HILLRD CULVT RPLT | DRN,RSD | No
NOT SET | 1124800 | #N/A | RSD MAXWELL RD WASHOUT REPAIR | FIN,CIP | No
NOT SET | 1124801 | #N/A | RSD SLIDE RPR34519 D POWELL RD | FIN,CIP | No
NOT SET | 1124820 | #N/A | RSD B BLDG ROOF RPLC&IMPRVMNTS | FAC,REH | No
NOT SET | 1124823 | #N/A | RSD KANASKET ARCH BR#3036 RPRS | Not Assigned | No
NOT SET | 1124836 | #N/A | RSD RENTON AV S/75 AV-S 126 ST | FIN,CIP | No
COMPLETE | 1124962 |  | RSD SKY RV BR #999Z(MNY CK)RPR | BRG,EP | Yes
NOT SET | 1124847 | #N/A | RSD SOUTH PARK BRIDGE 1% ART | FIN,CIP | No
NOT SET | 1124935 | #N/A | RSD GRDRL SE MAY VLLY&ISSQ-HBT | PMD,TRF | No
NOT SET | 1124964 | #N/A | RSD OLD CASCDE/MILLER RVR WEST | Not Assigned | No
NOT SET | 1124965 | #N/A | RSD OLD CASCDE/MILLER RVR EAST | Not Assigned | No
COMPLETE | 1124968 |  | RSD KC 2014 SFTY HF SURF TRMTS | PMD,TRF | Yes
COMPLETE | 1124969 |  | RSD GUARDRAIL INSTL/HAZRD RMVL | PMD,TRF | No
NOT SET | 1124966 | #N/A | RSD MILLER RVR BANK PROTECTION | Not Assigned | No
COMPLETE | 1125296 |  | RSD S 96 ST&8 AVE S SINKHOLE | FIN,CIP | Yes
NOT SET | 1124967 | #N/A | RSD MILLER RIVER BRDGE REMOVAL | Not Assigned | No
NOT SET | 1125069 | #N/A | RSD KELLY BR 5007 RAIL UPGRD | PMD,TRF | No
NOT SET | 1125330 | #N/A | RSD CIP CONST BR 1&2 TEMPLATE | Not Assigned | No
NOT SET | 1125331 | #N/A | RSD CIP PRES BR 1&2 TEMPLATE | Not Assigned | No
NOT SET | 1125333 | #N/A | RSD 2015/16 DRNG PRES PGM ADM | DRN,RSD | No
NOT SET | 1125336 | #N/A | RSD 2015/16 DIV1 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125337 | #N/A | RSD 2015/16 DIV2 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125338 | #N/A | RSD 2015/16 DIV3 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125339 | #N/A | RSD 2015/16 DIV4 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125340 | #N/A | RSD 2015/16 DIV5 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125341 | #N/A | RSD 2015/16 DIV6 DRNG PRES PGM | DRN,RSD | No
NOT SET | 1125549 | #N/A | RSD MAINTENANCE PIT RELOCATION | FAC,REH | No
NOT SET | 1125550 | #N/A | RSD MAP CENTER RELOCATION | FAC,REH | No
NOT SET | 1125757 | #N/A | RSD 2015/16 DIV 4 SHLDR RECON | DRN,RSD | No
NOT SET | 1125784 | #N/A | RSD RENTON FACILITY IMPRVMENTS | FAC,REH | No
NOT SET | 1125785 | #N/A | RSD DIV2/DIV6 FACILITY IMPRVNT | FAC,REH | No
NOT SET | 1125786 | #N/A | RSD DIV 4 FACILITY IMPROVMENTS | FAC,REH | No
NOT SET | 1125789 | #N/A | RSD 2015/16 DIV 1 SHLDR RECON | DRN,RSD | No
NOT SET | 1125790 | #N/A | RSD 2015/16 DIV 2 SHLDR RECON | DRN,RSD | No
NOT SET | 1125791 | #N/A | RSD 2015/16 DIV 3 SHLDR RECON | DRN,RSD | No
NOT SET | 1125792 | #N/A | RSD 2015/16 DIV 5 SHLDR RECON | DRN,RSD | No
NOT SET | 1125793 | #N/A | RSD 2015/16 DIV 6 SHLDR RECON | DRN,RSD | No
NOT SET | 1125862 | #N/A | RSD HIGH RISK PAVEMENT TRTMNT | PAV,CIP | No
NOT SET | 1125863 | #N/A | RSD A BLDG ROOF REPLACEMENT | FAC,REH | No
NOT SET | 1126042 | #N/A | RSD BVR DCVR 36900 MLTRY RD S | DRN,RSD | No
NOT SET | 1126043 | #N/A | RSD BEAVER DECEIVER 437 AVE SE | DRN,RSD | No
NOT SET | 1126178 | #N/A | RSD BVR DCVR 180XX 185 AVE NE | DRN,RSD | No
COMPLETE | 1126280 |  | RSD HGH RISK PVMT RENTON AVE S | PAV,CIP | No
NOT SET | 1126227 | #N/A | RSD HGH RSK PVMT 68A S - SR900 | PAV,CIP | No
NOT SET | 1126268 | #N/A | RSD HGH RISK PVMT S132-S133 ST | PAV,CIP | No
NOT SET | 1126281 | #N/A | RSD HGH RISK PVMT NE NVLTY HLL | PAV,CIP | No
NOT SET | 1126282 | #N/A | RSD HGH RISK PVMT 238 AVE NE | PAV,CIP | No
NOT SET | 1126283 | #N/A | RSD HGH RISK PVMT 236 AVE NE | PAV,CIP | No
NOT SET | 1126284 | #N/A | RSD HGH RISK PVMT SAHALEE WAY | PAV,CIP | No
NOT SET | 1126285 | #N/A | RSD HGH RISK PVMT 244 AVE NE | PAV,CIP | No
NOT SET | 1126286 | #N/A | RSD HGH RSK PVT 148AV/140PL NE | PAV,CIP | No
NOT SET | 1126287 | #N/A | RSD HGH RISK PVMT SE 232 ST | PAV,CIP | No
NOT SET | 1126288 | #N/A | RSD HGH RISK PVMT 140 AVE SE | PAV,CIP | No
NOT SET | 1126373 | #N/A | RSD COUNTYWIDE BRIDGE WASHING | Not Assigned | No
NOT SET | 1126430 | #N/A | RSD DUVALL BRIDGE APPROACH | FIN,CIP | No
COMPLETE | 1126436 |  | RSD NE UNION HILL RD&225 AV NE | DRN,RSD | No
CANCELLED | 1126437 |  | RSD XPIPE 16215 NE 124 ST | DRN,RSD | No
COMPLETE | 1126438 |  | RSD XPIPE NE 124 ST&164 AVE NE | DRN,RSD | Yes
NOT SET | 1126434 | #N/A | RSD SKYKOMISH FACILITY LIGHTNG | FAC,REH | No
NOT SET | 1126435 | #N/A | RSD XPIPE 185 AV N/O NE179ST | DRN,RSD | No
COMPLETE | 1126441 |  | RSD S 96 ST STORMWATER PIPES | DRN,RSD | Yes
NOT SET | 1126439 | #N/A | RSD XPIPE GREEN RVR RD&94 PL S | DRN,RSD | No
COMPLETE | 1126443 |  | RSD CROSSPIPE 229 DRIVE SE | DRN,RSD | No
NOT SET | 1126440 | #N/A | RSD W VALLEY HIGHWAY CULVERTS | DRN,RSD | No
NOT SET | 1126442 | #N/A | RSD 284 AV SE&VZ/CMBRLND RD | DRN,RSD | No
NOT SET | 1126889 | #N/A | RSD BARING BRDG#509A TWR SPPT | FIN,CIP | No
NOT SET | 1127129 | #N/A | RSD 2016 O/L S 320 PEASLEY CYN | PAV,CIP | No
COMPLETE | 1127270 |  | RSD CW SNOW&ICE MTRLS STORAGE | FAC,NEW | No
NOT SET | 1127268 | #N/A | RSD EMERGENT NEED FUND 3850 | FIN,CIP | No
NOT SET | 1127269 | #N/A | RSD GRANT CONTINGNCY FUND 3850 | Not Assigned | No
NOT SET | 1127272 | #N/A | RSD FACILITY SITE DVLPMNT&PLNG | Not Assigned | No
NOT SET | 1127276 | #N/A | RSD CW ROADWAY SAFETY IMPRVMTS | Not Assigned | No
NOT SET | 1127277 | #N/A | RSD BARING BRIDGE #509A | Not Assigned | No
COMPLETE | 1127591 |  | RSD 185 AV NE FLD RSK RDUCTN | DRN,RSD | No
NOT SET | 1127278 | #N/A | RSD BRRYDALE OXING BRDG#3086OX | Not Assigned | No
NOT SET | 1127328 | #N/A | RSD FACILITIES CIP BR 3 | Not Assigned | No
NOT SET | 1127595 | #N/A | RSD 2015 GO BONDS | Not Assigned | No
NOT SET | 1127612 | #N/A | RSD UPPR PRESTON BDG#1239A RPR | Not Assigned | No
NOT SET | 1127613 | #N/A | RSD WYNACO BDG#3194 SCOUR RPR | Not Assigned | No
NOT SET | 1127616 | #N/A | RSD BRRYDL OXING#3086 2015 RPR | Not Assigned | No
NOT SET | 1127617 | #N/A | RSD SE PETROVITSKY RD GDRL ADJ | PMD,TRF | No
NOT SET | 1127699 | #N/A | RSD SLD RPR UPP PRSTN SE/SE 97 | FIN,CIP | No
NOT SET | 1127885 | #N/A | RSD SNOW&ICE MTRL STRG DESIGN | FAC,NEW | No
NOT SET | 1128143 | #N/A | RSD 2015/16 CW RS OBSTCLE RMVL | PMD,TRF | No
NOT SET | 1128945 | #N/A | RSD RD RPR UPP PRSTN SE/SE 97 | FIN,CIP | No
NOT SET | 1128968 | #N/A | RSD SE RETREAT KNSKT GDRL ADJ | PMD,TRF | No
NOT SET | 1128969 | #N/A | RSD NE WD/DVL RD GDRL ADJ | PMD,TRF | No
NOT SET | 1128970 | #N/A | RSD PRSTN-FC RD GDRL ADJ | PMD,TRF | No
NOT SET | 1128971 | #N/A | RSD NE 133 ST GDRL ADJ | PMD,TRF | No
NOT SET | 1129074 | #N/A | RSD SE 400 WAY GUARDRAIL ADJ | PMD,TRF | No
NOT SET | 1129075 | #N/A | RSD SE 416 ST GUARDRAIL ADJ | PMD,TRF | No
COMPLETE | 1129290 |  | RSD DOCKTON RD SW EROSN PROT | FIN,CIP | No
NOT SET | 1129525 | #N/A | RSD DIV 1 FACILITY IMPROVMENTS | FAC,REH | No
NOT SET | 1129579 | #N/A | RSD CIP POT MASTER TEMPLATE | FIN,CIP | No
NOT SET | 1129589 | #N/A | RSD CWP CLEAR ZONE SAFETY | PMD,RD | No
NOT START | 1129597 | #N/A | RSD ISS HBRT RD@CDR GROV IMPRV | PMD,RND | No
NOT SET | 1129600 | #N/A | RSD HIGHLINE SCH DIST IMPRVMNT | PAV,CIP | No
NOT SET | 1129625 | #N/A | RSD BRRYDL OXNG 3086OX2016 RPR | FIN,CIP | No
NOT SET | 1129712 | #N/A | RSD PAVEMENT | PAV,CIP | No
NOT SET | 1129713 | #N/A | RSD HIGH RISK PAVING | PAV,CIP | No
NOT SET | 1129715 | #N/A | RSD WHITE CENTER OVERLAY | PAV,CIP | No
NOT SET | 1129729 | #N/A | RSD HIGH COLLISION LOCATIONS | PMD,TRF | No
NOT SET | 1129730 | #N/A | RSD HIGH COLLISION ROAD SGMNTS | PMD,TRF | No
COMPLETE | 1129859 |  | RSD NEELY BR 3014 DECK REPRS | Not Assigned | No
COMPLETE | 1129877 |  | RSD HGH FRICTION SRF TREATMENT | PAV,CIP | Yes
NOT SET | 1130013 | #N/A | RSD HRP RENTON AV S/S126 TO CL | PAV,CIP | No
NOT SET | 1130014 | #N/A | RSD HRP RENTON AV/74AV S-S 126 | PAV,CIP | No
NOT SET | 1130015 | #N/A | RSD HRP NE UNION HILL ROAD | PAV,CIP | No
NOT SET | 1130016 | #N/A | RSD HRP 212 AVE NE | PAV,CIP | No
COMPLETE | 1130162 |  | RSD SUNSET RD SW SLIDE REPAIR | FIN,CIP | No
NOT SET | 1130163 | #N/A | RSD SW LUANA BEACH SLIDE RPR | FIN,CIP | No
NOT SET | 1130188 | #N/A | RSD OLD CASCDE/MILLER BR W | FIN,CIP | No
NOT SET | 1130189 | #N/A | RSD OLD CASCDE/MILLER BR E | FIN,CIP | No
COMPLETE | 1130260 |  | RSD SW 108&8 AV SW ROUNDABOUT | PMD,RND | No
COMPLETE | 1130261 |  | RSD SE176&SE171 WAY ROUNDABOUT | PMD,RND | No
COMPLETE | 1130410 |  | RSD WESTSIDE HWY PERM RD RPR | FIN,CIP | No
COMPLETE | 1130412 |  | RSD 148A NE/TOLT PPLN SIGNAL | FIN,CIP | No
COMPLETE | 1130440 |  | RSD TATE CREEK BRIDGE 122N | FIN,CIP | No
NOT SET | 1130448 | #N/A | RSD CADMAN SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130449 | #N/A | RSD DIAMOND SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130450 | #N/A | RSD KRAIN SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130451 | #N/A | RSD MILETA SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130452 | #N/A | RSD NORTH BD SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130453 | #N/A | RSD RENTON SAND/SALT STORAGE | FAC,NEW | No
COMPLETE | 1130454 |  | RSD SKYKOMISH SAND/SALT STORGE | FAC,NEW | No
NOT SET | 1130455 | #N/A | RSD STILLWTR SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130456 | #N/A | RSD VASHON SAND/SALT STORAGE | FAC,NEW | No
NOT SET | 1130682 | #N/A | RSD DRG DSGN 46000 SAHALEE WAY | DRN,RSD | No
NOT SET | 1130683 | #N/A | RSD DRG DSGN PETROVITSKY ROAD | DRN,RSD | No
NOT START | 1130709 | #N/A | RSD FC SE 384 ST @ 176 A SE | DRN,FLD | No
COMPLETE | 1130711 |  | RSD FC WD/DVL BRG 1136B/E SCR | DRN,FLD | No
COMPLETE | 1130712 |  | RSD FC DUVALL BRG 1136A SCR | DRN,FLD | No
COMPLETE | 1130713 |  | RSD FC RAGING RVR 1008E SCR | DRN,FLD | No
COMPLETE | 1130714 |  | RSD FC PATTON BRG 3015 | DRN,FLD | No
NOT SET | 1130883 | #N/A | RSD CW DRAINAGE PRES TEMP MTCE | FIN,CIP | No
NOT SET | 1130960 | #N/A | RSD SW CEDARHURST SLIDE RPR | FIN,CIP | No
NOT SET | 1130961 | #N/A | RSD GRN VLLY RD SLIDE RPR | FIN,CIP | No
NOT SET | 1131002 | #N/A | RSD NEWAUKUM CR BR 3071 REHAB | Not Assigned | No
NOT SET | 1131003 | #N/A | RSD CHERRY CK BR 4271 REPAIR | Not Assigned | No
NOT SET | 1131142 | #N/A | RSD DIV 1 DRAINAGE | DRN,RSD | No
NOT SET | 1131143 | #N/A | RSD DIV 2 DRAINAGE | DRN,RSD | No
NOT SET | 1131144 | #N/A | RSD DIV 3 DRAINAGE | DRN,RSD | No
NOT SET | 1131145 | #N/A | RSD DIV 4 DRAINAGE | DRN,RSD | No
NOT SET | 1131146 | #N/A | RSD DIV 5 DRAINAGE | DRN,RSD | No
NOT SET | 1131147 | #N/A | RSD DIV 6 DRAINAGE | DRN,RSD | No
COMPLETE | 1131150 |  | RSD HGH COLLISION SIGN & STRIP | PMD,TRF | No
COMPLETE | 1131152 |  | RSD HGH COLLISION MARKING REV | PMD,TRF | No
COMPLETE | 1131237 |  | RSD SW 102 ST&8 AVE SW RNDABT | PMD,RND | No
COMPLETE | 1131274 |  | RSD 2017-18 GUARDRAIL PRESVTN | PMD,RD | Yes
COMPLETE | 1131275 |  | RSD STOSSEL BR 1023A DECK O/L | BRG,BPM | No
NOT SET | 1131328 | #N/A | RSD SW RORSUCH RD IMPRVMNT | FIN,CIP | No
NOT SET | 1131329 | #N/A | RSD SW GORSUCH RD IMPRVMNT | FIN,CIP | No
NOT SET | 1131420 | #N/A | RSD NE 124 ST SLIDE REPAIR | FIN,CIP | No
COMPLETE | 1131505 |  | RSD CW FACLTY IMPRVMT 17-18 | FAC,REH | No
NOT SET | 1131507 | #N/A | RSD DIV 3 FACLTY IMPRVMT 17-18 | FAC,REH | No
NOT SET | 1131527 | #N/A | RSD 221 A NE @ NE 54 ST | DRN,RSD | No
NOT SET | 1131635 | #N/A | RSD 196 AVE SE GDRL ADJ | PMD,TRF | No
NOT SET | 1131749 | #N/A | RSD NEWAUKUM CK BR 3071 REHAB | BRG,BPM | No
NOT SET | 1131812 | #N/A | RSD OVERFLW BR 3217 JOINT REP | Not Assigned | No
COMPLETE | 1131849 |  | RSD BARING BRDG EMGY RPR 2017 | FIN,CIP | Yes
NOT SET | 1131897 | #N/A | RSD ROAD CONSTRUCTION | FIN,CIP | No
NOT SET | 1131898 | #N/A | RSD MAJOR MAINTENANCE | FIN,CIP | No
NOT SET | 1132085 | #N/A | RSD HRP SE KENT-KANGLEY RD | PAV,CIP | No
NOT SET | 1132088 | #N/A | RSD HRP 64 A S/S 124 ST/68 A S | PAV,CIP | No
NOT SET | 1132089 | #N/A | RSD HRP SE 368 WY/SE 368 ST | PAV,CIP | No
COMPLETE | 1132160 |  | RSD HIGH COLL MARKING REV 2 | PMD,TRF | No
CANCELLED | 1132177 |  | RSD 17-18 CLEAR ZONE SAFETY | PMD,RD | No
COMPLETE | 1132218 |  | RSD TOLT BRG 1834A EMGY RPR-17 | FIN,CIP | Yes
COMPLETE | 1132364 |  | RSD N FORK ROAD SE RDWY RPR | FIN,CIP | No
COMPLETE | 1132396 |  | RSD NVLTY BR404B JNT REHAB | BRG,BPM | No
NOT SET | 1132398 | #N/A | RSD NE WD/DV RDWY EMG REHAB | FIN,CIP | No
COMPLETE | 1132418 |  | RSD 8 BRIDGES RAIL RPLCMNT | BRG,BPM | No
NOT SET | 1132419 | #N/A | RSD DEEP CR BRG TMBR RPLCMNT | BRG,BPM | No
NOT SET | 1132542 | #N/A | RSD HRP MINK RD NE | PAV,CIP | No
COMPLETE | 1132582 |  | RSD 196TH AVE SE HFST REPAIR | PMD,TRF | No
COMPLETE | 1132715 |  | RSD COAL CREEK #3035A DECK | BRG,BPM | No
COMPLETE | 1132949 |  | RSD ISS HOB RD ENH SIGNAL | FIN,CIP | No
COMPLETE | 1132960 |  | RSD BRDG WASH 404B-615A-3024 | BRG,BPM | No
NOT SET | 1133169 | #N/A | RSD CIP GEN CONST BR1&2 TMPLT | Not Assigned | No
NOT SET | 1133170 | #N/A | RSD CIP GEN CONST BR3 TEMPLTE | Not Assigned | No
NOT SET | 1133171 | #N/A | RSD CIP GEN PRES BR 1&2 TMPLT | Not Assigned | No
NOT SET | 1133172 | #N/A | RSD CIP GEN PRES BR 3 TEMPLATE | Not Assigned | No
NOT SET | 1133173 | #N/A | RSD CIP GEN MAINT BR 1&2 TMPLT | Not Assigned | No
NOT SET | 1133174 | #N/A | RSD CIP GEN MAINT BR 3 TEMPLTE | Not Assigned | No
CANCELLED | 1133447 |  | RSD CWP 2018 BRIDGE SAFETY | BRG,BSP | No
COMPLETE | 1133668 |  | RSD FIFTEEN ML CR BRG 493C RPR | BRG,BPM | No
COMPLETE | 1133669 |  | RSD FLAM GEYSER BRG 3024 RPR | BRG,BPM | No
COMPLETE | 1133670 |  | RSD PATTON BRG 3015 RPR | BRG,BPM | No
COMPLETE | 1133671 |  | RSD KANASKET BRG 3037OX RPR | BRG,BPM | No
COMPLETE | 1133672 |  | RSD CEDAR GROVE BRG 3164 RPR | BRG,BPM | No
COMPLETE | 1133673 |  | RSD BRISSACK BRG 1116A RPR | BRG,BPM | No
COMPLETE | 1133674 |  | RSD DUVALL BRG 1136A RPR | BRG,BPM | No
COMPLETE | 1133675 |  | RSD YORK BRG 225C RPR | BRG,BPM | No
NOT SET | 1133755 | #N/A | RSD UPPER PRESTON RD GDRL ADJ | PMD,TRF | No
NOT SET | 1133868 | #N/A | RSD 144TH 142ND PAVE PRES | PAV,CIP | No
NOT SET | 1133870 | #N/A | RSD SE 232ND ST GDRL ADJ | PMD,TRF | No
NOT SET | 1133871 | #N/A | RSD SE 224TH ST GDRL ADJ | PMD,TRF | No
NOT SET | 1133876 | #N/A | RSD HRP VASHON HWY SW OLD | PAV,CIP | No
NOT SET | 1134004 | #N/A | RSD HRP SE 384 AND SE 383 OLD | PAV,CIP | No
CANCELLED | 1134005 |  | RSD HRP MOUNTN VIEW RD NE OLD | PAV,CIP | No
CANCELLED | 1134006 |  | RSD HRP BECN COAL MINE RD OLD | PAV,CIP | No
COMPLETE | 1134048 |  | RSD BRAC WD DUV BRG 1136E RPR | BRG,BPM | No
COMPLETE | 1134049 |  | RSD BRAC LANDSBRG BRG 3075 RPR | BRG,BPM | No
NOT START | 1134094 | #N/A | RSD CWP OBSOLETE IT SYS RPLMNT | FIN,CIP | No
COMPLETE | 1134845 |  | RSD GRNWTR BRG 3050A LD UPGRD | FIN,CIP | No
NOT SET | 1134849 | #N/A | RSD HRP VASHON HWY SW | FIN,CIP | No
NOT SET | 1134850 | #N/A | RSD HRP SE 384TH AND SE 383RD | FIN,CIP | No
NOT SET | 1134851 | #N/A | RSD HRP MOUNTAIN VIEW RD NE | FIN,CIP | No
NOT SET | 1134852 | #N/A | RSD HRP BEACON COAL MINE RD S | FIN,CIP | No
NOT SET | 1134956 | #N/A | RSD CURB RAMP REPLACEMENT | PAV,CIP | No
COMPLETE | 1134986 |  | RSD FC GRN RVR RD SLIDE REPAIR | DRN,FLD | No
COMPLETE | 1134994 |  | RSD FC 428TH AV CULVERT RPLCMT | DRN,FLD | No
NOT SET | 1135280 | #N/A | RSD BARING BRG 509A RPR | BRG,BPM | No
NOT SET | 1135876 | #N/A | RSD BEAL RD SW | DRN,RSD | No
NOT SET | 1135878 | #N/A | RSD CHERRY VALLEY ROAD | DRN,RSD | No
NOT SET | 1135880 | #N/A | RSD REINIG ROAD | DRN,RSD | No
COMPLETE | 1136087 |  | RSD FOSS RIVER BRG 2605A PAINT | FIN,CIP | No
COMPLETE | 1136209 |  | RSD 2019 BRIDGE WASHING | BRG,BPM | No
COMPLETE | 1136212 |  | RSD SUNDAY CR BRG 364C RPR | BRG,BPM | No
COMPLETE | 1136240 |  | RSD 22233 NE 170TH PL CULVERT | DRN,FPP | No
CANCELLED | 1136578 |  | RSD S 42ND ST SCHOOL PTHWY | PMD,TRF | No
COMPLETE | 1136930 |  | RSD CIP DBASE RPLCMNT | FIN,CIP | No
COMPLETE | 1136934 |  | RSD HRP BCON COAL MINE RD S | PAV,CIP | No
CANCELLED | 1136935 |  | RSD HRP 236A SE SE 384 ST | PAV,CIP | No
COMPLETE | 1136972 |  | RSD SW 108&8 AV SW RNDBT REVSN | FIN,CIP | No
NOT SET | 1137078 | #N/A | RSD HRP SE GREEN VALLEY RD | PAV,CIP | No
COMPLETE | 1137079 |  | RSD OVERFLW BR 3217 OVLY | BRG,BPM | No
COMPLETE | 1137161 |  | RSD STOSSEL BR 1023A GUSSETS | BRG,BPM | No
COMPLETE | 1137385 |  | RSD PRESTON FRNT BRG 5046 OVLY | BRG,BPM | No
NOT SET | 1137510 | #N/A | RSD HRP SE EDGEWICK ROAD | PAV,CIP | No
COMPLETE | 1137856 |  | RSD BRNG BR TMBR.SCR RPR 2019 | BRG,BPM | No
COMPLETE | 1137858 |  | RSD 2019 LK DRTHY LJM BR359B | BRG,BPM | No
NOT SET | 1138803 | #N/A | RSD STORM MIDDLE FORK RD RPR | FIN,CIP | No
NOT SET | 1139148 | #N/A | RSD ORILLIA ROAD S OVERLAY | PAV,CIP | No
NOT SET | 1139242 | #N/A | RSD NE NOVELTY HILL WINTR 2020 | FIN,CIP | No
NOT SET | 1139252 | #N/A | RSD HRP 194TH AVENUE SE | PAV,CIP | No
NOT SET | 1139253 | #N/A | RSD HRP RIVERBEND COMMUNITY | PAV,CIP | No
NOT START | 1140178 | #N/A | RSD BEAR CREEK BRG#480A APPRCH | BRG,BPM | No

## Current
Bridge
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
n/a | 2019 Bridge Load Rating Program | Su |  |  | Various for program work |  |  |  | n/a | n/a | n/a | 1 | Status is varied for program work | Up to 30 projects planned for 2019. Seven (7) projects completed in-house and five (5) consultant projects completed this year.
1141464 | Bridge Load Upgrade Safety Program | Jiang | [6 empty] | Various dates for program work | Ad not scheduled |  | 1 | Status is varied for program work | Jacobs currently reviewing 12 bridges for potential upgrade feasibility and costs. Draft report anticipated Q4 2021
1129588 | 2021 Bridge Priority Maintenance | Roark | SE King County; Snoqualmie Valley; Vashon/Maury | Bridge | 550000 | Multiple entries in CIP Database | Multiple entries in CIP Database | Inadequate funding identified - current estimate exceeds ITD budget | Various dates for program work | In-house | 0.1335% | 1 | Status is varied for program work | Completed 15 bridge repair or maintenance projects in 2021. Two planned deck repairs were delayed to 2022 because of supply chain issues.
1137509 | Dockton Seawall Repair | Roark |  |  | #REF! |  |  |  | November 2019 | In-house | No dollars planned in Q1 2020 | 1 | Implementation | Project Phase II reached substantial completion 9/29/20. Funded out of Quick Response.
1137752 | Flaming Geyser Bridge #3024 Painting | Martin |  |  | #REF! |  |  |  | July 2020 | May 2020 | No dollars planned in Q1 2020 | 1 | Implementation | Project reached physical completion w/ Mericka Group 11/6/20.
1136633 | Patton Bridge Repair | Jiang |  |  | 400000 |  |  |  | February 2021 | July 2020 | -0.2452% | 1 | Substantially Complete | Construction w/ Massana Construction, Inc. substantially complete May 2021. Funded out of Quick Response.
1136631 | Judd Creek Bridge #3184 Load Upgrade/Repair | O'Day | Vashon/Maury Island Area | Bridge | 100000 | 40000 | 100000 | Adequate funding identified - current is less than or equal to ITD budget | March 2021 | August 2020 | No dollars planned in Q1 2020 | 1 | Substantially Complete | Construction w/ Combined Construction substantially complete April 2021
1138337 | Fish Hatchery Bridge #61B Emergent Repair - Flood Control District | Jose | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | July 2021 | In-house | No dollars planned in Q1 2020 | 1 | Substantially Complete | Bridge removal completed July 2021. Permanent fence removal installation to be completed Q1 2022
1136001 | S 277th St. Bridge #3126 - Bridge Safety Program | Premachandra | SE King County Area | Bridge | 2886511.4062 | 2886511.4062 | 533000 | Inadequate funding identified - current estimate exceeds ITD budget | July 2021 | April 2021 | No dollars planned in Q1 2020 | 1 | Substantially Complete | Construction w/Active Construction, substantially complete November 2021.
1135997 | Coal Creek Bridge #3035A - Bridge Safety Program | Martin | SE King County Area | Bridge | 4708280 | 4708280 | 2055000 | Inadequate funding identified - current estimate exceeds ITD budget | September 2021 | May 2021 | 12.9% | 2 | Implementation | Construction w/Active Construction. Installation of bridge/detour delayed to Jan 2022; bridge team actively monitoring load limit on existing bridge. New bridge replacement scheduled to begin May 2022.
1135999 | Upper Tokul Creek Bridge #271B - Bridge Safety Program | Martin | Snoqualmie Valley/NE King County Area | Bridge | 4728421.1875 | 4728421.1875 | 920000 | Inadequate funding identified - current estimate exceeds ITD budget | April 2022 | February 2022 | 10.24% | 1 | Final Design | 100% Design complete w/ DEA December 2021.
1138914 | Fifteen Mile Creek Bridge #493C - Flood Control District | Jose | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | January 2023 | November 2022 | No dollars planned in Q1 2020 | 1 | Final Design | 100% Design in progress w/ Stantec; anticipated to complete July 2022. Federal Grant for (PE, ROW, & CN). CN can be 100% funded if obligated by 9/21/2022--ROW acquisition is critical path.
1135998 | Ames Lake Trestle Bridge #1320A - Bridge Safety Program | Truong | Snoqualmie Valley/NE King County Area | Bridge | 12575002.5 | 12575002.5 | 2094000 | Inadequate funding identified - current estimate exceeds ITD budget | June 2023 | March 2023 | No dollars planned in Q1 2020 | 1 | Final Design | 90% Design in progress w/ Jacobs; anticipated to complete March 2022.
1136000 | Baring Bridge #509A - Bridge Safety Program | Truong | Snoqualmie Valley/NE King County Area | Bridge | 14029436.4648 | 14029436.4648 | 1500014 | Inadequate funding identified - current estimate exceeds ITD budget | April 2024 | November 2023 | No dollars planned in Q1 2020 | 2 | Final Design | 90% Design in progress w/ HNTB; anticipated to be complete Q4 2022. Design has been delayed due to additional time needed for execution of contract amendment. This may impact permit/ROW acquisition.
1138913 | Boise X Connection #3055A | Jin |  |  | 2309000 |  |  |  | February 2024 | October 2023 | No dollars planned in Q1 2020 | 2 | Preliminary Design | 30% Design in progress; anticpated to complete March 2022. CDR completed December 2021. Construction moved from 2023 to 2024.
1141001 | NE Tolt Hill Road Repair - Winter 2020 | Premachandra | [6 empty] | March 2023 | June 2023 |  | 2 | Preliminary Design | 30% Design w/ DEA in progress; anticipated complete March 2022. Construction needs to be obligated 9/20/2022. Design charette being prepared to accelerate schedule to meet WSDOT requirements in tight timeline.
tbd | Duvall Slough Bridge #1136B Re-Deck | Jin | [6 empty] | 2023-10-01 | Ad not scheduled |  | 1 | Preliminary Design | Preliminary Design anticipated to begin March 2022. Federal funds through Bridge Program Grant.
1134340 | North Fork Bridge #1221 Feasibility Study | Jose | [6 empty] | Not Scheduled | Ad not scheduled |  | 1 | Preliminary Design | Notice to Proceed issued in April 2021 to TranTech. Feasibility study in progress and anticipated to be complete by February 2022.
Roadway and Roadside
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1135419 | NE Novelty Hill Rd Slide - Emergency Repair | Sahagun | [6 empty] | July 2020 | Emergency Declaration 2020 | No dollars planned in Q1 2020 | 1 | Implementation | Construction w/ GSI began in July 2020. Road opened 7/24/20. Funded out of Quick Response.
1136352 | 2019 Pavement Preservation - Countywide | Moore | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | July 2019 | April 2019 | No dollars planned in Q1 2020 | 1 | Implementation | Project reached substantial completion in July 2020.
1136084 | 2019/20 New Guardrail Construction - Traffic Safety Program/Countywide | Mott | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | September 2020 | June 2020 | -15.88% | 1 | Implementation | Construction w/ Petersen Brothers Inc. began 9/8/20. Project reached substantial completion on 12/4/20.
1139815 | 356th Drive SE Slide - Emergency Repair | Truong | [6 empty] | September 2020 | Emergency Declaration 2020 | No dollars planned in Q1 2020 | 1 | Implementation | Project reached substantial completion w/ RNCW 12/21/20. Funded out of Quick Response.
1141580 | 2021 High Risk Paving Ames Lake Carnation | Moore | [6 empty] | June 2021 | In-house |  | 1 | Substantially Complete | Construction completed June 2021. Project charges are processing.
1137996 | 2020 Pavement Preservation - Countywide | Moore | #N/A | #N/A | 5420000 | Not in CIP Database | Not in CIP Database | Not in CIP Database | June 2020 | March 2020 | No dollars planned in Q1 2020 | 1 | Substantially Complete | Project reached substantial completion w/ Icon 2/23/21 (includes 11.1 miles of County roads and 3.2 miles for the City and utility companies).
1141581 | 2021 High Risk Paving Alpental Access Rd | Moore | [6 empty] | July 2021 | In-house |  | 1 | Substantially Complete | Construction completed July 2021.
1137577 | 304th St Haul Road Mitigation | Moore | [6 empty] | July 2021 | May 2021 |  | 1 | Substantially Complete | Included in 2021 Countywide Pavement Preservation Program contract. Paving completed July 2021.
1136085 | 2019/20 Guardrail Preservation Tier 2 Roadways - Traffic Safety Program/Countywide | Mott | Locations TBD by Q2 2020 | Roadside | 4520000 | 4520000 | 3000000 | Inadequate funding identified - current estimate exceeds ITD budget | February 2021 | October 2020 | -4.194% | 1 | Substantially Complete | Tier 2 roadway guardrail construction w/ Petersen Brother substantially complete July 2021.
1141044 | 2021 Pavement Preservation - Countywide | Mott | [6 empty] | July 2021 | May 2021 |  | 1 | Implementation | Construction with Lakeside Industries, Inc. began July 2021. Substantial completion anticipated May 2022.
1141111 | 2019/20 Guardrail Preservation Tier 3 Roadways - Traffic Safety Program/Countywide | Mott |  |  | 2309000 |  |  |  | February 2022 | January 2022 | No dollars planned in Q1 2020 | 2 | Final Design | Final Design in progress. Tier 3 on track to advertise January 2022. Delays due to utility relocation coordination.
1142993 | 2022 Pavement Preservation | Mott | [6 empty] | Summer 2022 | Spring 2022 |  | 1 | Preliminary Design | New project; anticipated to advertise Spring 2022. CWP Roadway Preservation funding.
Roadway and Roadside (cont.)
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1140858 | 244th Ave NE Winter 2020 Slide Repair | Wang | [6 empty] | June 2023 | April 2023 |  | 2 | Preliminary Design | 30% In-House Design in progress. CDR anticipated to be complete Q1 2022. FHWA requirements involving permitting and property acquisition may impact schedule.
School Safety
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1136576 | 2019/20 School Zone Safety - School Safety Program | Hafele | West King County Areas; Snoqualmie Valley/NE King County Area | Traffic Control/Safety | 168509.87 | 100000 | 168509.87 | Adequate funding identified - current is less than or equal to ITD budget | Various dates for program work | In-house | No dollars planned in Q1 2020 | 1 | Status is varied for program work | All 4 projects scheduled for 2021 completed: Lake view Elementary, 8th Ave S ADA Ramp and Marked Crosswalk, Chief Kanim Middle School, and Northwood Middle School.
1136646 | 42nd Ave S - School Safety Program - School Pathway Project | Ashti | #REF! | #REF! | 66000 | #REF! | #REF! | #REF! | October 2020 | June 2020 | No dollars planned in Q1 2020 | 1 | Implementation | Construction w/ NPM Construction began 10/1/20. Project reached substantial completion 12/12/20.
1136582 | S 298th St - School Safety Program - School Pathway Project | Ashti | #REF! | #REF! | 120000 | #REF! | #REF! | #REF! | October 2020 | June 2020 | No dollars planned in Q1 2020 | 1 | Implementation | Construction w/ NPM Construction began 10/1/20. Project reached substantial completion 12/12/20.
1136580 | S 360th St - School Safety Program - School Pathway Project | Karinen | West King County Areas | Roadside | 175000 | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | May 2022 | March 2022 | No dollars planned in Q1 2020 | 2 | Implementation | 100% PS&E Package completed April 2021. Weather-dependent work impacted advertisement date - construction will be staged and extended to 2022. Combined contract with 360th School Pathway Project.
Traffic Control
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1134093 | Traffic Safety Program | Various | [6 empty] | Various dates for program work | Various dates for program work |  | 1 | Status is varied for program work | Construction w/ Road Construction Northwest for Traffic Calming and Transverse Rumble Strips completed in June 2021. Left Turn Phasing completed October 2021. Radar Speed Signs installed Q4 2021. Ad date for Roadway Lighting currently scheduled for Jan 2022.
1129714 | NE Stillwater Hill Rd Reconstruction | Linders | Snoqualmie Valley/NE King County Area | Traffic Control/Safety | 4675000 | 4675000 | 845190 | Inadequate funding identified - current estimate exceeds ITD budget | July 2021 | March 2021 | 57.53% | 1 | Substantially Complete | Construction w/ Interwest substantially complete 10/19/2021. Landscaping work taking place December 2021.
1137862 | 2020 High Friction Surface Treatment | Linders |  |  | 3232000 |  |  |  | TBD 2022 | June 2021 | No dollars planned in Q1 2020 | 2 | Implementation | CN contract w/ American Civil Constructors West Coast executed 8/26/21. Construction pushed to May 2022 due to advertisement delays and weather restrictions for HFST application.
1131157 | High Collision Sightline Improvements S 360 St & 32 Ave S - Traffic Safety Program | Karinen | West King County Areas | Traffic Control/Safety | 150000 | 150000 | 150000 | Adequate funding identified - current is less than or equal to ITD budget | May 2022 | March 2022 | No dollars planned in Q1 2020 | 2 | Implementation | 100% PS&E Package completed April 2021. Weather-dependent work impacted advertisement date - construction will be staged and extended to 2022. Combined contract with 360th School Pathway Project.
1136086 | 218th Ave SE Reconstruction | Linders | Bear Creek/Sammamish Area | Traffic Control/Safety | 5972000 | 5972000 | 877846 | Inadequate funding identified - current estimate exceeds ITD budget | May 2022 | February 2022 | -6.962% | 1 | Final Design | 100% Design completed Oct 2021. PSRC Grant on track to obligate by Feb 2022.
1134081 | Redmond Ridge NE Roundabout | Karinen | Bear Creek/Sammamish Area | Traffic Control/Safety | 1380000 | 1380000 | 1200000 | Inadequate funding identified - current estimate exceeds ITD budget | June 2022 | April 2022 | 12.5% | 1 | Final Design | 100% Design in progress; anticipated complete Jan 2022. Received additional $300K in 2nd omnibus.
1129599 | Renton Ave Phase III Sidewalk | Linders | West King County Areas | Roadside | 3200000 | 2630000 | 3200000 | Adequate funding identified - current is less than or equal to ITD budget | June 2022 | April 2022 | -22.85% | 2 | Final Design | 100% Design in progress; anticipated complete Jan 2022. Construction moved to 2022. ROW & Permitting are critical path. Project awarded $2M from WSDOT 2020 Pedestrian and Bicyclist Program construction funds and received additional $300K Reet Funding.
1141625 | SE Kent-Kangley Rd at Landsburg (Mid-Term) - Traffic Safety Program | Linders | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | July 2022 | May 2022 | No dollars planned in Q1 2020 | 1 | Final Design | 100% design in progress; anticipated complete February 2022. ROW acquisition with Parks properties to be completed March 2022.
1131235 | S 360 St & Military Road Roundabout - Traffic Safety Program | Karinen | West King County Areas | Traffic Control/Safety | 1085000 | 1085000 | 1085000 | Adequate funding identified - current is less than or equal to ITD budget | August 2023 | June 2023 | 17.63% | 1 | Final Design | 90% Design in progress; anticipated complete January 2022. Construction has been awarded 2023 Congestion Mitigation and Air Quality Improvement funds. Grant construction obligation date of 6/1/2023
1142502 | Avondale Rd NE at Cottage Lake Elementary Safety Improvements | Hafele | [6 empty] | April 2022 | In-house |  | 2 | Final Design | Final Design in progress; anticipated complete Feb 2022. Coordinating with Puget Sound Energy and school district on schedule updates; delays due to responsiveness of PSE.
1138330 | SE Covington Sawyer Rd Sightline Improvements- CWP High Collision Safety | Wang | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | May 2023 | March 2023 | No dollars planned in Q1 2020 | 1 | Final Design | 60% Design in progress; anticipated to complete March 2022. Work is separate from the WSDOT funded project #1134083 that produced the Concept Development Report for this location.
1138918 | 16th Ave SW Ped Improvements | Mott |  |  | 958000 |  |  |  | Summer 2024 | Spring 2023 | No dollars planned in Q1 2020 | 3 | Final Design | 60% Design in progress; anticipate complete May 2022. Ongoing public outreach. (Impact to local businesses + translation to 7 languages). Federal Highway Safety Improvement Program funds awarded for CN. Will need additional urgent funds as of 11/4 due to design cost overruns. Construction delayed to 2024.
1139146 | Rainier S and Lakeridge Drive Intersection | Zhen | [6 empty] | Summer 2023 | Spring 2023 |  | 1 | Preliminary Design | Consultant hired for design (originally in-house). Design anticipated to begin Q2 2022.
1129598 | Issaquah-Hobart at May Valley Roundabout - Traffic Safety Program/Flood Control District | Wang | Four Creeks/Tiger Mountain Area | Traffic Control/Safety | 7132000 | 7132000 | 2039000 | Inadequate funding identified - current estimate exceeds ITD budget | June 2024 | April 2024 | -12.24% | 1 | Preliminary Design | Consultant Design negotiations with Transpo in progress; NTP expected April 2022. Construction moved to 2024 to coordinate with 15 Mile Creek.
Traffic Control (cont.)
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1134080 | NE Woodinville Duvall at West Snoqualmie Valley NE Roundabout | Linders | Bear Creek/Sammamish Area | Traffic Control/Safety | 150000 | 150000 | 150000 | Adequate funding identified - current is less than or equal to ITD budget | Not Scheduled | Ad not scheduled | 22.42% | 1 | Preliminary Design | Preliminary Design in progress; anticpated to complete Q4 2023. New design layout may require agricultural land acquisition. No construction funding.
1139145 | SE Green Valley Rd and 218th Ave SE Intersection Improvement | Linders | [6 empty] | June 2024 | February 2024 |  | 1 | Planning | Preliminary Design to begin Q1 2022. Awarded $454K PSRC grant for PE and ROW.
Drainage
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1130991 | Drainage Preservation - Division Drainage | Quach | Bear Creek/Sammamish Area; Four Creeks/Tiger Mountain Area; Greater Maple Valley/Cedar River Area; Vashon/Maury Island Area; SE King County Area; Snoqualmie Valley/NE King County Area; West King County Areas | Drainage | Various entries for program work | Various entries for program work | Various entries for program work | Various entries for program work | Various dates for program work | In-house | No dollars planned in Q1 2020 | 1 | Status is varied for program work | $2.7M budgeted for 2021. $2.04M spent (75%) spent as of 12/24/21.
1125758 | West Snoqualmie Valley Culvert Replacement | Cassidy | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | August 2020 | In-house | No dollars planned in Q1 2020 | 1 | Implementation | Project reached substantial completion 9/30/20.
1130707 | 162 Ave SE @ 166 Court Design - Flood Control District | Lyou | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | August 2020 | June 2020 | -34.95% | 1 | Implementation | Project reach substantial completion w/ Marshbank 11/5/20.
n/a | 178th Slide Repair | Lyou | [6 empty] | September 2020 | In-house |  | 1 | Implementation | Project reach substantial completion 11/5/20. Funded out of the 2019 - 2020 operating budget.
1130991 | Drainage Preservation - Division Shouldering | Quach | [6 empty] | Various dates for program work | In-house |  | 1 | Status is varied for program work | $500,000 budgeted for 2021. $460,417 spent (92%) as of 12/24/21.
1132710 | Sahalee at 4800 blk | Dulan | Bear Creek/Sammamish Area | Drainage | 382650 | 382650 | 100000 | Inadequate funding identified - current estimate exceeds ITD budget | June 2022 | In-house | No dollars planned in Q1 2020 | 2 | Final Design | 100% Design complete. Mitigation plan in progress. Design and ROW delays have extended schedule. CN to be funded through Drainage Preservation.
1130710 | SE 380 Place at SR 164 Culvert Replacement - Flood Control District | Lyou | SE King County Area | Drainage | 900000 | 900000 | 190000 | Inadequate funding identified - current estimate exceeds ITD budget | June 2022 | March 2022 | 14.07% | 3 | Final Design | 90% Design in progress; design on hold due to competing priorities and ROW delays. May push construction out to 2023.
1129595 | Old Cascade Miller River Bridge West | Lyou | Snoqualmie Valley/NE King County Area | Drainage | 2300000 | 2300000 | 2300000 | Adequate funding identified - current is less than or equal to ITD budget | July 2022 | May 2022 | 10.45% | 3 | Final Design | 100% Design in progress. Construction delays to accommodate for permitting review and negotiations with BNSF Railway Co. FEMA grant funded--2022 extension approved 10/4/21. Schedule closely monitored.
1129596 | Old Cascade Miller River Bridge East | Lyou | Snoqualmie Valley/NE King County Area | Drainage | 2750000 | 2750000 | 2750000 | Adequate funding identified - current is less than or equal to ITD budget | July 2022 | May 2022 | 12.41% | 3 | Final Design | See 1129595 above.
1138339 | S 106th St (18th Ave S) - Flood Control District | Quach | [6 empty] | August 2022 | In-house | No dollars planned in Q1 2020 | 2 | Final Design | 100% Design complete. Construction moved to 2022 to accommodate for property easement acquisition.
1131511 | Sahalee at 4600 Block | Dulan | Bear Creek/Sammamish Area | Drainage | 400850 | 400850 | 160000 | Inadequate funding identified - current estimate exceeds ITD budget | August 2022 | In-house | No dollars planned in Q1 2020 | 3 | Final Design | 100% Design complete. Construction extended to 2022 due to crew availability. Funded by Drainage Preservation.
1127589 | NE 165th St Flood Risk Reduction | Karinen | Bear Creek/Sammamish Area | Traffic Control/Safety | 760146 | 391713 | 760146 | #N/A | TBD | In-house | No dollars planned in Q1 2020 | 3 | Final Design | Revisiting Final Design--raising road by 1.8 ft. Ongoing clarification of permitting and compensatory storage requirements. Proposed to move construction to 2023 or 2024 to accommodate.
1131526 | Petrovitsky Road and 134th Ave SE | Mitchell | West King County Areas | Drainage | 3864000 | 3864000 | 440700.26 | Inadequate funding identified - current estimate exceeds ITD budget | May 2024 | March 2024 | No dollars planned in Q1 2020 | 3 | Final Design | Final Design on hold. Delays with finalizing amendment to consultant (OTAK) contract; Amendment 14 processing for parts A & B of project. Parts C & D of project will now be in-house. CN to be funded through Drainage Preservation.
1131672 | Petrovitsky Road at 20300 Block | Mitchell | Greater Maple Valley/Cedar River Area | Drainage | 165000 | 165000 | 135000 | Inadequate funding identified - current estimate exceeds ITD budget | Not Scheduled | Ad not scheduled | No dollars planned in Q1 2020 | 3 | Final Design | See 1131526 above. CN in 2024.
1131671 | Petrovitsky Road at 151st Ave SE | Mitchell | West King County Areas | Drainage | 165000 | 165000 | 130000 | Inadequate funding identified - current estimate exceeds ITD budget | Not Scheduled | Ad not scheduled | No dollars planned in Q1 2020 | 3 | Final Design | See 1131526 above. CN in 2024.
1139716 | Langston at South 125th Flood Control District | Mitchell |  |  | 994000 |  |  |  | October 2022 | September 2022 | No dollars planned in Q1 2020 | 1 | Preliminary Design | Consultant design negotiations in progress w/ Four Elements. Design anticipated to start Jan 2022. $778k funded for design (Construction not funded).
1130706 | NE 8th Lake Allen Outlet Flood Control District | Lyou |  |  | 2350000 |  |  |  | 2022 | In-house | No dollars planned in Q1 2020 | 2 | Preliminary Design | CDR in progress; alternative selected by 1/31/2022. Delays in acquiring ROEs (high level of public resistance) continue to impact project schedule.
1130705 | Snoqualmie Valley Flood Mitigation Study Flood Control District | Truong | [6 empty] | Not Scheduled | Ad not scheduled |  | 2 | Preliminary Design | Feasibility study for 2021-2022. Consultant design anticipated to start June 2022.
1139811 | SE 384th St at #17110 West of 176th Ave SE Drainage Improvement | Lyou | [6 empty] | July 2023 | Ad not scheduled |  | 1 | Planning | Planning; working on RFP for consultant design. Design must be obligated by July 2022. Awarded $800k CRAB funds for design and construction for 2021 - 2023 biennium.
1136241 | Green River Rd (In-house) | Shular | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | July 2020 | In-house | No dollars planned in Q1 2020 | 1 | Implementation | Project reached substantial completion 8/27/20.
1130709 | SE 384th St at 176th Ave SE Flood Control District | Lyou | [6 empty] | TBD | Ad not scheduled |  | 1 | Planning | Preliminary Design to start January 2022. Waiting for ROEs to start project. FCD funded.
Drainage - Fish Passage Program
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1136233 | NE Lake Joy Rd at NE 118th Pl Culvert Replacement (Consultant) | Quach | Snoqualmie Valley/NE King County Area | Drainage | 1296000 | No Estimate | 108000 | Adequate funding identified - current is less than or equal to ITD budget | July 2021 | In-house | 7.237% | 1 | Substantially Complete | Completed 10/15/21 with XL Tech. Mitigation is upcoming.
1136238 | NE 24th St @33609 (In-house) | Quach | Snoqualmie Valley/NE King County Area | Drainage | tbd | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | July 2023 | In-house | No dollars planned in Q1 2020 | 2 | Final Design | 90% Design in progress. Anticipated to complete March 2022. Received Flood Reduction Grant for 2023 CN. Construction to start summer 2023 due to flooding from beaver activity.
1136419 | SE 432nd St @27609 (In-house) | Dulan | SE King County Area | Drainage | 1078000 | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | 2023 | In-house | No dollars planned in Q1 2020 | 1 | Final Design | 99% Design and ROW in progress. In house construction cost estimate is underway.
1136235 | Bear Creek Basin (3) - Avondale Culvert Replacement (Consultant) | Mitchell | Bear Creek/Sammamish Area | Drainage | 3725001 | No Estimate | 664000 | Adequate funding identified - current is less than or equal to ITD budget | 2023 | Ad not scheduled | -22.92% | 2 | Final Design | 99% Design in progress w/ TetraTech; anticipated complete June 2022. Delays due to obtaining properly documented invoices and resolve SCS issues.
Drainage - Fish Passage Program (cont.)
Project Number | Project Name | PM | CSA | Product Family | Estimated Total Cost | Project Estimate | Project Budget | Project Fully Funded? (Estimate vs. Budget) | CN Start Date | Ad Date | 1st Quarter Percent O/U Plan | Risk Level | Status | Project Status
1136236 | Bear Creek Basin (3) - 165th Culvert Replacement (Consultant) | Mitchell | [6 empty] | Not Scheduled | Ad not scheduled | -1.99% | 2 | Final Design | See above.
1136232 | Bear Creek Basin (3) - 128th Culvert Replacement (Consultant) | Mitchell | [6 empty] | Not Scheduled | Ad not scheduled | -15.38% | 2 | Final Design | See above.
1138947 | 284th Ave SE @ 46913 Culvert Replacement | Dulan | [6 empty] | July 2022 | In-house |  | 2 | Preliminary Design | Preliminary Design in progress. Project is programmed for 2022 construction; more CN funding needed. Concerns ROW may impact schedule; solidifying ROW plans ongoing.
1140906 | 156th SE at SE 240th Culvert | Dulan | [6 empty] | Not Scheduled | In-house |  | 2 | Preliminary Design | In house design anticipated to start Q2 2022. Construction was extended to 2023 to coordinate with 15 mile creek project. Schedule pending until more information available from procurement.
1136234 | NE Woodinville Duvall Rd at NE 172nd St (Consultant) | Wang | Bear Creek/Sammamish Area | Drainage | 1492000 | No Estimate | 322000 | Adequate funding identified - current is less than or equal to ITD budget | June 2023 | May 2023 | No dollars planned in Q1 2020 | 2 | Preliminary Design | 60% Design in progress w/KPFF; final design anticipated to complete April 2022. $4.3 million REET Funding received; goal is to construct summer 2022---Construction will now be 2023.
1136237 | S 370th St @ Enchanted Pkwy S (In-house) | Lyou | West King County Areas | Drainage | tbd | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | Not Scheduled | In-house | No dollars planned in Q1 2020 | 2 | Preliminary Design | 30% Design; On hold due to limited staff capacity. Project schedule has been impacted as staff focus design efforts on projects programmed for construction. Funding for construction is uncertain due to no fish in region.
1136239 | SE 317th &Thomas Rd SE (In-house) | Quach | SE King County Area | Drainage | tbd | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | Not Scheduled | In-house | No dollars planned in Q1 2020 | 2 | Preliminary Design | Preliminary Design; CDR delayed. On hold due to limited staff capacity.
1136229 | 180th Ave SE at SE 408th (Consultant) | Mitchell | SE King County Area | Drainage | 986000 | No Estimate | 292000 | Adequate funding identified - current is less than or equal to ITD budget | Not Scheduled | Ad not scheduled | 0.5% | 2 | Preliminary Design | Project suspended at 30% Design (w/KPFF). Schedule and cost impacts due to ongoing coordination with Muckleshoot Tribal Council; Muckleshoot Planning reviewing alternatives.
1136231 | 185th Ave NE at NE 179th (Consultant) | Mitchell | Bear Creek/Sammamish Area | Drainage | 1568000 | No Estimate | 12000 | Adequate funding identified - current is less than or equal to ITD budget | 2023 | Ad not scheduled | No dollars planned in Q1 2020 | 2 | Preliminary Design | CDR and 30% Design in progress. Negotiating Phase II amendment to extend KPFF. Design considerations as road is sole access for 125 houses.
1136230 | Fairwood E of 151st Culvert (Consultant) | Berryessa (WLRD) |  |  | 2929200 |  |  |  | CN not scheduled | In-house | No dollars planned in Q1 2020 | 2 | Preliminary Design | Consultant contract advertisement anticipated Q1 2021 (previously 2020). MOU signed in November 2020.
1140905 | 17401 SE 240 Street SE Culvert (Consultant) | Dulan | [6 empty] | Not Scheduled | Ad not scheduled |  | 2 | Preliminary Design | Consultant design; likely contract will be signed April 2022. Schedule delays due to drilling and obtaining ROEs; anticipate 100% Design by May 2023. Construction is not funded.
1136230 | SE Fairwood Blvd at 151st Ave SE Culvert (Consultant) | Cassidy | [6 empty] | Not Scheduled | Ad not scheduled |  | 2 | Preliminary Design | Consultant design contract with HRD executed in September 2021. Delays in executing consultant contract have impacted design schedule. WLRD is the lead.
[12 empty] | Key: | Schedule Risk Level Legend
1136235 | [5 empty] | No Estimate | 332000 |  |  |  |  | 3 | Substantial risk
11 | [5 empty] | #N/A | 0 |  |  |  |  | 2 | Moderate risk
1136232 | [5 empty] | No Estimate | 332000 |  |  |  |  | 1 | Low to no risk
1136235
1136236
1136232
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I did not update this one yet Reply: Sent Larry/Stephen email 1/18/22 for current status
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from TingTing--is that necessary? Reply: I will double check but I think we need to keep with the assigned PM (even though someone else is taking over temporarily)
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to yellow? Reply: I think so, since the temp bridge CN was delayed
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same as above--changed from TingTing
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: changed to Hiromal as acting pm
Note on O20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dont see an update on this one Reply: sent email 1/18/22 to jessy for udpate Reply: Entered Jessy's update
Note on O32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: did not do this one Reply: no changes to update
Note on K48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date pending, was not sure what to put (actualized in prism) Reply: the CN start date is pending and the project was already advertised June 2021
Note on M50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This one seems like we can move to green? Reply: good call. i agree. done
Note on M51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this still need to be yellow? Reply: No, I updated to green
Note on M54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to yellow? Reply: agreed. done Reply: Actually, looked at it again and think I'll keep green since there is no clear issue to explain need for yellow besides the fact that we are closely monitoring. ROW was at risk before ROW plans were finally given to ROW team back in Sept
Note on O58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is in the notes, but I don't see any contract info in PRISM. Need to verify with Haiyan. I'll reach out via IM wed morning
Note on M59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated this from yellow to green. Since CN was moved to 2024, the delays getting the consultant onboard were no longer an issue
Note on C72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Abbas is only the temp design engineer, not the project manager. Going to change back to Lyou until new PM is assigned. May change all of Lyou's to Cassidy or Shular. Will check with Rose and Jon
Note on O72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Want to ask Rose about this one. Whether or not we want to disclose this recent development from a meeting we had on 1/13/22
Note on M76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: switch to green or yellow?
Note on O78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was not sure on wording for this one--too much detail?
Note on M82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: maybe move to red?
Note on M100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to red?

## Expense Report (hidden)
Project Number | Project Name | Project Type | Project Manager | YTD 2020 Percentage = (Actuals - Forecast)/Forecast
1127271 | RSD PRESTON MAINT FACILITY | Standalone | Kosai-Eng | #DIV/0!
1127273 | RSD FAILED ENV & HVAC REHAB | Standalone | Kosai-Eng | 18.88%
1129584 | RSD CWP QUICK RESPONSE | Master | Various | 7.816%
1129585 | RSD CWP ROADWAY PRESERVATION | Master | Various | 6.692%
1129586 | RSD CWP DRAINAGE PRESERVATION | Master | Various | 8.131%
1129587 | RSD CWP GUARDRAIL PRESERVATION | Master | Mott | -3.296%
1129588 | RSD CWP BRIDGE PRIORITY MAINT | Master | Various | 0.1335%
1129590 | RSD CWP HIGH COLLISION SAFETY | Master | Various | #DIV/0!
1129591 | RSD CWP SCHOOL ZONE SAFETY | Master | Various | #DIV/0!
1129841 | RSD CIP OVERSIGHT 3855 | Admin | Foote | #DIV/0!
1131333 | RSD CWP FLOOD CONTROL DISTRICT | Master | Various | -14.42%
1134082 | RSD FACILITIES LED CONVERSION | Standalone | Ho | -16.02%
1134083 | RSD COVINGTON WAY SE IMPROVE | Standalone | Zhen | 1.538%
1134093 | RSD CWP TRAFFIC SAFETY | Master | Various | -11.59%
1135045 | RSD CWP CLVRT RPLCMT FISH PASS | Master | Various | 12.79%
1135046 | RSD MAINT HDQTRS BLDG D REHAB | Standalone | Kosai-Eng | #DIV/0!
1135073 | RSD CWP 2019-20 BRIDGE SAFETY | Master | Truong
1135997 | COAL CREEK BRG 3035A REPL | Subproject | Truong | 12.9%
1135998 | AMES LK TRS BRG 1320A REPL | Subproject | Truong | #DIV/0!
1135999 | UPR TOKUL CK BRG 271B REPL | Subproject | Truong | 10.24%
1136000 | BARING BRG 509A REPL | Subproject | Truong | #DIV/0!
1136001 | 277TH ST BRG 3126 REPL | Subproject | Truong | #DIV/0!
TBD | Fifteen Mile Creek Bridge #493C Replacement | Subproject |  | #DIV/0!
TBD | Boise X Connection #3035 Replacement | Subproject |  | #DIV/0!
1027163 | RSD QUICK RESPONSE | Master | Various
1111819 | RSD C W DRAINAGE PRESERVATION | Master | Various | #DIV/0!
1125758 | RSD W SNOQ VLY RD/NE124-W/D RD | Standalone | Posey | #DIV/0!
1129594 | RSD CWP GUARDRAIL CONSTRUCTION | Master | Mott | -15.88%
1129595 | RSD OLD CASCADE/MILLER BR WEST | Standalone | Lyou | 10.45%
1129596 | RSD OLD CASCADE/MILLER BR EAST | Standalone | Lyou | 12.41%
1129598 | RSD ISS HBRT RD@MAY VLLY IMPRV | Standalone | McManus | -12.24%
1129599 | RSD RENTON AVE PH III SIDEWALK | Standalone | Sahagun | -22.85%
1130260 | RSD SW 108&8 AV SW ROUNDABOUT | Standalone | Mott | #DIV/0!
1130261 | RSD SE176&SE171 WAY ROUNDABOUT | Standalone | Mott | #DIV/0!
1130303 | RSD CIP OVERSIGHT 3865 | Admin | Foote | #DIV/0!
1131235 | RSD S 360ST&MILITARY RD RNDABT | Standalone | McManus | 17.63%
1131236 | RSD S LANGSTON RD&59 AV RNDABT | Standalone |  | #DIV/0!
1131237 | RSD SW 102 ST&8 AVE SW RNDABT | Standalone | Mott | #DIV/0!
1134079 | RSD KENTKANGLEY LNDSBRG RNDABT | Standalone | Linders | -2.1%
1134080 | RSD WDDUV SNOQ VALLEY IMPROVE | Standalone | Linders | 22.42%
1134081 | RSD REDMOND RIDGE DR NE RNDABT | Standalone | Sahagun | 12.5%
1135042 | RSD VASHON MAINT FACILITY REPL | Standalone | Foote | #DIV/0!
1126441 | RSD S 96 ST STORMWATER PIPES | subproject | Truong | #DIV/0!
1127589 | RSD 165 ST FLD RSK RDUCTN | subproject | Bleasdale | #DIV/0!
1125296 | RSD S 96 ST&8 AVE S SINKHOLE | subproject | Truong | #DIV/0!
1130162 | RSD SUNSET RD SW SLIDE REPAIR | subproject | Posey | #DIV/0!
1130410 | RSD WESTSIDE HWY PERM RD RPR | subproject | Posey | #DIV/0!
1132218 | RSD TOLT BRG 1834A EMGY RPR-17 | subproject | Jiang | #DIV/0!
1132949 | RSD ISS HOB RD ENH SIGNAL | subproject | McManus | #DIV/0!
1136087 | RSD FOSS RIVER BRG 2605A PAINT | subproject | Martin | #DIV/0!
1136631 | RSD JUDD CK BRD 3184 RPR | subproject | Jiang | #DIV/0!
1136633 | RSD PATTON BRD 3015 BKT RPR | subproject | Jiang | -0.2452%
1136972 | RSD SW 108&8 AV SW RNDBT REVSN | subproject | McManus | #DIV/0!
1137364 | RSD WSDE HWY SW DEGRADATN | subproject | Posey | #DIV/0!
1137509 | RSD DOCKTON SEAWALL RPR | subproject | Roark | #DIV/0!
1137577 | RSD 304 ST HAUL RD MITGN | subproject | Moore | #DIV/0!
1137572 | RSD REDMOND RIDGE DR NE XNG | subproject | Hafele | #DIV/0!
1137584 | RSD MIDDLE FORK RD RPR | subproject | Cassidy | #DIV/0!
1137860 | RSD 2019 DVD PWLL RD RPR 36621 | subproject |  | #DIV/0!
1129714 | RSD NE STILLWATER HILL RD | subproject | Sahagun | 57.53%
1133219 | RSD VASHON HWY SW PAVE PRES | subproject | Moore | #DIV/0!
1133220 | RSD 2018 CNTYWDE PAVE PRES | subproject | Moore | #DIV/0!
1133757 | RSD 2018 BITUM SURF TREATMENT | subproject | Moore | #DIV/0!
1136086 | RSD 218TH AV SE RECONSTRUCTION | subproject | Bleasdale | -6.962%
1136351 | RSD CURB RAMP REPLACEMENT 3855 | subproject | Moore | #DIV/0!
1136352 | RSD 2019 CNTYWDE PAVE PRES | subproject | Moore | #DIV/0!
1137996 | RSD 2020 CNTYWDE PAVE PRES | subproject | Moore | #DIV/0!
1136934 | RSD HRP BCON COAL MINE RD S | subproject | Moore | #DIV/0!
1136935 | RSD HRP 236A SE SE 384 ST | subproject | Moore | #DIV/0!
1137078 | RSD HRP SE GREEN VALLEY RD | subproject | Moore | #DIV/0!
1137510 | RSD HRP SE EDGEWICK ROAD | subproject | Moore | #DIV/0!
TBD | TBD | subproject | Bridge and Construction | #DIV/0!
1129716 | RSD DIVISION 1 DRAINAGE | subproject | Drainage | #DIV/0!
1129717 | RSD DIVISION 2 DRAINAGE | subproject | Drainage | #DIV/0!
1129718 | RSD DIVISION 3 DRAINAGE | subproject | Drainage | #DIV/0!
1129720 | RSD DIVISION 4 DRAINAGE | subproject | Drainage | #DIV/0!
1129721 | RSD DIVISION 5 DRAINAGE | subproject | Drainage | #DIV/0!
1129722 | RSD DIVISION 6 DRAINAGE | subproject | Drainage | #DIV/0!
1129723 | RSD DIVISION 1 SHOULDERING | subproject | Maintenance | #DIV/0!
1129724 | RSD DIVISION 2 SHOULDERING | subproject | Maintenance | #DIV/0!
1129725 | RSD DIVISION 3 SHOULDERING | subproject | Maintenance | #DIV/0!
1129726 | RSD DIVISION 4 SHOULDERING | subproject | Maintenance | #DIV/0!
1129727 | RSD DIVISION 5 SHOULDERING | subproject | Maintenance | #DIV/0!
1129728 | RSD DIVISION 6 SHOULDERING | subproject | Maintenance | #DIV/0!
1131511 | RSD SAHALEE WY NE 46000 BLK | subproject | Drainage | #DIV/0!
1131526 | RSD SE PTRVSKY & 134 A SE | subproject | Drainage | #DIV/0!
1131671 | RSD SE PTRVSKY @ 151ST A SE | subproject | Drainage | #DIV/0!
1131672 | RSD SE PTRVSKY @20300BLK | subproject | Drainage | #DIV/0!
1132446 | RSD S LANGSTN RD@132ST DRG IMP | subproject | Drainage | #DIV/0!
1132523 | RSD GREEN RVR RD S28728 DR IMP | subproject | Drainage | #DIV/0!
1132710 | RSD DRAIN IMP SAHALEE-4800 | subproject | Drainage | #DIV/0!
1131274 | RSD 2017-18 GUARDRAIL PRESVTN | subproject | Design and Traffic | -2.631%
1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | subproject | Design and Traffic | -4.194%
1138763 | RSD 2019-20 GUARDRAIL PRESERVATION 2 NEW | subproject |  | #DIV/0!
1133675 | RSD YORK BRG 225C RPR | subproject | Bridge and Construction | #DIV/0!
1136209 | RSD 2019 BRIDGE WASHING | subproject | Bridge and Construction | #DIV/0!
1136212 | RSD SUNDAY CR BRG 364C RPR | subproject | Bridge and Construction | #DIV/0!
1136453 | RSD FSH HTCH BRG 61B APRCH RPR | subproject | Bridge and Construction | #DIV/0!
1137079 | RSD OVERFLW BR 3217 OVLY | subproject | Bridge and Construction | #DIV/0!
1137161 | RSD STOSSEL BR 1023A GUSSETS | subproject | Bridge and Construction | #DIV/0!
1137385 | RSD PRESTON FRNT BRG 5046 OVLY | subproject | Bridge and Construction | #DIV/0!
1137752 | RSD FLMNG GYSR BRG 3024 PNTG | subproject | Bridge and Construction | #DIV/0!
1137856 | RSD BRNG BR TMBR.SCR RPR 2019 | subproject | Bridge and Construction | #DIV/0!
1137858 | RSD 2019 LK DRTHY LJM BR359B | subproject | Bridge and Construction | 0.7727%
| 2020 Bridge Washing | subproject | Bridge and Construction | -0.683%
| Berrydale OX 3080OX Deck Repair | subproject | Bridge and Construction | #DIV/0!
| 4 Creek Ranch 5044 Deck Repair | subproject | Bridge and Construction | #DIV/0!
| 2020 Bridge Priority Maintenance Project 4 | subproject | Bridge and Construction | #DIV/0!
| 2020 Bridge Priority Maintenance Project 5 | subproject | Bridge and Construction | #DIV/0!
TBD | Projects TBD | subproject | Bridge and Construction | #DIV/0!
1134048 | RSD BRAC WD DUV BRG 1136E RPR | subproject | Bridge and Construction | #DIV/0!
1134049 | RSD BRAC LANDSBRG BRG 3075 RPR | subproject | Bridge and Construction | -9.3%
1131157 | RSD HGH COLLSN SIGHTLINE IMPV | subproject | Design and Traffic | #DIV/0!
1137862 | RSD 2020 HGH FRCTN SFC TRTMT | subproject | Design and Traffic | #DIV/0!
TBD | 164th Place and Covington Sawyer Road | subproject | Design and Traffic | #DIV/0!
| 16th Avenue SW Pedestrian Improvement | subproject |  | #DIV/0!
| TBD -- early action countermeasures when next High Collision report is released | subproject | Design and Traffic | #DIV/0!
1131557 | RSD 17-18 SCHOOL ZONE SAFETY | subproject | Design and Traffic | #DIV/0!
1136576 | RSD 19-20 SCHOOL ZONE SAFETY | subproject | Design and Traffic | #DIV/0!
1136582 | RSD S 298TH ST SCHOOL PTHWY | subproject | Design and Traffic | #DIV/0!
1136580 | RSD S 360TH ST SCHOOL PTHWY | subproject | Design and Traffic | #DIV/0!
1136646 | RSD 42ND AVE S SCHOOL PTHWY | subproject | Design and Traffic | #DIV/0!
1130706 | RSD FC NE 8S@LK ALLEN OLET CDR | subproject | Drainage | #DIV/0!
1130707 | RSD FC 162 AVE SE @ SE 166 CT | subproject | Drainage | -34.95%
1130708 | RSD FC DAVID POWELL RD RPR | subproject | Drainage | #DIV/0!
1130710 | RSD FC 380 PL @SR-164 CDR | subproject | Drainage | 14.07%
1133600 | RSD FC FIFTEEN ML CR BRG #493C | subproject | Bridge and Construction | -1.157%
1138337 | RSD FC FSH HTCHRY BRG 61B RPR | subproject | Bridge and Construction | #DIV/0!
1138339 | RSD FC S 106 ST DRAINAGE IMPRV | subproject | Drainage | #DIV/0!
1136715 | RSD LEFT TURN PHASING | subproject | Design and Traffic | 286.9%
1136709 | RSD TRAFFIC CALMING | subproject | Design and Traffic | #DIV/0!
1136711 | RSD ROADWAY LIGHTING | subproject | Design and Traffic | -53.61%
1136712 | RSD RADAR SPEED SIGNS | subproject | Design and Traffic | #DIV/0!
1136716 | RSD TRANSVERSE RUMBLE SIGNS | subproject | Design and Traffic | #DIV/0!
1136228 | RSD PET RD AT 134TH CULVERT | subproject | Drainage | #DIV/0!
1136229 | RSD 180TH AT 408TH CULVERT | subproject | Drainage | 0.5%
1136231 | RSD 185TH AT 179TH CULVERT | subproject | Drainage | #DIV/0!
1136232 | RSD 18430 NE 128TH WY CULVERT | subproject | Drainage | -15.38%
1136233 | RSD LAKE JOY AT 118TH CULVERT | subproject | Drainage | 7.237%
1136234 | RSD WD DUV AT 172ND CULVERT | subproject | Drainage | #DIV/0!
1136235 | RSD AVONDALE AND 144TH CULVERT | subproject | Drainage | -22.92%
1136236 | RSD 165TH AND 176TH CULVERT | subproject | Drainage | -1.99%
1136230 | RSD FAIRWOOD E OF 151 CULVERT | subproject | Drainage | #DIV/0!
1136237 | RSD S 370TH ST CULVERT | subproject | Drainage | #DIV/0!
1136238 | RSD 33609 NE 24TH ST CULVERT | subproject | Drainage | #DIV/0!
1136239 | RSD 317TH AND THOMAS CULVERT | subproject | Drainage | #DIV/0!
1136240 | RSD 22233 NE 170TH PL CULVERT | subproject | Drainage | #DIV/0!
1136241 | RSD 28278 GREEN RVR RD CULVERT | subproject | Drainage | #DIV/0!
1136419 | SE 432nd Street at 27606 | subproject | Drainage | #DIV/0!
1131132 | RSD 2017-18 NEW GRDL CONSTRUCT | subproject | Design and Traffic | #DIV/0!
1136084 | RSD 2019-20 NEW GRDRAIL CONST | subproject | Design and Traffic | -15.88%
Note on B123: Guerrero, Sheilla: Changed name to include s

## Prism Export
Number | Name | Active | EAC (Current) | Lifetime Appropriation | EAC Gate 3
1026798 | RSD EMRGNT NEED-EXISTING PRJ | Yes |  | 0.26
1026799 | RSD CIP GRANT CONTIGENCY | Yes
1026800 | RSD CAP PROJ O S FUND 3860 | Yes | 179399.42 | 179399.42
1027163 | RSD QUICK RESPONSE | Yes | 16955637.89 | 17665361.05
1111819 | RSD C W DRAINAGE PRESERVATION | Yes | 29370485.72 | 30715568.14
1114792 | RSD ROADS-COUNTY ROAD CONST | Yes | 10596271.61 | 10878774.33
1116885 | RSD WOODINVILLE DUVALL ITS | Yes | 1091709.71 | 1438000.06
1124986 | RSD CW HRRRP | Yes | 2454816.42 | 3290000.01
1127271 | RSD PRESTON MAINT FACILITY | Yes | 1927906.18 | 4500000.06
1127273 | RSD FAILED ENV & HVAC REHAB | Yes | 7297029.4938 | 7150000 | 6216227.9576
1127589 | RSD 165 ST FLD RSK RDUCTN | Yes | 811593.11 | 760146
1127590 | RSD 212 AV SE FLD RSK RDUCTN | Yes | 235859.8 | 409594
1129582 | RSD EMERGENT NEED 3855 | Yes | 1335457.3433 | 3215188
1129583 | RSD GRANT CONTINGENCY 3855 | Yes |  | 7730053
1129584 | RSD CWP QUICK RESPONSE | Yes | 13681111.7724 | 13687000
1129585 | RSD CWP ROADWAY PRESERVATION | Yes | 69192794.988 | 53157434
1129586 | RSD CWP DRAINAGE PRESERVATION | Yes | 35881088.6885 | 22971916
1129587 | RSD CWP GUARDRAIL PRESERVATION | Yes | 8447323.292 | 8800000
1129588 | RSD CWP BRIDGE PRIORITY MAINT | Yes | 7761399.3046 | 5225961
1129590 | RSD CWP HIGH COLLISION SAFETY | Yes | 8271762.9344 | 7877167
1129591 | RSD CWP SCHOOL ZONE SAFETY | Yes | 1552960.9022 | 1615150
1129592 | RSD EMERGENT NEED 3865 | Yes |  | 818448
1129593 | RSD GRANT CONTINGENCY 3865 | Yes |  | 4845711
1129594 | RSD CWP GUARDRAIL CONSTRUCTION | Yes | 2802191.0792 | 2150000
1129595 | RSD OLD CASCADE/MILLER BR WEST | Yes | 2254358.4047 | 2300000 | 2299999.89
1129596 | RSD OLD CASCADE/MILLER BR EAST | Yes | 2719436.9767 | 2750000 | 2750000.51
1129598 | RSD ISS HBRT RD@MAY VLLY IMPRV | Yes | 669943.52 | 755000
1129599 | RSD RENTON AVE PH III SIDEWALK | Yes | 2798477.2227 | 2854412 | 3399999.3319
1129714 | RSD NE STILLWATER HILL RD | Yes | 4270387.5293 | 845190 | 5049999.4596
1129716 | RSD DIVISION 1 DRAINAGE | Yes | 893769.68 | 991430
1129717 | RSD DIVISION 2 DRAINAGE | Yes | 521150.34 | 587642.08
1129718 | RSD DIVISION 3 DRAINAGE | Yes | 5999133.55 | 6179274
1129720 | RSD DIVISION 4 DRAINAGE | Yes | 1881565.6 | 1925419
1129721 | RSD DIVISION 5 DRAINAGE | Yes | 1612415.88 | 1927255
1129722 | RSD DIVISION 6 DRAINAGE | Yes | 123606.66 | 123913
1129841 | RSD CIP OVERSIGHT 3855 | Yes | 46425.64 | 110091
1130162 | RSD SUNSET RD SW SLIDE REPAIR | Yes | 830581.32 | 835149
1130260 | RSD SW 108&8 AV SW ROUNDABOUT | Yes | 720365.46 | 792000
1130261 | RSD SE176&SE171 WAY ROUNDABOUT | Yes | 491701.79 | 490000
1130303 | RSD CIP OVERSIGHT 3865 | Yes | 11986.53 | 30072
1130707 | RSD FC 162 AVE SE @ SE 166 CT | Yes | 5173305.77 | 4566000 | 2542600.36
1130708 | RSD FC DAVID POWELL RD RPR | Yes | 1074203.07 | 2050000 | 1916000.24
1130710 | RSD FC 380 PL @SR-164 CDR | Yes | 996484.7967 | 590000 | 1001250.3936
1130962 | RSD BLK DMND-RVNSDL RD SLD RPR | Yes | 531772.91 | 531772.91
1131132 | RSD 2017-18 NEW GRDL CONSTRUCT | Yes | 1100788.91 | 1100788.91 | 1349999.97
1131157 | RSD HGH COLLSN SIGHTLINE IMPV | Yes | 171863.6 | 150000
1131162 | RSD HGH COLLSN SIGNAL MOD | Yes | 68997.89 | 68997.89
1131163 | RSD HGH FRICTION SURF TMT | Yes | 2319640 | 3269290 | 3145000
1131235 | RSD S 360ST&MILITARY RD RNDABT | Yes | 4181199.9672 | 4150000
1131236 | RSD S LANGSTON RD&59 AV RNDABT | Yes | 57842.02 | 57842
1131237 | RSD SW 102 ST&8 AVE SW RNDABT | Yes | 678407.95 | 678408
1131274 | RSD 2017-18 GUARDRAIL PRESVTN | Yes | 3151457.55 | 3200000 | 4800000.02
1131333 | RSD CWP FLOOD CONTROL DISTRICT | Yes | 15679665.3421 | 13609700
1131387 | RSD 2017 CW PVMNT PRESERVATION | Yes | 12953162.39 | 12953162.39 | 14899999.89
1131508 | RSD DIV 4 FACLTY IMPRVMT 17-18 | Yes | 175077.63 | 175077.63
1131511 | RSD SAHALEE WY NE 46000 BLK | Yes | 362498.05 | 160000
1131526 | RSD SE PTRVSKY & 134 A SE | Yes | 5325001.279 | 530700.26
1131557 | RSD 17-18 SCHOOL ZONE SAFETY | Yes | 771490.13 | 771490.13
1131582 | RSD NE WD/DVL CULVERT REPL | Yes | 994760.7 | 994760.7 | 1155000.06
1131671 | RSD SE PTRVSKY @ 151ST A SE | Yes | 248469.71 | 102800
1131672 | RSD SE PTRVSKY @20300BLK | Yes | 175322.83 | 91200
1131693 | RSD UNION HILL@225 BOXCULVRT | Yes | 795984.85 | 797179.69 | 1099999.74
1132446 | RSD S LANGSTN RD@132ST DRG IMP | Yes | 303809.67 | 309000
1132448 | RSD SW 108ST@10 AVE SW DRG IMP | Yes | 15800.85 | 15800.85
1132450 | RSD 177 AVE SE DRG IMP | Yes | 40593.52 | 40593.52
1132523 | RSD GREEN RVR RD S28728 DR IMP | Yes | 106311.99 | 106311.99
1132710 | RSD DRAIN IMP SAHALEE-4800 | Yes | 341170.88 | 100000
1132958 | RSD 15 MILE BRDG #1384A LOAD | Yes | 286572.71 | 286572.71
1133219 | RSD VASHON HWY SW PAVE PRES | Yes | 4730146.46 | 4880000 | 5700000
1133220 | RSD 2018 CNTYWDE PAVE PRES | Yes | 4447489.29 | 4447489.29 | 4300000.49
1133413 | RSD SE SAWYER RDG OVERLAY | Yes | 193013.24 | 193013.24
1133440 | RSD MOUNT VIEW RD REPAIR | Yes | 106104.14 | 106104.14
1133600 | RSD FC FIFTEEN ML CR BRG #493C | Yes | 322547.46 | 350000.01
1133757 | RSD 2018 BITUM SURF TREATMENT | Yes | 3234062.61 | 3234062.61 | 4763000
1133864 | RSD NE NVLTY HILL RD TRAIL | Yes | 347559.23 | 347559.23
1134079 | RSD KENTKANGLEY LNDSBRG RNDABT | Yes | 1266468.7274 | 100000
1134080 | RSD WDDUV SNOQ VALLEY IMPROVE | Yes | 412629.5891 | 150000
1134081 | RSD REDMOND RIDGE DR NE RNDABT | Yes | 1457608.8067 | 1200000 | 1379999.52
1134082 | RSD FACILITIES LED CONVERSION | Yes | 289181.28 | 900000
1134083 | RSD COVINGTON WAY SE IMPROVE | Yes | 213940.46 | 300001
1135042 | RSD VASHON MAINT FACILITY REPL | Yes | 15453207.3091 | 505000
1135043 | RSD NE MAINT FACILITY REPL | Yes | 22233006.3873
1135045 | RSD CWP CLVRT RPLCMT FISH PASS | Yes | 14025265.9442 | 8822000
1135046 | RSD MAINT HDQTRS BLDG D REHAB | Yes | 2880558.78 | 1800000 | 1800000.2264
1135073 | RSD CWP 2019-20 BRIDGE SAFETY | Yes |  | 24085428
1135997 | RSD COAL CREEK BRG 3035A REPL | Yes | 6619816.296 | 0.07 | 5534359.8348
1135998 | RSD AMES LK TRS BRG 1320A REPL | Yes | 10111246.4549 | 0.07 | 10165177.4481
1135999 | RSD UPR TOKUL CK BRG 271B REPL | Yes | 5045999.6746 | 0.04
1136000 | RSD BARING BRG 509A REPL | Yes | 13144595.6684 | 0.04
1136001 | RSD 277TH ST BRG 3126 REPL | Yes | 2555316.0528 | 0.04 | 1953030.6524
1136084 | RSD 2019-20 NEW GRDRAIL CONST | Yes | 1235274.8 | 1049211.09 | 1045000.2047
1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | Yes | 3598914.55 | 4100000 | 4520001.008
1136086 | RSD 218TH AV SE RECONSTRUCTION | Yes | 5468484.2546 | 877846
1136228 | RSD PET RD AT 134TH CULVERT | Yes
1136229 | RSD 180TH AT 408TH CULVERT | Yes | 704656.0738 | 292000
1136230 | RSD FAIRWOOD E OF 151 CULVERT | Yes | 1407.61 | 10000
1136231 | RSD 185TH AT 179TH CULVERT | Yes | 1147132.7994 | 122000
1136232 | RSD 18430 NE 128TH WY CULVERT | Yes | 896682.59 | 332000
1136233 | RSD LAKE JOY AT 118TH CULVERT | Yes | 1925321.87 | 262000
1136234 | RSD WD DUV AT 172ND CULVERT | Yes | 1769920.73 | 322000
1136235 | RSD AVONDALE AND 144TH CULVERT | Yes | 2309147.7407 | 332000
1136236 | RSD 165TH AND 176TH CULVERT | Yes | 658688.35 | 332000
1136237 | RSD S 370TH ST CULVERT | Yes | 13851.96 | 57000
1136238 | RSD 33609 NE 24TH ST CULVERT | Yes | 913608.1271 | 57000
1136239 | RSD 317TH AND THOMAS CULVERT | Yes | 975352.1199 | 57000
1136241 | RSD 28278 GREEN RVR RD CULVERT | Yes | 1040834.05 | 1044000
1136351 | RSD CURB RAMP REPLACEMENT 3855 | Yes | 305736.17 | 300000
1136352 | RSD 2019 CNTYWDE PAVE PRES | Yes | 2782956.73 | 3127798 | 3067000.1934
1136419 | RSD SE 432ND ST CULVERT | Yes | 1101340.1614 | 57000
1136453 | RSD FSH HTCH BRG 61B APRCH RPR | Yes | 12231.52 | 12231.52
1136576 | RSD 19-20 SCHOOL ZONE SAFETY | Yes | 224135.6 | 248509.87
1136580 | RSD S 360TH ST SCHOOL PTHWY | Yes | 258894.068 | 208300
1136582 | RSD S 298TH ST SCHOOL PTHWY | Yes | 102250.95 | 120000
1136631 | RSD JUDD CK BRD 3184 RPR | Yes | 93832.79 | 100000
1136633 | RSD PATTON BRD 3015 BKT RPR | Yes | 115422.22 | 620000
1136646 | RSD 42ND AVE S SCHOOL PTHWY | Yes | 110016.43 | 99700
1136709 | RSD TRAFFIC CALMING | Yes | 21152.26 | 100000
1136711 | RSD ROADWAY LIGHTING | Yes | 379083.76 | 375000
1136712 | RSD RADAR SPEED SIGNS | Yes | 72329.68 | 150000
1136715 | RSD LEFT TURN PHASING | Yes | 144228.55 | 200000
1136716 | RSD TRANSVERSE RUMBLE SIGNS | Yes | 3204.42 | 168000
1136930 | RSD CIP DBASE RPLCMNT | Yes | 105398.95 | 250000
1136931 | RSD SCALE DBASE RPLCMNT | Yes | 86146.26 | 200000
1136932 | RSD BIZDOC MAP VLT RPLCMNT | Yes | 78748.01 | 90000
1136933 | RSD CUTRL RES DBASE RPLCMNT | Yes | 35978.96 | 125000
1136972 | RSD SW 108&8 AV SW RNDBT REVSN | Yes | 66007.28 | 66007.28
1137364 | RSD WSDE HWY SW DEGRADATN | Yes | 32781.29 | 32781.29
1137509 | RSD DOCKTON SEAWALL RPR | Yes | 389755.92 | 391542.41
1137577 | RSD 304 ST HAUL RD MITGN | Yes |  | 155000
1137584 | RSD MIDDLE FORK RD RPR | Yes | 41832.96 | 76000
1137752 | RSD FLMNG GYSR BRG 3024 PNTG | Yes | 801840.3993 | 857000
1137856 | RSD BRNG BR TMBR.SCR RPR 2019 | Yes | 46605.37 | 46605.38
1137860 | RSD 2019 DVD PWLL RD RPR 36621 | Yes | 42018.75 | 100000
1137862 | RSD 2020 HGH FRCTN SFC TRTMT | Yes | 3053659.6293 | 537400 | 3139019.2148
1137996 | RSD 2020 CNTYWDE PAVE PRES | Yes | 5920885.71 | 5195706 | 4444263.9775
1138326 | RSD 2020 BRIDGE WASHING | Yes | 46996.42 | 120000
1138330 | RSD CVGTN SWYR SGHTLN IMPR | Yes | 794129.6844 | 100000
1138337 | RSD FC FSH HTCHRY BRG 61B RPR | Yes | 43933.48 | 80000
1138339 | RSD FC S 106 ST DRAINAGE IMPRV | Yes | 413592 | 151000
1138763 | RSD 2019-20 GUARDRAL PRSRVTN 2 | Yes | 531902.3428 | 500000
1138769 | RSD BERRYDALE OX #3086 DECK | Yes | 91999.59 | 115000
1138770 | RSD DEEP CREEK #364 DECK RPR | Yes | 21675.33 | 21675.33
1138913 | RSD BOISE X BRDG #3055A REPL | Yes | 2971062.1711 | 0.06
1138914 | RSD FIFTN MILE CRK#493C B REP | Yes | 5471258.3527 | 0.08
1138918 | RSD 16TH AVE PED IMPRVMNTS | Yes | 976312.183 | 958000
1139144 | RSD SE REINIG RD DRNG IMPR CUL | Yes | 1456310 | 1500000
1139145 | RSD SE GRN VLLY & 218 AVE INT | Yes | 674999.7306 | 675000
1139146 | RSD RAINIER S & LKRDG DR INT | Yes | 1499999.5106 | 400000
1139147 | RSD CWP ADA PROGRAM | Yes | 1297706.9072 | 300000
1139236 | RSD JUDD CK BRG 3184 RECONT | Yes | 230040.7 | 255000
1139286 | RSD CWP BRIDGE LOAD UPGRD SFTY | Yes | 3228155.4439 | 780000
1139716 | RSD S LANGSTN RD@125TH DRG IM | Yes | 8375.41 | 778416
1139744 | RSD 4-CREEK-RANCH 5044 DECK | Yes | 13736.04 | 260000
1139749 | RSD MMS REPLACEMENT | Yes |  | 1000000
1139810 | RSD BEALL RD SW RESTOR CULVERT | Yes |  | 575000
1139811 | RSD SE384TH DRNG IMPRV CULVERT | Yes |  | 1150000
1139815 | RSD 356TH DR SE WINTER 2020 | Yes | 2736005.94 | 3000000
1140178 | RSD BEAR CREEK BRG#480A APPRCH | Yes | 8773.46 | 35000
1140858 | RSD 244TH AVE NE WINTER 2020 | Yes |  | 200000
1140905 | RSD 17401 SE 240 ST SE CULVERT | Yes |  | 400000
1140906 | RSD 156TH SE- SE 240TH CULVERT | Yes |  | 100000
1141001 | RSD TOLT BRG 1834A RP WNTR2020 | Yes
1141044 | RSD 2021 CNTYWDE PAVE PRES | Yes
1141111 | RSD 2019-20 GUARDRAL PRSRVTN 3 | Yes
2020-001 | DRN DIV DRN | Yes
2020-002 | DRN DIV SHOULDER | Yes
2020-003 | PAV Pres Sub | Yes
2020-004 | BRG BPM list | Yes
2020-005 | HIGH COLLISION | Yes
2020-006 | SCHOOL SAFETY | Yes
2020-007 | TRAFFIC SAFETY | Yes
Test-RSD | Test | Yes |  |  | 0
1026676 | RSD ROOFING ENERGY EFFICIENCY | No | 3092432.87 | 3092432.87
1026677 | RSD RNTN BLDG BOND DEBT RTRMT | No | 2717905.38 | 2717905.38
1026678 | RSD CAP PROJ O S RENTON CIP | No | 5094.68 | 5094.68
1026726 | RSD INFORMATION TECH PROJECTS | No | 637877.29 | 637877.29
1026727 | RSD 100 AV NE NE 132 NE 137 | No | 384292.89 | 384292.89
1026728 | RSD SAFER WILDLIFE COMM MBLTY | No | 4759011.54 | 4759011.54
1026729 | RSD NOVELTY HL RD ITS ENHNCMT | No | 350090.74 | 350090.74
1026730 | RSD NOVELTY HILL RD AVON 238 | No | 64165015.39 | 64165015.39
1026731 | RSD LK ALICE RD SE CLVRT RPLC | No | 2109825.21 | 2109825.21
1026732 | RSD PATTERSON CREEK BRG #180L | No | 3299694.48 | 3299694.48
1026734 | RSD PRESTON FC RD SE SLIDE RP | No | -75.78 | -75.78
1026735 | RSD W SNOQUALMIE VALLEY RD NE | No | 6816689.55 | 6816689.55
1026736 | RSD 324 AV NE CULVERT RPLCMNT | No | 55.7 | 55.7
1026737 | RSD S 277 ST ITS 55AV S SR167 | No | 1067596.47 | 1067596.47
1026738 | RSD S STAR LK RD MIL RD 42 AV | No | 705921.75 | 705921.75
1026739 | RSD SOUTH PARK BRG | No | 172537335.46 | 172537335.46
1026740 | RSD 16A SW ITS SW RXBRY SW116 | No | 1355685.67 | 1355685.67
1026742 | RSD MILITARY RD S&S 342 ST | No | 2007531.69 | 2007531.69
1026789 | RSD ALVORD T BRG #3130 DEM | No | 1433338.13 | 1433338.13
1026790 | RSD NEWAUKUM CRK BRG RPLCMNT | No | 1255688.28 | 1255688.28
1026791 | RSD SE SUMMIT LANDSBURG RD | No | 1437842.6 | 1437842.6
1026792 | RSD NEWAUKUM CR BRG #3042 | No | 1091740.75 | 1091740.75
1026793 | RSD GRN VLY BR-E/O 180 AV NE | No | 53828.76 | 53828.76
1026794 | RSD SE 424 ST BRG RPLCMNT | No | 1240885.06 | 1240885.06
1026795 | RSD 15 MILE CRK BRG RPLCMENT | No | 2593661.64 | 2593661.64
1026796 | RSD CIP BOND DEBT PAYMENT | No | 59046215.66 | 59046215.66
1026797 | RSD HUD DEBT SERVICE PAYMENTS | No | 3600000 | 3600000
1026801 | RSD CW GUARDRAIL PROGRAM ADMIN | No | 1106866.41 | 1106866.41
1026802 | RSD 2010 C W GUARDRAIL PROJCT | No
1026803 | RSD FINANCIAL ADMIN MRSDR1 | No | 155154.73 | 155154.73
1026804 | RSD PROPERTY SALE COMP PROJ | No | 99798.95 | 99798.95
1026805 | RSD WA DOT ENCUMBRANCE REVIEW | No |  | 0
1026853 | RSD BRIDGE PRIORITY MTCE ADMIN | No | 477532.48 | 477532.48
1027150 | RSD 2009 NORTH COUNTY OVERLAY | No
1027151 | RSD 2010 NORTH COUNTY OVERLAY | No
1027152 | RSD 2010 SOUTH COUNTY OVERLAY | No
1027153 | RSD 2011 C W OVERLAY PS AND E | No
1027154 | RSD ADA PROGRAM ADMIN | No | 26750.67 | 26750.67
1027155 | RSD 2011 ADA-NORTH OVERLAY | No | 206019.59 | 206019.59
1027156 | RSD 2011 ADA-SOUTH OVERLAY | No |  | 0
1027157 | RSD 2011 ADA PROGRAM PS&E | No | 236735.96 | 236735.96
1027158 | RSD CW ROADWAY PRESERVATION | No | 31040449.11 | 31040449.11
1027159 | RSD ADA COMPLIANCE | No | 2954894.29 | 2954894.29
1027160 | RSD BRG PRIORITY MAINTNCE | No | 3669766.32 | 3669766.32
1027161 | RSD CLEAR ZONE SAFETY PROGRAM | No | 4773743.23 | 4773743.23
1027162 | RSD PERMIT MNTRNG&REMEDIATION | No | 231.5 | 231.5
1047572 | RSD FAY ROAD RETAINING WALL | No | 269.14 | 269.14
1047573 | RSD S 360 ST/SR161-32 AVE S | No | 45244.89 | 45244.89
1047575 | RSD GRN VLLY BR/202P-212AV SE | No | 46039.26 | 46039.26
1047576 | RSD 2011 C/W GUARDRAIL PRJECT | No | 858187.88 | 858187.88
1111170 | RSD COTTAGE LK CRK BRDGE #240A | No | 2876.01 | 2876.01
1111171 | RSD FACILITIES MASTER PLAN | No | 80415.09 | 80415.09
1111172 | RSD FACIL PRESERVATION C/WIDE | No | 2224158.81 | 2224158.81
1111173 | RSD W SNOQ VAL ROADWY REPAIR | No | 654794.44 | 654794.44
1111174 | RSD MILLER RIVER BRDGE REPLCMT | No
1111175 | RSD KENT KNGLEY RD CLVRT REPL | No | 245029.22 | 245029.22
1111176 | RSD NOVELTY RD AT TRILOGY ADA | No | 147315.67 | 147315.67
1111177 | RSD ISSAQUAH HOBART RD SE | No | 1080195.21 | 1080195.21
1111178 | RSD UPPER PRESTON RD SE&SE97th | No | 34.88 | 34.88
1111179 | RSD DRAINAGE PRESERVATION | No
1111817 | RSD SOUTH RGNL MAINT FACILITY | No | 3770708.25 | 3770708.25
1111818 | RSD 2011 NORTH COUNTY OVERLAY | No | 2521001.07 | 2521001.07
1111820 | RSD PEASLEY CANYON RD AT PC WA | No | 1449859.76 | 1449859.76
1111821 | RSD 2012 C/W OVERLAY PS&E | No | 363493.26 | 363493.26
1111822 | RSD RCAMM RDS COMP ASSET AND M | No | 637877.29 | 637877.29
1111823 | RSD 2011 SOUTH COUNTY OVERLAY | No | 3433482.97 | 3433482.97
1111824 | RSD PRESTON FC AT SE HIGH PT | No | 557346.67 | 557346.67
1111825 | RSD RENTON AV SDWLK 75-76 AV | No | 1134019.18 | 1134019.18
1114398 | RSD BEAR CREEK BRIDGE #480A | No | 945.64 | 945.64
1114399 | RSD AVONDALE RD ITS PHASE 1 | No | 1717805.48 | 1717805.48
1114655 | RSD W AMES LK DR DRNG IMPVMNTS | No
1114656 | RSD CORNELL AVE DRNG IMPRVMNTS | No | 1790.92 | 1790.92
1114657 | RSD SE408&292AV DRNG IMPVMNTS | No | 52960.29 | 52960.29
1114659 | RSD DRNG DSGN NE8B/T245P&24800 | No | 1014.47 | 1014.47
1114660 | RSD DRNG DSGN 3919 S 301 PL | No | 102169.33 | 102169.33
1114789 | RSD PROPERTY SALE TRANS COSTS | No | 313265.19 | 313265.19
1114790 | RSD ESS STAFF CONVERSION TRNG | No |  | 0
1114791 | RSD ROADS-RENTON FACILITY | No | 1119300.06 | 1193474.06
1114793 | RSD SKYKOMISH SHOP REPAIRS | No
1114794 | RSD BEACON COAL MINE RD S | No |  | 0
1114795 | RSD BANDARET BRIDGE #493B | No | 6749209.92 | 6749209.92
1114796 | RSD SE 277 ST BRIDGE #3126 | No | 239619.64 | 239619.64
1114797 | RSD SE 408 ST&292 AVE SE DRNG | No
1114798 | RSD COUNTYWIDE OVERLAY ADMIN | No | 278929.54 | 278929.54
1114799 | RSD ASSET MGMT ASSESSMENT | No | 369736.54 | 369736.54
1114800 | RSD DOCKTON/ELLISPORT-PORTAGE | No | 45530.43 | 45530.43
1114801 | RSD GORUSECH RD SLIDE REPAIR | No | 241976.67 | 241976.67
1114802 | RSD 17 AV SE/SE 100-SW 104 ST | No | 464102.78 | 464102.78
1114803 | RSD MONEY CREEK SCOUR REPAIR | No
1114804 | RSD RENTON AV S RKRY/SDWLK RPR | No | 661868.57 | 661868.57
1114877 | RSD DRNG DSGN SW 112&25 AV SW | No
1114878 | RSD DRNG DSGN 28841 164 AV SE | No
1114879 | RSD DRNG FISH NE165W/O176AV NE | No
1114880 | RSD DRNG FISH 20229 NE 198 ST | No
1114881 | RSD DRNG FISH SE NWPT E/O152AV | No
1114883 | RSD DRNG FISH26428SE KNT-KNGLY | No
1115087 | RSD ISSAQUAH NSPAR CONTRBUTION | No
1115090 | RSD JUANITA-WOODNVL/NE 160 ITS | No
1115091 | RSD 100 AV NE ITS/NE132-NE145 | No | 21.97 | 21.97
1115092 | RSD MILITARY RD S & S 272 ST | No
1115099 | RSD MIDDLE FORK SNOQ RIVER RD | No | 232020.15 | 232020.15
1115104 | RSD 2012 C/W GUARDRAIL PROJECT | No | 729844.12 | 729844.12
1115106 | RSD 2012 NORTH COUNTY OVERLAY | No
1115107 | RSD 2012 SOUTH COUNTY OVERLAY | No
1115114 | RSD AVONDALE ITS PHASE 2 | No | 1770243.78 | 1770243.78
1115235 | RSD CW NEAL BRIDGE #249B | No
1115237 | RSD CW NEAL RD BRIDGE #249C | No
1115238 | RSD 312 AVE SE BRIDGE #228F | No
1115244 | RSD 2012 ADA-NORTH OVERLAY | No | 585981.6 | 585981.6
1115245 | RSD 2012 ADA-SOUTH OVERLAY | No | 286659.95 | 286659.95
1115246 | RSD 2012 ADA PROGRAM-PS&E | No | 346674.42 | 346674.42
1115252 | RSD SE MID FORK SNOQ RIVER RD | No | 647891.89 | 647891.89
1115255 | RSD NE WD/DVL RD@W SNOQ VLY RD | No | 330940.59 | 330940.59
1115260 | RSD BEAR CREEK BRIDGE #333A | No | 2536.01 | 2536.01
1115264 | RSD KENT-BLACK DIAMND&SE292 ST | No | 350345.73 | 350345.73
1115298 | RSD DRNG FISH KERRISTON RD | No | 25673.63 | 25673.63
1115299 | RSD DRNG DSGN140P NE N/O 16116 | No | 406.7 | 406.7
1115300 | RSD DRNG DSGN SE ISS/FC&DUTHIE | No
1115301 | RSD DRNG DSGN 10800 103 AV SW | No | 4189.04 | 4189.04
1115302 | RSD DRNG DSGN 10800 VASHON HWY | No | 149.29 | 149.29
1115303 | RSD DRNG DSGN 52A S N/O #36622 | No | 6493.91 | 6493.91
1115304 | RSD DRNG DSGN SE472 E/O #26126 | No
1115305 | RSD DRNG FISH 16215 NE 124 ST | No
1115306 | RSD DRNG DSGN NE124 W/O 164AV | No
1115307 | RSD DRNG DSGN 7240 S 135 ST | No | 18933.92 | 18933.92
1115308 | RSD DRNG DSGN 13703 SW POHL RD | No | 17474.05 | 17474.05
1115309 | RSD DRNG DSGN VASHON HWY&SW112 | No | 6357.25 | 6357.25
1115310 | RSD DRNG VSHN B/T SW112&11018 | No | 6036.05 | 6036.05
1115311 | RSD DRNG DSGN VSHN HWY@ #11018 | No | 3466.25 | 3466.25
1115312 | RSD DRNG 45 AV B/T #28125&S282 | No | 12154.76 | 12154.76
1115314 | RSD DRNG BD-RVNSDL S/O 267A SE | No
1115316 | RSD DRNG LKRDG B/T OKWD&11005 | No | 150419.75 | 150419.75
1115317 | RSD DRNG S LAUREL B/T7589&7615 | No | 85694.89 | 85694.89
1115319 | RSD DRNG CNSTR S SUNNYCREST RD | No | 78758.13 | 78758.13
1115320 | RSD DRNG DIXON B/T OKWD&#10831 | No | 211072.54 | 211072.54
1115321 | RSD DRNG DIXON B/T OKWD&#10631 | No | 45237.19 | 45237.19
1115322 | RSD DRNG DIXON B/T 10891&10837 | No | 89838.24 | 89838.24
1115323 | RSD DRNG FOREST AV S&S RUSTIC | No | 32506.49 | 32506.49
1115324 | RSD DRNG FOREST N/O CRSTWD DR | No
1115325 | RSD DRNG FOREST B/T RUSTIC&SUN | No | 73643.47 | 73643.47
1115355 | RSD DRNG 16506 TIGER MTN RD SE | No | 45.12 | 45.12
1115369 | RSD DRNG TIGER MTN RD&SE 162 P | No
1115379 | RSD DRNG 13362 198 AVE NE | No | 13168.8 | 13168.8
1115380 | RSD DRNG TIGER MTN RD@SE 162 P | No | 101080.89 | 101080.89
1115381 | RSD DRNG 176 AVE NE&NE 195 ST | No | 512644.14 | 512644.14
1115382 | RSD DRNG NE UNION HL E/O 247AV | No | 6456.68 | 6456.68
1115383 | RSD DRNG 17407 155 AVE SE | No | 5521.26 | 5521.26
1115384 | RSD DRNG NE 100 E/O W SNOQ VLY | No | 213980.56 | 213980.56
1115385 | RSD DRNG 23020 148 AVE SE | No | 415.3 | 415.3
1115386 | RSD DRNG 268 AV SE S/O SE 411 | No
1115387 | RSD DRNG 23621 VASHON HWY S | No | 32.5 | 32.5
1115388 | RSD DRNG SE 187 PL&134 AV SE | No | 265.39 | 265.39
1115389 | RSD DRNG 344 AV NE N/O NE 20 | No
1115390 | RSD DRNG SW250WYB/T12002&12128 | No
1115391 | RSD DRNG S RUSTIC RD @ #6928 | No | 60 | 60
1115392 | RSD DRNG CORNELL AV&S SNNYCRST | No | 8088.97 | 8088.97
1115393 | RSD DRNG 17420 158 AVE SE | No
1115455 | RSD SOUTH PK BRIDGE DEMOLITION | No
1115473 | RSD STOSSEL BRDG#1023A STRNGNG | No | 1185.17 | 1185.17
1115521 | RSD C/W BRIDGE WASHING | No | 13802.92 | 13802.92
1115566 | RSD DUVALL SLOUGH BRDG #1136B | No | 274941.6 | 274941.6
1115607 | RSD W SNOQ VY NE NE124-W/D RD | No | 201605.33 | 201605.33
1115642 | RSD 2012 ADA PROGRAM ADMIN | No
1115643 | RSD 2012 ADA COUNTYWIDE PS&E | No | 71543.9 | 71543.9
1115644 | RSD 2012 ADA C/W IMPLMNTATION | No |  | 0
1115670 | RSD DRNG ORILLIA RD N/O 42AV S | No | 14218.93 | 14218.93
1115671 | RSD DRNG 10826 RAINIER AVE S | No | 20424.79 | 20424.79
1115786 | RSD DRNG 196AV SE/#41128-41232 | No | 4991.97 | 4991.97
1115789 | RSD DRNG 212 AVE SE N/O #37308 | No | 680.17 | 680.17
1115792 | RSD 2012 MAINT DIV 1 O/L PREP | No | 511595.06 | 511595.06
1115793 | RSD 2012 MAINT DIV 2 O/L PREP | No | 499325.55 | 499325.55
1115794 | RSD 2012 MAINT DIV 3 O/L PREP | No | 291217.29 | 291217.29
1115795 | RSD 2012 MAINT DIV 4 O/L PREP | No | 347700.9 | 347700.9
1115820 | RSD SE NWPRT WY/165P SE-SE42PL | No | -13.9 | -13.9
1115821 | RSD DOCKTON ROAD PRESERVATION | No
1115840 | RSD DRNG S LKRDG/RAINIER-DIXON | No | 292824.11 | 292824.11
1115841 | RSD DRNG 7728 S LAKERIDGE DR | No | 76050.31 | 76050.31
1115850 | RSD COUNTYWIDE HMA OVERLAY | No | 3106377.56 | 3106377.56
1116037 | RSD 1 PERCENT FOR ART | No
1116468 | RSD DRNG RPLC 16707 TIGER MTN | No | 52656.01 | 52656.01
1116494 | RSD DRNG SE 135 ST&184 AVE SE | No | 6884.29 | 6884.29
1116495 | RSD DRNG CULVRT CRESCENT DR SW | No | 8173.3 | 8173.3
1116496 | RSD DRNG W/O 20062 SE 232 ST | No | 3354.12 | 3354.12
1116540 | RSD CAREY CREEK @ 276 AVE SE | No
1116541 | RSD 181 AV SE&CVNGTN SAWYER RD | No | 862658.17 | 862658.17
1116542 | RSD SE COVINGTON SAWYER ROAD | No | 836493.12 | 836493.12
1116543 | RSD 78 AVE S/S 126-RENTON AV S | No | 24760.34 | 24760.34
1116544 | RSD 284 AVE SE BRIDGE #3049 | No
1116545 | RSD BERRYDALE OVERCRSNG#3086OX | No
1116546 | RSD SW CEMETERY RD/BEALL RD SW | No
1116547 | RSD RENTON AV S/68 AV-74 AV S | No | 942615.01 | 942615.01
1116623 | RSD RAGING RIVER BRIDGE #1008G | No | 2758.46 | 2758.46
1116637 | RSD PROP SALES COMPL PROJ CN | No | 162157.88 | 162157.88
1116638 | RSD WSDOT COMPL PROJ CN | No | 28070.55 | 28070.55
1116639 | RSD FINANCE ADM COMPL PROJ CN | No | 45004.17 | 45004.17
1116640 | RSD PROP SALES COMPL PROJ PRS | No | 12792.27 | 12792.27
1116641 | RSD WSDOT COMPL PROJ PRS | No | 1701.02 | 1701.02
1116642 | RSD FINANCE ADM COMPL PROJ PRS | No | 95186.14 | 95186.14
1116643 | RSD PROP SALES COMPL PROJ MTC | No | 7987.47 | 7987.47
1116651 | RSD WSDOT COMPL PROJ MTC | No | -19105.51 | -19105.51
1116652 | RSD FINANCE ADM COMPL PROJ MTC | No | -43.46 | -43.46
1116804 | RSD CONTRACTOR INT PYMTS ABT | No | 5849.24 | 5849.24
1116806 | RSD ESS CIP TRKNG TOOL DVLPMNT | No | 184937.55 | 184937.55
1116870 | RSD LANDSBURG BRDG S APPROACH | No | 151653.4 | 151653.4
1116886 | RSD TATE CREEK BRIDGE #122N | No
1116887 | RSD 14 AV SW/SW 110-SW 114 ST | No
1116888 | RSD SW ROXBURY/28 AV-30 AV SW | No | 517444.03 | 661000
1116894 | RSD DRNG MTCE RPR 204 PL NE | No
1116938 | RSD NE 124 ST ITS PHASE II | No
1116945 | RSD ISSQ-HBRT RD SE/15 ML BRDG | No
1116956 | RSD NE WOOD-DVL@AVONDALE RD NE | No
1117147 | RSD WESTSIDE HWY SHOULDER PREP | No | 17716.71 | 17716.71
1117165 | RSD DRNIMPRV-6 AV SW S/O SW102 | No
1117166 | RSD DRNIMPRV-18627 MAXWELL SE | No
1117245 | RSD DRNIMPRV-SE LK DOROTHY RD | No
1117246 | RSD DRNIMPRV-S342B/T44AV&4225 | No
1117247 | RSD DRNIMPRV-SE KERRISTON RD | No | 3870.96 | 3870.96
1117248 | RSD DRNIMPRV-SE MAY VLY&176 AV | No | 67582.29 | 67582.29
1117249 | RSD DRNIMPRV-15A SW&SW RXBY ES | No | 6462.98 | 6462.98
1117250 | RSD DRNIMPRV-15A SW&SW RXBY WS | No | 366.57 | 366.57
1117251 | RSD DRNIMPRV-17306 TIGER MT RD | No
1117252 | RSD DRNIMPRV-16 AV SW&SW106 ST | No | 4099.06 | 4099.06
1117253 | RSD DRNIMPRV-TIGER MTN RD SE | No
1117254 | RSD DRNIMPRV-204PL NE S/O 6019 | No | 10035.89 | 10035.89
1117830 | RSD SCOUR RPRS BRDGS 3066&3068 | No | 30915.6 | 30915.6
1117869 | RSD MRSDR1-SE 408 ST BRDG 3056 | No | 55623.51 | 55623.51
1117870 | RSD MRSDR1 RESERVED ONE MAINT | No
1118099 | RSD 2012 GO BONDS | No | 89547.05
1118131 | RSD OPER TO CIP EXPEND CORRECT | No | 1902629.16 | 1902629.16
1118226 | RSD LK ALICE RD OVERFLOW PIPE | No | 156827.97 | 156827.97
1118634 | RSD C/W OVERLAY ADMINISTRATION | No | 375759.16 | 375759.16
1118635 | RSD NE 124 ST OVERLAY | No | 502897.96 | 502897.96
1118636 | RSD S 288 STREET OVERLAY | No | 406355.52 | 406355.52
1118637 | RSD ISSAQUAH-HBRT RD OVERLAY | No | 422131.52 | 422131.52
1118638 | RSD SE MAY VALLEY ROAD OVERLAY | No | 1134597.62 | 1134597.62
1118664 | RSD SPPARO TO CIP EXPEND CORR | No
1118689 | RSD COAL CRK BRIDGE #3035A RPR | No | 78761.51 | 78761.51
1118796 | RSD EMER RPR 269WY/NE116-272NE | No | 85374.79 | 85374.79
1119111 | RSD CAP PROJ OS O/L & DRAINAGE | No | 45390.33 | 45390.33
1119296 | RSD 2013 DIV 1 DRAINAGE PRESRV | No | 288551.1 | 288551.1
1119297 | RSD 2013 DIV 2 DRAINAGE PRESRV | No | 314836.31 | 314836.31
1119298 | RSD 2013 DIV 3 DRAINAGE PRESRV | No | 1506147.94 | 1506147.94
1119299 | RSD 2013 DIV 4 DRAINAGE PRESRV | No | 641343.25 | 641343.25
1119414 | RSD C/W DRAINAGE PRES PRGM ADM | No | 496257.78 | 496257.78
1120153 | RSD 2013 COUNTYWIDE GUARDRAIL | No | 966078.86 | 966078.86
1120167 | RSD 2013 ADA PTRVSKY RETRO IMP | No
1120168 | RSD 2013 ADA PTRVSKY RTRO PS&E | No | 6977.74 | 6977.74
1120169 | RSD 2013 ADA S 288 RETRO IMP | No | 506340.99 | 506340.99
1120170 | RSD 2013 ADA S 288 RETRO PS&E | No | 100743.42 | 100743.42
1120319 | RSD O/L PREP ISSQ-HOBART RD SE | No | 120439.7 | 120439.7
1120320 | RSD O/L PREP SE MAY VALLEY RD | No | 345020.68 | 345020.68
1120321 | RSD OVERLAY PREP NE 124TH ST | No | 77939.77 | 77939.77
1120322 | RSD OVERLAY PREP S 288TH ST | No | 244801.63 | 244801.63
1120867 | RSD BARING BRG#509A TIMBER RPR | No | 34604.82 | 34604.82
1121109 | RSD SWIP VASHON HY SEAWALL RPR | No | 316803.84 | 316803.84
1121138 | RSD 2013 OVERLAY S 288 ST ADA | No
1121139 | RSD 2013 OVERLAY NE 124 ST ADA | No
1121140 | RSD 2013 OVERLAY ISSQ-HBRT ADA | No
1121141 | RSD 2013 O/L SE MAY VALLEY ADA | No
1121203 | RSD C/W HPG STRMWTR RTRFT PRGM | No | 96410.92 | 96410.92
1121224 | RSD RIVERBEND 444 AV SE&SE 151 | No | 18908.61 | 18908.61
1121428 | RSD CLOUGH CRK STREAM IMPRVMNT | No | 212751.75 | 212751.75
1121437 | RSD LK DOROTHY BRDG DECK REHAB | No | 5227.32 | 5227.32
1121601 | RSD NE 80 FARM DITCHES DRNG | No | 27378.78 | 27378.78
1121699 | RSD PRESTON-FC RD GRNDWTR C/O | No | 410053.56 | 410053.56
1121701 | RSD NE STOSSEL CRK DRNG IMPRV | No | 9526.85 | 9526.85
1121702 | RSD NE MONEY CRK RD DRNG IMPRV | No | 13998.35 | 13998.35
1121776 | RSD KERRISTON RD DRNG IMPRVMNT | No | 73216.68 | 73216.68
1121897 | RSD BRAC FOSS RVR BRDG #2605A | No | 126917.24 | 126917.24
1121898 | RSD BRAC LK DOROTHY BRDG #359B | No | 245390.25 | 245390.25
1121899 | RSD BRAC BRISSACK BRDG #1116A | No | 230664.67 | 230664.67
1121900 | RSD BRAC MONEY CRK BRDG #506A | No | 215984.16 | 215984.16
1121901 | RSD BRAC STOSSEL BRIDGE #1023A | No | 980203.48 | 980203.48
1122199 | RSD PATTERSON CK BRDG 180L ART | No | 24648.16 | 24648.16
1122200 | RSD NEWAUKUM CK BRDG 3040A ART | No | 19552.42 | 19552.42
1122309 | RSD 2014 COUNTYWIDE GUARDRAIL | No | 328950.55 | 328950.55
1122327 | RSD N FORK BRG #1221 SCOUR RPR | No | 56663.01 | 56663.01
1122354 | RSD KERRISTON RD CULVERT IMPV | No | 615778.57 | 615778.57
1122355 | RSD CEDAR GROVE WTR QLTY IMPRV | No | 248733.5 | 248733.5
1122356 | RSD AVONDALE RD WTR QLTY IMPVR | No | 3931.74 | 3931.74
1122727 | RSD 2014 DRAINAGE PRES PRG ADM | No | 446799.7 | 446799.7
1122728 | RSD 2014 DIV 1 DRNG PRES PRGM | No | 456283.24 | 456283.24
1122729 | RSD 2014 DIV 2 DRNG PRES PRGM | No | 624877.59 | 624877.59
1122730 | RSD 2014 DIV 3 DRNG PRES PRGM | No | 651417.46 | 651417.46
1122731 | RSD 2014 DIV 4 DRNG PRES PRGM | No | 902276.35 | 902276.35
1122907 | RSD SE JONES RD DRNG IMPRVMNTS | No | 807.02 | 807.02
1122908 | RSD NUDIST CAMP CRK STRM IMPV | No | 47620.21 | 47620.21
1122909 | RSD PEASLEY CNYN DRNG IMPRVMNT | No | 6812.33 | 6812.33
1122910 | RSD NORTH FORK RD DRNG IMPRVMT | No | 23623.61 | 23623.61
1122911 | RSD MIDDLE FORK DRNG IMPRVMENT | No
1122912 | RSD WILDERNESS RIM DRNG IMPVMT | No | 60323.74 | 60323.74
1122928 | RSD ELK RUN BUYOUT | No
1123047 | RSD 2014 ADA PROGRAM PS&E | No | 433150.38 | 433150.38
1123183 | RSD DOCKTON ROAD DRNG IMPRVMNT | No | 479738.49 | 479738.49
1123184 | RSD BLK DMD-RAVENSDALE RD DRNG | No | 63879.91 | 63879.91
1123319 | RSD 2014 C/W HT MIX ASPHLT O/L | No | 3979918.41 | 3979918.41
1123351 | RSD SE DAVID POWELL RD DRG IMP | No
1123362 | RSD WASHOUT RPR MAXWELL RD | No
1123718 | RSD SE MAY VALLEY RD EMERG RPR | No | 1149058.34 | 1149058.34
1123719 | RSD W SNOQ VLLY EMER SLIDE RPR | No | 935079.29 | 935079.29
1123787 | RSD CIP CONST BR 3 TEMPLATE | No
1123800 | RSD CIP PRES BR 3 TEMPLATE | No
1123801 | RSD CIP MAINT BR 3 TEMPLATE | No
1123869 | RSD GREEN RVR RD EMERG SLD RPR | No | 543945.96 | 543945.96
1123870 | RSD ISSQ CRK BRIDGE #1741A RPR | No | 45351.86 | 45351.86
1123871 | RSD CHERRY VLY TRSL BR267X O/L | No | 73220.95 | 73220.95
1123872 | RSD DUVALL BRDG #1136 A&B RPR | No | 49660.8 | 49660.8
1123878 | RSD 2014 O/L PREP SE 240 ST | No | 55629.13 | 55629.13
1123879 | RSD 2014 O/L PREP 276 AVE SE | No | 149771.72 | 149771.72
1123880 | RSD 2014 O/L PREP SE 416 ST | No | 58702.78 | 58702.78
1123881 | RSD 2014 O/L PRP PRESTON-FC RD | No | 38695.37 | 38695.37
1123882 | RSD 2014 O/L PRP SE204/LK YNGS | No | 82326.85 | 82326.85
1123883 | RSD 2014 OL PRP A-BD GRN RV BR | No | 139491.57 | 139491.57
1123884 | RSD 2014 OL PRP AUB-BD LK HOLM | No | 178398.06 | 178398.06
1123885 | RSD 2014 O/L PREP SE244/152AVE | No | 63896.06 | 63896.06
1123905 | RSD 2014 O/L PRP W SNOQ VLY RD | No | 210750.74 | 210750.74
1124001 | RSD CLEAR ZONE SAFETY | No
1124061 | RSD 148 AV SE RD RECONSTRCTION | No
1124072 | RSD SUMMIT PIT RELOCATION CIP | No | 453110.9 | 453110.9
1124103 | RSD GREEN RIVER RD SLD RPR IPR | No | 221448.03 | 221448.03
1124135 | RSD SE 456 WY WASHOUT W/O 212 | No | 468527.85 | 468527.85
1124419 | RSD ELK RUN BUY OUT | No
1124491 | RSD 2015/16 RDWY LGT LED CONV | No | 438406.5 | 438406.5
1124602 | RSD 2014 BEAVER DECEIVER | No | 45089.37 | 45089.37
1124637 | RSD KELLY RD BRG 5007 RAIL RPR | No | 56767.06 | 56767.06
1124657 | RSD NE 127 ST CULVERT RPLCMNT | No | 323698.69 | 323698.69
1124658 | RSD NE UNION HILLRD CULVT RPLT | No
1124800 | RSD MAXWELL RD WASHOUT REPAIR | No | 212701.08 | 212701.08
1124801 | RSD SLIDE RPR34519 D POWELL RD | No | 121082.4 | 121082.4
1124820 | RSD B BLDG ROOF RPLC&IMPRVMNTS | No
1124823 | RSD KANASKET ARCH BR#3036 RPRS | No | 77774.57 | 77774.57
1124836 | RSD RENTON AV S/75 AV-S 126 ST | No | 28000.49 | 28000.49
1124847 | RSD SOUTH PARK BRIDGE 1% ART | No | 232460 | 232460
1124935 | RSD GRDRL SE MAY VLLY&ISSQ-HBT | No | 193975.13 | 193975.13
1124962 | RSD SKY RV BR #999Z(MNY CK)RPR | No | 1577622.73 | 1577623 | 1473900.34
1124964 | RSD OLD CASCDE/MILLER RVR WEST | No
1124965 | RSD OLD CASCDE/MILLER RVR EAST | No
1124966 | RSD MILLER RVR BANK PROTECTION | No
1124967 | RSD MILLER RIVER BRDGE REMOVAL | No
1124968 | RSD KC 2014 SFTY HF SURF TRMTS | No | 1634654.32 | 1634654.32 | 2480033.6
1124969 | RSD GUARDRAIL INSTL/HAZRD RMVL | No | 741447.99 | 741447.99
1125069 | RSD KELLY BR 5007 RAIL UPGRD | No | 62272.67 | 62272.67
1125296 | RSD S 96 ST&8 AVE S SINKHOLE | No | 1076335.96 | 1076335.96 | 1038930.74
1125330 | RSD CIP CONST BR 1&2 TEMPLATE | No
1125331 | RSD CIP PRES BR 1&2 TEMPLATE | No
1125333 | RSD 2015/16 DRNG PRES PGM ADM | No | 443698.69 | 443698.69
1125336 | RSD 2015/16 DIV1 DRNG PRES PGM | No | 837389.96 | 837389.96
1125337 | RSD 2015/16 DIV2 DRNG PRES PGM | No | 446853.77 | 446853.77
1125338 | RSD 2015/16 DIV3 DRNG PRES PGM | No | 2905267.31 | 2905267.31
1125339 | RSD 2015/16 DIV4 DRNG PRES PGM | No | 2523551.7 | 2523551.7
1125340 | RSD 2015/16 DIV5 DRNG PRES PGM | No | 875733.55 | 875733.55
1125341 | RSD 2015/16 DIV6 DRNG PRES PGM | No | 1281.89 | 1281.89
1125549 | RSD MAINTENANCE PIT RELOCATION | No | 168128.79 | 168128.79
1125550 | RSD MAP CENTER RELOCATION | No | 75120.63 | 75120.63
1125757 | RSD 2015/16 DIV 4 SHLDR RECON | No | 401103.86 | 401103.86
1125758 | RSD W SNOQ VLY RD/NE124-W/D RD | No | 599463.84 | 961421
1125784 | RSD RENTON FACILITY IMPRVMENTS | No | 713929.17 | 713929.17
1125785 | RSD DIV2/DIV6 FACILITY IMPRVNT | No | 35040.29 | 35040.29
1125786 | RSD DIV 4 FACILITY IMPROVMENTS | No | 473286.97 | 473286.97
1125789 | RSD 2015/16 DIV 1 SHLDR RECON | No | 411067.68 | 411067.68
1125790 | RSD 2015/16 DIV 2 SHLDR RECON | No | 566026.19 | 566026.19
1125791 | RSD 2015/16 DIV 3 SHLDR RECON | No | 487665.7 | 487665.7
1125792 | RSD 2015/16 DIV 5 SHLDR RECON | No | 143914.2 | 143914.2
1125793 | RSD 2015/16 DIV 6 SHLDR RECON | No | 55782.22 | 55782.22
1125862 | RSD HIGH RISK PAVEMENT TRTMNT | No | 51967.06 | 51967.06
1125863 | RSD A BLDG ROOF REPLACEMENT | No | 247745.83 | 247745.83
1126042 | RSD BVR DCVR 36900 MLTRY RD S | No | 22658.21 | 22658.21
1126043 | RSD BEAVER DECEIVER 437 AVE SE | No | 13542.71 | 13542.71
1126178 | RSD BVR DCVR 180XX 185 AVE NE | No | 22276.28 | 22276.28
1126227 | RSD HGH RSK PVMT 68A S - SR900 | No | 102976.75 | 102976.75
1126268 | RSD HGH RISK PVMT S132-S133 ST | No | 187641.31 | 187641.31
1126280 | RSD HGH RISK PVMT RENTON AVE S | No | 253013.16 | 253013.16
1126281 | RSD HGH RISK PVMT NE NVLTY HLL | No | 141509.99 | 141509.99
1126282 | RSD HGH RISK PVMT 238 AVE NE | No | 158146.01 | 158146.01
1126283 | RSD HGH RISK PVMT 236 AVE NE | No | 123135.55 | 123135.55
1126284 | RSD HGH RISK PVMT SAHALEE WAY | No
1126285 | RSD HGH RISK PVMT 244 AVE NE | No
1126286 | RSD HGH RSK PVT 148AV/140PL NE | No
1126287 | RSD HGH RISK PVMT SE 232 ST | No
1126288 | RSD HGH RISK PVMT 140 AVE SE | No | 138065.41 | 138065.41
1126373 | RSD COUNTYWIDE BRIDGE WASHING | No | 64582.63 | 64582.63
1126430 | RSD DUVALL BRIDGE APPROACH | No | 192969.58 | 192969.58
1126434 | RSD SKYKOMISH FACILITY LIGHTNG | No | 13905.04 | 13905.04
1126435 | RSD XPIPE 185 AV N/O NE179ST | No | 4655.01 | 4655.01
1126436 | RSD NE UNION HILL RD&225 AV NE | No | 353213.96 | 353213.96
1126437 | RSD XPIPE 16215 NE 124 ST | No | 133169.98 | 133169.98
1126438 | RSD XPIPE NE 124 ST&164 AVE NE | No | 1033368.68 | 1248190.04 | 1498141.36
1126439 | RSD XPIPE GREEN RVR RD&94 PL S | No | 4392.22 | 4392.22
1126440 | RSD W VALLEY HIGHWAY CULVERTS | No | 5025.85 | 5025.85
1126441 | RSD S 96 ST STORMWATER PIPES | No | 1895282.2 | 2342895.35 | 2082942.83
1126442 | RSD 284 AV SE&VZ/CMBRLND RD | No | 5193.16 | 5193.16
1126443 | RSD CROSSPIPE 229 DRIVE SE | No | 364375.63 | 364375.63
1126889 | RSD BARING BRDG#509A TWR SPPT | No | 62770.75 | 62770.75
1127129 | RSD 2016 O/L S 320 PEASLEY CYN | No | 1593986.21 | 1593986.21
1127268 | RSD EMERGENT NEED FUND 3850 | No |  | 674097.36
1127269 | RSD GRANT CONTINGNCY FUND 3850 | No
1127270 | RSD CW SNOW&ICE MTRLS STORAGE | No | 2825826.13 | 2825826.12
1127272 | RSD FACILITY SITE DVLPMNT&PLNG | No
1127276 | RSD CW ROADWAY SAFETY IMPRVMTS | No
1127277 | RSD BARING BRIDGE #509A | No
1127278 | RSD BRRYDALE OXING BRDG#3086OX | No
1127328 | RSD FACILITIES CIP BR 3 | No
1127591 | RSD 185 AV NE FLD RSK RDUCTN | No | 106632.03 | 106632.03
1127595 | RSD 2015 GO BONDS | No | 2365.56
1127612 | RSD UPPR PRESTON BDG#1239A RPR | No | 59107.66 | 59107.66
1127613 | RSD WYNACO BDG#3194 SCOUR RPR | No | 159588.7 | 159588.7
1127616 | RSD BRRYDL OXING#3086 2015 RPR | No | 45140.13 | 45140.13
1127617 | RSD SE PETROVITSKY RD GDRL ADJ | No | 107071.67 | 107071.67
1127699 | RSD SLD RPR UPP PRSTN SE/SE 97 | No | 72497.23 | 72497.23
1127801 | RSD 2016 BITUMINOUS SURF TRTMT | No | 2265078.33 | 2265078.33 | 2400000.2
1127802 | RSD 2016 HOT MIX ASPHALT O/L | No | 3506087.82 | 3506087.82 | 3533999.98
1127885 | RSD SNOW&ICE MTRL STRG DESIGN | No
1128143 | RSD 2015/16 CW RS OBSTCLE RMVL | No | 44772.66 | 44772.66
1128945 | RSD RD RPR UPP PRSTN SE/SE 97 | No | 730326.21 | 730326.21
1128968 | RSD SE RETREAT KNSKT GDRL ADJ | No | 84696.29 | 84696.29
1128969 | RSD NE WD/DVL RD GDRL ADJ | No | 13266.57 | 13266.57
1128970 | RSD PRSTN-FC RD GDRL ADJ | No | 61617.17 | 61617.17
1128971 | RSD NE 133 ST GDRL ADJ | No | 8849.47 | 8849.47
1129074 | RSD SE 400 WAY GUARDRAIL ADJ | No | 16620.38 | 16620.38
1129075 | RSD SE 416 ST GUARDRAIL ADJ | No | 3789.36 | 3789.36
1129290 | RSD DOCKTON RD SW EROSN PROT | No | 207434.97 | 207434.97
1129525 | RSD DIV 1 FACILITY IMPROVMENTS | No
1129579 | RSD CIP POT MASTER TEMPLATE | No
1129589 | RSD CWP CLEAR ZONE SAFETY | No
1129597 | RSD ISS HBRT RD@CDR GROV IMPRV | No
1129600 | RSD HIGHLINE SCH DIST IMPRVMNT | No |  | 5250000
1129625 | RSD BRRYDL OXNG 3086OX2016 RPR | No | 51962.24 | 51962.24
1129712 | RSD PAVEMENT | No
1129713 | RSD HIGH RISK PAVING | No
1129715 | RSD WHITE CENTER OVERLAY | No
1129723 | RSD DIVISION 1 SHOULDERING | No | 398868.92 | 400693.12
1129724 | RSD DIVISION 2 SHOULDERING | No | 461054.83 | 492559.76
1129725 | RSD DIVISION 3 SHOULDERING | No | 449860.03 | 451864.77
1129726 | RSD DIVISION 4 SHOULDERING | No | 369098.61 | 373799.94
1129727 | RSD DIVISION 5 SHOULDERING | No | 228668.71 | 230406.81
1129728 | RSD DIVISION 6 SHOULDERING | No | 37968.52 | 47968.52
1129729 | RSD HIGH COLLISION LOCATIONS | No
1129730 | RSD HIGH COLLISION ROAD SGMNTS | No
1129859 | RSD NEELY BR 3014 DECK REPRS | No | 73466.57 | 73466.57
1129877 | RSD HGH FRICTION SRF TREATMENT | No | 959779.16 | 959779.16 | 1165499.62
1130013 | RSD HRP RENTON AV S/S126 TO CL | No | 279277.06 | 279277.06
1130014 | RSD HRP RENTON AV/74AV S-S 126 | No | 232700.28 | 232700.28
1130015 | RSD HRP NE UNION HILL ROAD | No | 128074.69 | 128074.69
1130016 | RSD HRP 212 AVE NE | No | 142311.93 | 142311.93
1130163 | RSD SW LUANA BEACH SLIDE RPR | No | 93839.31 | 93839.31
1130188 | RSD OLD CASCDE/MILLER BR W | No | 7508.35 | 7508.35
1130189 | RSD OLD CASCDE/MILLER BR E | No | 8757.33 | 8757.33
1130410 | RSD WESTSIDE HWY PERM RD RPR | No | 834393.21 | 866265
1130412 | RSD 148A NE/TOLT PPLN SIGNAL | No | 92682.2 | 92682.2
1130440 | RSD TATE CREEK BRIDGE 122N | No | 231272.97 | 231272.97
1130448 | RSD CADMAN SAND/SALT STORAGE | No | 7258.81 | 7258.81
1130449 | RSD DIAMOND SAND/SALT STORAGE | No | 390080.08 | 390080.08
1130450 | RSD KRAIN SAND/SALT STORAGE | No | 357109.22 | 357109.22
1130451 | RSD MILETA SAND/SALT STORAGE | No | 372888.47 | 372888.46
1130452 | RSD NORTH BD SAND/SALT STORAGE | No | 410867.39 | 410867.39
1130453 | RSD RENTON SAND/SALT STORAGE | No | 403310.99 | 403310.99
1130454 | RSD SKYKOMISH SAND/SALT STORGE | No | 515749.1 | 515749.1
1130455 | RSD STILLWTR SAND/SALT STORAGE | No | 362059.58 | 362059.58
1130456 | RSD VASHON SAND/SALT STORAGE | No | 6502.49 | 6502.49
1130682 | RSD DRG DSGN 46000 SAHALEE WAY | No
1130683 | RSD DRG DSGN PETROVITSKY ROAD | No
1130705 | RSD FC SNQ VLY MJR FL MIT STDY | No
1130706 | RSD FC NE8ST@ALLEN LAKE OUTLET | No | 19365.28 | 400000
1130709 | RSD FC SE 384 ST @ 176 A SE | No
1130711 | RSD FC WD/DVL BRG 1136B/E SCR | No | 277937.1 | 400000
1130712 | RSD FC DUVALL BRG 1136A SCR | No | 142411.36 | 150000
1130713 | RSD FC RAGING RVR 1008E SCR | No | 25061.69 | 25061.69
1130714 | RSD FC PATTON BRG 3015 | No | 47523.56 | 47523.56
1130883 | RSD CW DRAINAGE PRES TEMP MTCE | No
1130960 | RSD SW CEDARHURST SLIDE RPR | No | 315719.41 | 315719.41
1130961 | RSD GRN VLLY RD SLIDE RPR | No | 511549.94 | 511549.94
1131002 | RSD NEWAUKUM CR BR 3071 REHAB | No
1131003 | RSD CHERRY CK BR 4271 REPAIR | No | 46150.05 | 46150.05
1131142 | RSD DIV 1 DRAINAGE | No
1131143 | RSD DIV 2 DRAINAGE | No
1131144 | RSD DIV 3 DRAINAGE | No
1131145 | RSD DIV 4 DRAINAGE | No
1131146 | RSD DIV 5 DRAINAGE | No
1131147 | RSD DIV 6 DRAINAGE | No
1131150 | RSD HGH COLLISION SIGN & STRIP | No | 14071.06 | 14071.06
1131152 | RSD HGH COLLISION MARKING REV | No | 193659.93 | 193659.93
1131275 | RSD STOSSEL BR 1023A DECK O/L | No | 88093.85 | 88093.85
1131328 | RSD SW RORSUCH RD IMPRVMNT | No
1131329 | RSD SW GORSUCH RD IMPRVMNT | No | 37226.38 | 235209.06
1131420 | RSD NE 124 ST SLIDE REPAIR | No | 100610.36 | 100610.36
1131505 | RSD CW FACLTY IMPRVMT 17-18 | No | 176117.79 | 176117.79
1131507 | RSD DIV 3 FACLTY IMPRVMT 17-18 | No | 145806.67 | 145806.67
1131527 | RSD 221 A NE @ NE 54 ST | No | 11413.69 | 11413.69
1131635 | RSD 196 AVE SE GDRL ADJ | No | 105189.52 | 105189.52
1131749 | RSD NEWAUKUM CK BR 3071 REHAB | No | 26369.92 | 26369.92
1131812 | RSD OVERFLW BR 3217 JOINT REP | No | 48412.26 | 48412.26
1131849 | RSD BARING BRDG EMGY RPR 2017 | No | 1143999.21 | 1143999.21 | 1414999.78
1131897 | RSD ROAD CONSTRUCTION | No |  | 434908
1131898 | RSD MAJOR MAINTENANCE | No
1132085 | RSD HRP SE KENT-KANGLEY RD | No | 529094.42 | 529094.42
1132088 | RSD HRP 64 A S/S 124 ST/68 A S | No
1132089 | RSD HRP SE 368 WY/SE 368 ST | No | 228134.28 | 228134.28
1132160 | RSD HIGH COLL MARKING REV 2 | No | 18733.26 | 18733.26
1132177 | RSD 17-18 CLEAR ZONE SAFETY | No
1132218 | RSD TOLT BRG 1834A EMGY RPR-17 | No | 3764770.83 | 3764770.83 | 4499999.72
1132364 | RSD N FORK ROAD SE RDWY RPR | No | 163283.75 | 163283.76
1132396 | RSD NVLTY BR404B JNT REHAB | No | 59659.04 | 59659.04
1132398 | RSD NE WD/DV RDWY EMG REHAB | No | 157701.18 | 157701.18
1132418 | RSD 8 BRIDGES RAIL RPLCMNT | No | 79361.96 | 79361.96
1132419 | RSD DEEP CR BRG TMBR RPLCMNT | No | 35928.47 | 35928.47
1132542 | RSD HRP MINK RD NE | No | 228920.23 | 228920.23
1132582 | RSD 196TH AVE SE HFST REPAIR | No | 78714.11 | 78714.11
1132715 | RSD COAL CREEK #3035A DECK | No | 44475.87 | 44475.87
1132949 | RSD ISS HOB RD ENH SIGNAL | No | 193315.02 | 193315.02
1132960 | RSD BRDG WASH 404B-615A-3024 | No | 158517.94 | 158517.94
1133169 | RSD CIP GEN CONST BR1&2 TMPLT | No
1133170 | RSD CIP GEN CONST BR3 TEMPLTE | No
1133171 | RSD CIP GEN PRES BR 1&2 TMPLT | No
1133172 | RSD CIP GEN PRES BR 3 TEMPLATE | No
1133173 | RSD CIP GEN MAINT BR 1&2 TMPLT | No
1133174 | RSD CIP GEN MAINT BR 3 TEMPLTE | No
1133447 | RSD CWP 2018 BRIDGE SAFETY | No
1133668 | RSD FIFTEEN ML CR BRG 493C RPR | No | 56607.78 | 56607.78
1133669 | RSD FLAM GEYSER BRG 3024 RPR | No | 15947.26 | 15947.26
1133670 | RSD PATTON BRG 3015 RPR | No | 26656.16 | 26656.16
1133671 | RSD KANASKET BRG 3037OX RPR | No | 55724.88 | 55724.88
1133672 | RSD CEDAR GROVE BRG 3164 RPR | No | 78900.15 | 78900.15
1133673 | RSD BRISSACK BRG 1116A RPR | No | 22747.55 | 22747.55
1133674 | RSD DUVALL BRG 1136A RPR | No | 26269.24 | 26269.24
1133675 | RSD YORK BRG 225C RPR | No | 20293.16 | 20293.16
1133755 | RSD UPPER PRESTON RD GDRL ADJ | No | 22869.26 | 22869.26
1133868 | RSD 144TH 142ND PAVE PRES | No | 492046.33 | 492046.33
1133870 | RSD SE 232ND ST GDRL ADJ | No | 17914.09 | 17914.09
1133871 | RSD SE 224TH ST GDRL ADJ | No | 23194.46 | 23194.46
1133876 | RSD HRP VASHON HWY SW OLD | No
1134004 | RSD HRP SE 384 AND SE 383 OLD | No
1134005 | RSD HRP MOUNTN VIEW RD NE OLD | No
1134006 | RSD HRP BECN COAL MINE RD OLD | No
1134048 | RSD BRAC WD DUV BRG 1136E RPR | No | 209578.56 | 209578.56
1134049 | RSD BRAC LANDSBRG BRG 3075 RPR | No | 583657.25 | 583643.51
1134093 | RSD CWP TRAFFIC SAFETY | No | 3487115.2441 | 2608900
1134094 | RSD CWP OBSOLETE IT SYS RPLMNT | No | 985883.8659 | 900000
1134845 | RSD GRNWTR BRG 3050A LD UPGRD | No | 47735.78 | 47735.78
1134849 | RSD HRP VASHON HWY SW | No | 97327.65 | 97327.65
1134850 | RSD HRP SE 384TH AND SE 383RD | No | 340042.99 | 340042.99
1134851 | RSD HRP MOUNTAIN VIEW RD NE | No | 564279.91 | 564279.91
1134852 | RSD HRP BEACON COAL MINE RD S | No
1134956 | RSD CURB RAMP REPLACEMENT | No | 150991.37 | 150991.37
1134986 | RSD FC GRN RVR RD SLIDE REPAIR | No | 167737.73 | 250000
1134994 | RSD FC 428TH AV CULVERT RPLCMT | No | 722079.56 | 724000
1135044 | RSD PRSTN MAINT FACILTY BLDOUT | No | 11262134.3426
1135280 | RSD BARING BRG 509A RPR | No | 31358.99 | 31358.99
1135876 | RSD BEAL RD SW | No
1135878 | RSD CHERRY VALLEY ROAD | No
1135880 | RSD REINIG ROAD | No
1136087 | RSD FOSS RIVER BRG 2605A PAINT | No | 468199.02 | 468199.02
1136209 | RSD 2019 BRIDGE WASHING | No | 108561.32 | 108561.32
1136212 | RSD SUNDAY CR BRG 364C RPR | No | 11537.69 | 11537.69
1136240 | RSD 22233 NE 170TH PL CULVERT | No | 268495.38 | 268495.38
1136578 | RSD S 42ND ST SCHOOL PTHWY | No
1136934 | RSD HRP BCON COAL MINE RD S | No | 212037.92 | 212037.92
1136935 | RSD HRP 236A SE SE 384 ST | No | 326359.81 | 326359.81
1137078 | RSD HRP SE GREEN VALLEY RD | No | 315925.34 | 315925.34
1137079 | RSD OVERFLW BR 3217 OVLY | No | 95943.15 | 95943.15
1137161 | RSD STOSSEL BR 1023A GUSSETS | No | 53977.68 | 53977.68
1137385 | RSD PRESTON FRNT BRG 5046 OVLY | No | 76853.39 | 76853.39
1137510 | RSD HRP SE EDGEWICK ROAD | No | 141309.41 | 141309.41
1137572 | RSD REDMOND RIDGE DR NE XNG | No | 11316.64 | 20000
1137858 | RSD 2019 LK DRTHY LJM BR359B | No | 19726.07 | 19726.07
1138803 | RSD STORM MIDDLE FORK RD RPR | No | 96980.99 | 120000
1138947 | RSD 284TH AVE S 46913 CULVERT | No
1139148 | RSD ORILLIA ROAD S OVERLAY | No
1139242 | RSD NE NOVELTY HILL WINTR 2020 | No | 307463.52 | 500000
1139252 | RSD HRP 194TH AVENUE SE | No | 336454.41 | 350000
1139253 | RSD HRP RIVERBEND COMMUNITY | No | 649600.53 | 650000

## Standalone CIP Data (hidden)
Master | Project | Project Name | PM | Life to Date Budget | Life to Date Expenditures | Current Year Adjusted Budget | Year to Date Expenditures | YTD Commitment | LTD Balance | YTD Balance | CurrentEstimate | Baseline Estimate
1026798 | 1026798 | RSD EMERGENT NEED-EXISTING PROJECTS |  | 216227.26 | 0 | 216227.26 | 0 | 0 | 216227.26 | 216227.26 | 0 | 0
1026799 | 1026799 | RSD CIP GRANT CONTIGENCY |  | 568294 | 0 | 568294 | 0 | 0 | 568294 | 568294 | 0 | 0
1026800 | 1026800 | RSD CAP PROJ O S FUND 3860 |  | 179399.42 | 179399.42 | -1.0623e-11 | 0 | 0 | -1.4552e-11 | -1.0623e-11 | 0 | 0
1114791 | 1114791 | RSD ROADS-RENTON FACILITY | Mitchell | 1119300.06 | 1120367.41 | -1067.35 | 0 | 0 | -1067.35 | -1067.35 | 0 | 0
1114792 | 1114792 | RSD ROADS-COUNTY ROAD CONST | n/a | 10596272.33 | 10596271.61 | 4091634.72 | 4091634 | 0 | 0.72 | 0.72 | 0 | 0
1116885 | 1116885 | RSD WOODINVILLE DUVAL ITS (100415) | McManus | 1438000.06 | 1091709.71 | 346290.35 | 0 | 0 | 346290.35 | 346290.35 | 1347684 | 1438000
1116888 | 1116888 | RSD SW ROXBURY/28 AV-30 AV SW | Mott | 661000 | 517444.03 | 143555.97 | 0 | 0 | 143555.97 | 143555.97 | 629319 | 0
1124962 | 1124962 | RSD SKY RV BR #999Z(MNY CK)RPR | Jose | 1643900 | 1577622.73 | 67352.48 | 1075.21 | 0 | 66277.27 | 66277.27 | 1363106.25 | 1473900
1125758 | 1125758 | RSD W SNOQ VY RD /NE124-W/D RD | Posey | 961421 | 203568.61 | 828159.03 | 70306.64 | 0 | 757852.39 | 757852.39 | 961000 | 0
1127268 | 1127268 | RSD EMERGENT NEED FUND 3850 |  | 674097.36 | 0 | 674097.36 | 0 | 0 | 674097.36 | 674097.36 | 0 | 0
1127270 | 1127270 | RSD CW SNOW&ICE MTRLS STORAGE | Cassidy | 74173.88 | 0 | 74173.88 | 0 | 0 | 74173.88 | 74173.88 | 0 | 0
1127270 | 1130455 | RSD STILLWTR SAND/SALT STORAGE | Harris | 362059.58 | 362059.58 | 9.0949e-12 | 0 | 0 | 0 | 9.0949e-12 | 264000 | 0
1127271 | 1127271 | RSD PRESTON MAINT FACILITY | Hicker | 4500000.06 | 1804531.1 | 2754618.73 | 59149.77 | 0 | 2695468.96 | 2695468.96 | 4490000 | 0
1127273 | 1127273 | RSD FAILED ENV & HVAC REHAB | Ho | 7150000 | 1279042.96 | 6030351.58 | 159394.54 | 0 | 5870957.04 | 5870957.04 | 6216230 | 6216230
1129582 | 1129582 | RSD EMERGENT NEED 3855 | Mitchell | 1230000 | 0 | 1230000 | 0 | 0 | 1230000 | 1230000 | 0 | 0
1129583 | 1129583 | RSD GRANT CONTINGENCY 3855 | Mitchell | 7039969 | 0 | 7039969 | 0 | 0 | 7039969 | 7039969 | 0 | 0
1129584 | 1129584 | RSD CWP QUICK RESPONSE | Mitchell | 3096478.68 | 0 | 3096478.68 | 0 | 0 | 3096478.68 | 3096478.68 | 0 | 0
1129584 | 1132218 | RSD TOLT BRG 1834A EMGY RPR | Jiang | 3779770.83 | 3764770.83 | 269332.67 | 254332.67 | 0 | 15000 | 15000 | 3771500 | 4500000
1129584 | 1132949 | RSD ISS HOB RD ENH SIGNAL | Zhen | 203316 | 193315.02 | 27948.11 | 17947.13 | 0 | 10000.98 | 10000.98 | 150000 | 0
1129584 | 1133864 | RSD NE NVLTY HILL RD SIDEWALK | Sahagun | 347559.23 | 347559.23 | -9.0949e-13 | 0 | 0 | 0 | -9.0949e-13 | 575000 | 0
1129584 | 1134845 | RSD GRNWTR BRG 3050A LD UPGRD | Roark | 47771.12 | 47771.12 | -1.819e-12 | 0 | 0 | 0 | -1.819e-12 | 40000 | 0
1129584 | 1136087 | RSD FOSS RIVER BRG 2605A PAINT | Martin | 640000 | 468199.02 | 640000 | 468199.02 | 0 | 171800.98 | 171800.98 | 640000 | 390000
1129584 | 1136631 | RSD JUDD CK BRD 3184 RPR | O'Day | 100000 | 0 | 100000 | 0 | 0 | 100000 | 100000 | 40000 | 0
1129584 | 1136633 | RSD PATTON DRD 3015 BKT RPR | Jiang | 60000 | 27049.57 | 60000 | 27049.57 | 0 | 32950.43 | 32950.43 | 40000 | 0
1129584 | 1136972 | RSD SW 108&8 AV SW RNDBT REVSN | McManus | 78000 | 66007.28 | 78000 | 66007.28 | 0 | 11992.72 | 11992.72 | 30000 | 0
1129584 | 1137364 | RSD WSD HWY SW DEGRADTN | Posey | 60000 | 32781.29 | 60000 | 32781.29 | 32781.3 | -5562.59 | -5562.59 | 20000 | 0
1129584 | 1137509 | RSD DOCKTON SEAWALL RPR | Roark | 630000 | 209054.9 | 630000 | 209054.9 | 0 | 420945.1 | 420945.1 | 630000 | 0
1129584 | 1137572 | RSD REDMOND RIDGE DR NE XNG | Hafele | 20000 | 0 | 20000 | 0 | 0 | 20000 | 20000 | 20000 | 0
1129584 | 1137577 | RSD 304 ST HAUL RD MITGN | Moore | 155000 | 0 | 155000 | 0 | 0 | 155000 | 155000 | 155000 | 0
1129584 | 1137584 | RSD MIDDLE FORK RD RPR | Cassidy | 76000 | 41832.96 | 76000 | 41832.96 | 0 | 34167.04 | 34167.04 | 76000 | 0
1129584 | 1137860 | RSD 2019 DVD PWLL RD RPR 33621 | Lyou | 100000 | 6511.62 | 100000 | 6511.62 | 0 | 93488.38 | 93488.38 | 100000 | 0
1129585 | 1129585 | RSD CWP ROADWAY PRESERVATION | Moore | 661068.13 | 0 | 661068.13 | 0 | 0 | 661068.13 | 661068.13 | 0 | 0
1129585 | 1129714 | RSD NE STILLWATER HILL RD | Linders | 845190 | 235176.7 | 845190 | 235176.7 | 0 | 610013.3 | 610013.3 | 4675000 | 5050000
1129585 | 1133219 | RSD VASHON HWY SW PAVE PRES | Moore | 4880000 | 4728758 | 156049.08 | 4807.08 | 0 | 151242 | 151242 | 4880000 | 5700000
1129585 | 1133220 | RSD 2018 CNTYWDE PAVE PRES | Moore | 4763000 | 4447489.29 | 4248262.8 | 3932752.09 | 0 | 315510.71 | 315510.71 | 4450000 | 4300000
1129585 | 1133757 | RSD 2018 BITUM SURF TREATMENT | Moore | 3390000.07 | 3234050.61 | 2464244.59 | 2308295.13 | 0 | 155949.46 | 155949.46 | 3235000 | 2900000
1129585 | 1134005 | RSD HRP MOUNTAIN VIEW RD NE | Moore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0
1129585 | 1134006 | RSD HRP BEACON COAL MINE RD S | Moore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0
1129585 | 1136086 | RSD 218TH AV SE RECONSTRUCTION | Sahagun | 877846 | 145014.92 | 877846 | 145014.92 | 0 | 732831.08 | 732831.08 | 5972000 | 0
1129585 | 1136351 | RSD CURB REPLACEMENT 3855 | Moore | 300000 | 102546.05 | 300000 | 102546.05 | 0 | 197453.95 | 197453.95 | 300000 | 0
1129585 | 1136352 | RSD 2019 CNTYWDE PAVE PRES | Moore | 3127798 | 2156750.5 | 3127798 | 2156750.5 | 73.03 | 970974.47 | 970974.47 | 3026000 | 3067000
1129585 | 1136934 | RSD HRP BCON MINE RD S | Moore | 212037.92 | 212037.92 | 212037.92 | 212037.92 | 0 | -2.9104e-11 | -2.9104e-11 | 500000 | 0
1129585 | 1136935 | RSD HRP 236A SE SE 384 ST | Moore | 326359.81 | 326359.81 | 326359.81 | 326359.81 | 0 | 0 | 0 | 500000 | 0
1129585 | 1137078 | RSD HRPSE GREENVALLEY RD | Moore | 315925.34 | 315925.34 | 315925.34 | 315925.34 | 0 | 0 | 0 | 300000 | 0
1129585 | 1137510 | RSD HRP SE EDGEWICK ROAD | Moore | 141309.41 | 141309.41 | 141309.41 | 141309.41 | 0 | 0 | 0 | 120000 | 0
1129585 | 1137996 | RSD 2020 CNTYWDE PAVE PRES | Moore | 4420000 | 0 | 4420000 | 0 | 0 | 4420000 | 4420000 | 0 | 0
1129586 | 1129586 | RSD CWP DRAINAGE PRESERVATION | Shular | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1129716 | RSD DIVISION 1 DRAINAGE | Shular | 668200 | 630230.29 | 389516.28 | 351546.57 | 0 | 37969.71 | 37969.71 | 600000 | 0
1129586 | 1129717 | RSD DIVISION 2 DRAINAGE | Shular | 359633.08 | 345907.92 | 129913.33 | 116188.17 | 0 | 13725.16 | 13725.16 | 600000 | 0
1129586 | 1129718 | RSD DIVISION 3 DRAINAGE | Shular | 5157800 | 5057116.66 | 1908140.41 | 1807457.07 | 0 | 100683.34 | 100683.34 | 600000 | 0
1129586 | 1129720 | RSD DIVISION 4 DRAINAGE | Shular | 1435738 | 1394418.88 | 160212.63 | 118893.51 | 0 | 41319.12 | 41319.12 | 350000 | 0
1129586 | 1129721 | RSD DIVISION 5 DRAINAGE | Shular | 1597900 | 1538698.03 | 688416.21 | 629214.24 | 0 | 59201.97 | 59201.97 | 250000 | 0
1129586 | 1129722 | RSD DIVISION 6 DRAINAGE | Shular | 130662 | 121528.82 | 10000.05 | 866.87 | 0 | 9133.18 | 9133.18 | 100000 | 0
1129586 | 1129723 | RSD DIVISION 1 SHOULDERING | Schwartz | 294621.12 | 280693.1 | 130000 | 116071.98 | 0 | 13928.02 | 13928.02 | 100000 | 0
1129586 | 1129724 | RSD DIVISION 2 SHOULDERING | Schwartz | 352559.76 | 352559.76 | 145992.7 | 145992.7 | 0 | 0 | 0 | 100000 | 0
1129586 | 1129725 | RSD DIVISION 3 SHOULDERING | Schwartz | 331863.77 | 331864.47 | 108842.62 | 108843.32 | 0 | -0.7 | -0.7 | 100000 | 0
1129586 | 1129726 | RSD DIVISION 4 SHOULDERING | Schwartz | 273810.94 | 253800.11 | 75164.68 | 55153.85 | 0 | 20010.83 | 20010.83 | 100000 | 0
1129586 | 1129727 | RSD DIVISION 5 SHOULDERING | Schwartz | 199242.81 | 200407 | 30000 | 31164.19 | 0 | -1164.19 | -1164.19 | 50000 | 0
1129586 | 1129728 | RSD DIVISION 6 SHOULDERING | Schwartz | 47968.52 | 37968.52 | 10000 | 0 | 0 | 10000 | 10000 | 50000 | 0
1129586 | 1131511 | RSD SAHALEE WY NE 46000 BLK | Posey | 160000 | 152705.94 | 17241.7 | 9947.64 | 0 | 7294.06 | 7294.06 | 400850 | 400850
1129586 | 1131526 | RSD SE PTRVSKY & 134 A SE | Posey | 440700.26 | 387073.6 | 145874.16 | 92247.5 | 0 | 53626.66 | 53626.66 | 3864000 | 3864000
1129586 | 1131671 | RSD SE PTRVSKY @ 151ST A SE | Posey | 130000 | 47805.29 | 94423.88 | 12229.17 | 0 | 82194.71 | 82194.71 | 165000 | 165000
1129586 | 1131672 | RSD SE PTRVSKY @ 20300BLK | Posey | 135000 | 15321.36 | 123277.19 | 3598.55 | 0 | 119678.64 | 119678.64 | 165000 | 165000
1129586 | 1131693 | RSD UNION HILL@225 BOXCULVERT | Truong | 823000 | 795984.85 | 35201.04 | 8185.89 | 0 | 27015.15 | 27015.15 | 861671 | 1100000
1129586 | 1132523 | RSD GREEN RVR RD S28728 DR IMP | Shular | 99491.68 | 106311.99 | 27480.82 | 34301.13 | 0 | -6820.31 | -6820.31 | 50000 | 0
1129586 | 1132710 | RSD DRAIN IMP SAHALEE-4800 | Posey | 100000 | 76988.45 | 40948.76 | 17937.21 | 0 | 23011.55 | 23011.55 | 382650 | 382650
1129586 | 1135876 | RSD BEAL RD SW | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1135878 | RSD CHERRY VALLEY RD | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1135880 | RSD REINIG ROAD | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129587 | 1129587 | RSD CWP GUARDRAIL PRESERVATION | Mott | -3000000 | 0 | -3000000 | 0 | 0 | -3000000 | -3000000 | 0 | 0
1129587 | 1131274 | RSD 2017-18 GUARDRAIL PRESVTN | Mott | 4800000 | 2973882.08 | 4738755.43 | 2912637.51 | 0 | 1826117.92 | 1826117.92 | 3180771 | 4800000
1129587 | 1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | Mott | 3000000 | 91162.78 | 3000000 | 91162.78 | 0 | 2908837.22 | 2908837.22 | 4520000 | 4520000
1129588 | 1129588 | RSD CWP BRIDGE PRIORITY MAINT | Roark | -440785.45 | 0 | -440785.45 | 0 | 0 | -440785.45 | -440785.45 | 0 | 0
1129588 | 1133675 | RSD YORK BRG 225C RPR | Roark | 20218.16 | 20218.16 | 3625.6 | 3625.6 | 0 | 0 | -1.3642e-12 | 40000 | 0
1129588 | 1134048 | RSD BRAC WD BRG 1136E RPR | Jose | 322208 | 209073.74 | 298895.49 | 185761.23 | 0 | 113134.26 | 113134.26 | 269000 | 322208
1129588 | 1134049 | RSD BRAC LANDSBRG BRG 3075 RPR | Jose | 923533 | 582244.94 | 854761.73 | 513473.67 | 0 | 341288.06 | 341288.06 | 800000 | 943533
1129588 | 1136209 | RSD 2019 BRDIGE WASHING | Roark | 108561.32 | 108561.32 | 108561.32 | 108561.32 | 0 | 0 | 0 | 100000 | 0
1129588 | 1136212 | RSD SUNDAY CR BRG 364C RPR | Roark | 11537.69 | 11537.69 | 11537.69 | 11537.69 | 0 | 1.819e-12 | 1.819e-12 | 50000 | 0
1129588 | 1136453 | RSD FSH HTCH BRG 61B APRCH RPR | Roark | 25000 | 12231.52 | 25000 | 12231.52 | 0 | 12768.48 | 12768.48 | 35000 | 0
1129588 | 1137079 | RSD OVERFLW BR #3217 OVLY | Roark | 95943.15 | 95943.15 | 95943.15 | 95943.15 | 0 | 0 | 0 | 100000 | 0
1129588 | 1137161 | RSD STOSSEL BR 1032A GUSSETTS | Roark | 53977.68 | 53977.68 | 53977.68 | 53977.68 | 0 | 0 | 0 | 75000 | 0
1129588 | 1137385 | RSD PRESTON FRNT BRG 5046 OVLY | Roark | 76853.39 | 76853.39 | 76853.39 | 76853.39 | 0 | 0 | 0 | 0 | 0
1129588 | 1137752 | RSD FLMNG GYSR BRG 3024 PNTG | Martin | 650000 | 0 | 650000 | 0 | 0 | 650000 | 650000 | 650000 | 0
1129588 | 1137856 | RSD BRNG BR TMBR SCR RPR 2019 | Roark | 90000 | 0 | 90000 | 0 | 0 | 90000 | 90000 | 90000 | 0
1129588 | 1137858 | RSD2019 LK DRTHY LKJM BR359B | Roark | 22000 | 17508.74 | 22000 | 17508.74 | 0 | 4491.26 | 4491.26 | 22000 | 0
1129590 | 1129590 | RSD CWP HIGH COLLISION SAFETY | Karinen | 406337.86 | 0 | 406337.86 | 0 | 0 | 406337.86 | 406337.86 | 0 | 0
1129590 | 1131150 | HIGH COLLISION SIGNING AND STRIPING | Mott | 14071.06 | 14071.06 | 0 | 0 | 0 | 0 | 0 | 55000 | 0
1129590 | 1131152 | HIGH COLLISION MARKING REVISION | Mott | 193659.93 | 193659.93 | -9.0949e-13 | 0 | 0 | 0 | -9.0949e-13 | 200000 | 0
1129590 | 1131157 | HIGH COLLISION SIGHTLINE IMPROVEMENT | Mott | 150000 | 660.6 | 149339.4 | 0 | 0 | 149339.4 | 149339.4 | 150000 | 0
1129590 | 1131162 | HIGH COLLISION SIGNAL MODIFICATIONS | Zhen | 68997.89 | 68997.89 | 0 | 0 | 0 | 0 | 0 | 90000 | 0
1129590 | 1131163 | 2017 HIGH FRICTION SURFACE TREATMENT | Sahagun | 3269290 | 2319640 | 963258.17 | 13608.17 | 0 | 949650 | 949650 | 2340000 | 3145000
1129590 | 1132160 | RSD HIGH COLL MARKING REV2 | Mott | 18733.26 | 18733.26 | -3.638e-12 | 0 | 0 | -3.638e-12 | -3.638e-12 | 40000 | 0
1129590 | 1137862 | RSD 2020 HIGH FRCTN SFC TRTMT | Linders | 323200 | 1750.17 | 323200 | 1750.17 | 0 | 321449.83 | 321449.83 | 3232000 | 0
1129591 | 1129591 | RSD CWP SCHOOL ZONE SAFETY | Ashti | -36000 | 0 | -36000 | 0 | 0 | -36000 | -36000 | 0 | 0
1129591 | 1136576 | RSD 19-20 SCHOOL ZONE SAFETY | Hafele | 168509.87 | 163654.77 | 168509.87 | 163654.77 | 825.15 | 4029.95 | 4029.95 | 100000 | 0
1129591 | 1136580 | RSD S 360TH ST SCHOOL PTHWY | Ashti | 12000 | 1922.17 | 12000 | 1922.17 | 660.6 | 9417.23 | 9417.23 | 0 | 0
1129591 | 1136582 | RSD S 298TH ST SCHOOL PTHWY | Ashti | 2000 | 0 | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
1129591 | 1136646 | RSD 42ND AVE S SCHOOL PTHWY | Ashti | 2000 | 0 | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
1129592 | 1129592 | RSD EMERGENT NEED 3865 | Mitchell | 501606 | 0 | 501606 | 0 | 0 | 501606 | 501606 | 0 | 0
1129593 | 1129593 | RSD GRANT CONTINGENCY 3865 | Mitchell | 7084394 | 0 | 7084394 | 0 | 0 | 7084394 | 7084394 | 0 | 0
1129594 | 1129594 | RSD CWP GUARDRAIL CONSTRUCTION | Bleasdale | -400000 | 0 | -400000 | 0 | 0 | -400000 | -400000 | 1350000 | 0
1129594 | 1136084 | RSD 2019-20 GUARDRAIL CONST | Mott | 1049211.09 | 101085.67 | 1049211.09 | 101085.67 | 0 | 948125.42 | 948125.42 | 1045000 | 1045000
1129595 | 1129595 | RSD OLD CASCADE/MILLER BR WEST | Lyou | 2300000 | 358219.35 | 1998411.66 | 56631.01 | 87.6 | 1941693.05 | 1941693.05 | 2300000 | 2300000
1129596 | 1129596 | RSD OLD CASCADE/MILLER BR EAST | Lyou | 2750000 | 448216 | 2385135.06 | 83351.06 | 728.12 | 2301055.88 | 2301055.88 | 2750000 | 2750000
1129598 | 1129598 | RSD ISS HBRT RD@MAY VLLY IMPRV | Sahagun | 2039000 | 136291.44 | 2039000 | 136291.44 | 0 | 1902708.56 | 1902708.56 | 7132000 | 0
1129599 | 1129599 | RSD RENTON AVE PH III SIDEWALK | Sahagun | 3200000 | 309640.91 | 3036341.72 | 145982.63 | 0 | 2890359.09 | 2890359.09 | 2630000 | 3400000
1129841 | 1129841 | RSD CIP OVERSIGHT 3855 | Mitchell | 49269 | 25389.95 | 31914.6 | 8035.55 | 0 | 23879.05 | 23879.05 | 0 | 0
1130260 | 1130260 | RSD SW 108&8 AV SW ROUNDABOUT | Bleasdale | 792000 | 720121.6 | 257066.36 | 185187.96 | 0 | 71878.4 | 71878.4 | 792000 | 0
1130261 | 1130261 | RSD SE176&SE171 WAY ROUNDABOUT | Mott | 452000 | 580583.36 | 372589.13 | 501172.49 | 12160.32 | -140743.68 | -140743.68 | 474000 | 0
1130303 | 1130303 | RSD CIP OVERSIGHT 3865 | Mitchell | 16225 | 8845.72 | 9155.33 | 1776.05 | 0 | 7379.28 | 7379.28 | 0 | 0
1131235 | 1131235 | RSD S 360ST&MILITARY RD RNDABT | Karinen | 1085000 | 132323.66 | 995593.57 | 42917.23 | 0 | 952676.34 | 952676.34 | 1085000 | 0
1131236 | 1131236 | RSD S LANGSTON RD&59 AV RNDABT | Bleasdale | 70000 | 42407.63 | 29283.29 | 1690.92 | 0 | 27592.37 | 27592.37 | 240000 | 0
1131237 | 1131237 | RSD SW 102 ST&8 AVE SW RNDABT | Mott | 662000 | 719613.17 | 579019.49 | 636632.66 | 67132.94 | -124746.11 | -124746.11 | 659687 | 0
1131333 | 1130707 | RSD FC SE 162 A @ 166 CT CDR | Lyou | 1100000 | 426520.03 | 892796.27 | 219316.3 | 0 | 673479.97 | 673479.97 | 2542600 | 2542600
1131333 | 1130708 | RSD FC DAVID POWELL RD RPR | Lyou | 2050000 | 1112189.13 | 1823851.34 | 886040.47 | 55 | 937755.87 | 937755.87 | 1500000 | 1916000
1131333 | 1130710 | RSD FC 380 PL @SR-164 CDR | Lyou | 190000 | 148565.63 | 105586.97 | 64152.6 | 0 | 41434.37 | 41434.37 | 900000 | 0
1131333 | 1130711 | RSD FC WD/DVL BRG 1136B/E SCR | Roark | 400000 | 277937.1 | 122062.9 | 0 | 0 | 122062.9 | 122062.9 | 0 | 0
1131333 | 1130712 | RSD FC DUVALL BRG 1136A SCR | Roark | 150000 | 142411.36 | 7588.64 | 0 | 0 | 7588.64 | 7588.64 | 0 | 0
1131333 | 1130714 | RSD FC PATTON BRG 3015 | Roark | 47523.56 | 47523.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1131333 | 1131333 | RSD CWP FLOOD CONTROL DISTRICT | Lyou | 688414.74 | 0 | 688414.74 | 0 | 0 | 688414.74 | 688414.74 | 0 | 0
1131333 | 1133600 | RSD FC FIFTEEN ML CR BRG#493C | Jose | 350000.01 | 233155.93 | 199395.86 | 82551.78 | 0 | 116844.08 | 116844.08 | 350000 | 0
1131333 | 1134986 | RSD FC GRN RVR RD SLIDE REPAIR | Lyou | 250000 | 167737.73 | 82262.27 | 0 | 0 | 82262.27 | 82262.27 | 250000 | 0
1131333 | 1134994 | RSD FC 428TH AV CULVERT RPLCMT | Shular | 724000 | 722079.56 | 1851.73 | -68.71 | 0 | 1920.44 | 1920.44 | 724000 | 0
1134079 | 1134079 | RSD KENTKANGLEY LNDSBRG RNDABT | Linders | 100000 | 48107.24 | 100000 | 48107.24 | 0 | 51892.76 | 51892.76 | 5220000 | 0
1134080 | 1134080 | RSD WDDUV SNOQ VALLEY IMPROVE | Linders | 150000 | 22002.59 | 150000 | 22002.59 | 0 | 127997.41 | 127997.41 | 150000 | 0
1134081 | 1134081 | RSD REDMOND RIDGE DR NE RNDABT | Sahagun | 1200000 | 8965.17 | 1200000 | 8965.17 | 0 | 1191034.83 | 1191034.83 | 1380000 | 1380000
1134082 | 1134082 | RSD FACILITIES LED CONVERSION | Kosai-Eng | 900000 | 197548.01 | 900000 | 197548.01 | 0 | 702451.99 | 702451.99 | 900000 | 900000
1134083 | 1134083 | RSD COVINGTON WAY SE IMPROVE | LeSmith | 300000 | 476.68 | 300000 | 476.68 | 0 | 299523.32 | 299523.32 | 0 | 0
1134093 | 1134093 | RSD CWP TRAFFIC SAFETY | LeSmith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1134093 | 1136709 | RSD TRAFFIC CALMING | Mott | 100000 | 45.74 | 100000 | 45.74 | 0 | 99954.26 | 99954.26 | 100000 | 0
1134093 | 1136711 | RSD ROADWAY LIGHTING | Mott | 75000 | 28294.93 | 75000 | 28294.93 | 0 | 46705.07 | 46705.07 | 75000 | 0
1134093 | 1136712 | RSD RADAR SPEED SIGNS | Kunihiro | 110000 | 14184.64 | 110000 | 14184.64 | 0 | 95815.36 | 95815.36 | 110000 | 0
1134093 | 1136715 | RSD LEFT TURN PHASING | Zhen | 100000 | 55702.56 | 100000 | 55702.56 | 0 | 44297.44 | 44297.44 | 100000 | 0
1134093 | 1136716 | RSD TRANSVERSE RUMBLE STRIPS | Mott | 84000 | 45.74 | 84000 | 45.74 | 0 | 83954.26 | 83954.26 | 84000 | 0
1134094 | 1134094 | RSD CWP OBSOLETE IT SYS RPLMNT | Yeatts | 550000 | 0 | 550000 | 0 | 0 | 550000 | 550000 | 0 | 0
1134094 | 1136930 | RSD CIP DBASE RPLCMNT | Crippen | 250000 | 0 | 250000 | 0 | 0 | 250000 | 250000 | 250000 | 0
1134094 | 1136931 | RSD SCALE DBASE RPLCMNT | Crippen | 200000 | 0 | 200000 | 0 | 0 | 200000 | 200000 | 125000 | 0
1134094 | 1136932 | RSD BIZDOC MAP VLT RPLCMNT | Crippen | 75000 | 0 | 75000 | 0 | 0 | 75000 | 75000 | 75000 | 0
1134094 | 1136933 | RSD CUTRL RES DBASE RPLCMNT | Crippen | 125000 | 0 | 125000 | 0 | 0 | 125000 | 125000 | 200000 | 0
1135042 | 1135042 | RSD VASHON MAINT FACILITY REPL | Kosai-Eng | 505000 | 10408.17 | 505000 | 10408.17 | 0 | 494591.83 | 494591.83 | 500000 | 0
1135043 | 1135043 | RSD NE MAINT FACILITY CNST | Kosai-Eng | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135044 | 1135044 | RSD PRSTN MAINT FACILTY BLDOUT | Kosai-Eng | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135045 | 1135045 | RSD CWP CLVRT RPLCMT FISH PASS | Cassidy | -737000 | 0 | -737000 | 0 | 0 | -737000 | -737000 | 0 | 0
1135045 | 1136228 | RSD PET RD AT 134TH CULVERT | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135045 | 1136229 | RSD 180TH AT 408TH CULVERT | Mitchell | 292000 | 1321.2 | 292000 | 1321.2 | 0 | 290678.8 | 290678.8 | 0 | 0
1135045 | 1136230 | RSD FAIRWOOD E OF 151 CULVERT | Berryessa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135045 | 1136231 | RSD 185TH AT 179TH CULVERT | Cassidy | 12000 | 14630.92 | 12000 | 14630.92 | 0 | -2630.92 | -2630.92 | 0 | 0
1135045 | 1136232 | RSD 18430 NE 128TH WY CULVERT | Mitchell | 332000 | 9701.56 | 332000 | 9701.56 | 0 | 322298.44 | 322298.44 | 0 | 0
1135045 | 1136233 | RSD LAKE JOY AT 118TH CULVERT | Posey | 108000 | 119478 | 108000 | 119478 | 0 | -11478 | -11478 | 0 | 0
1135045 | 1136234 | RSD WD DUV AT 172ND CULVERT | Shular | 322000 | 25620.26 | 322000 | 25620.26 | 0 | 296379.74 | 296379.74 | 0 | 0
1135045 | 1136235 | RSD AVONDALE AND 144TH CULVERT | Mitchell | 332000 | 29818.88 | 332000 | 29818.88 | 0 | 302181.12 | 302181.12 | 0 | 0
1135045 | 1136236 | RSD 165TH AND 176TH CULVERT | Mitchell | 332000 | 5429.45 | 332000 | 5429.45 | 0 | 326570.55 | 326570.55 | 0 | 0
1135045 | 1136237 | RSD S 370TH ST CULVERT | Lyou | 12000 | 0 | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
1135045 | 1136238 | RSD 33609 NE 24TH ST CULVERT | Quach | 12000 | 17290.38 | 12000 | 17290.38 | 0 | -5290.38 | -5290.38 | 0 | 0
1135045 | 1136239 | RSD 317TH AND THOMAS CULVERT | Quach | 12000 | 9921.23 | 12000 | 9921.23 | 0 | 2078.77 | 2078.77 | 0 | 0
1135045 | 1136240 | RSD 22233 NE 170TH PL CULVERT | Quach | 420000 | 268495.38 | 420000 | 268495.38 | 0 | 151504.62 | 151504.62 | 420000 | 420000
1135045 | 1136241 | RSD 28278 GREEN RVR RD CULVERT | Shular | 800000 | 11350.76 | 800000 | 11350.76 | 0 | 788649.24 | 788649.24 | 740000 | 0
1135045 | 1136419 | RSD SE 432ND CULVERT REPLACEMENT | Cassidy | 12000 | 11516.71 | 12000 | 11516.71 | 0 | 483.29 | 483.29 | 0 | 0
1135046 | 1135046 | RSD PRSTN MAINT FACILTY BLDOUT | Kosai-Eng | 1800000 | 0 | 1800000 | 0 | 0 | 1800000 | 1800000 | 1800000 | 1800000
1135073 | 1135073 | RSD CWP 2019-20 Bridge Safety | Truong | 6040480 | 0 | 6040480 | 0 | 0 | 6040480 | 6040480 | 0 | 0
1135073 | 1135997 | RSD COAL CREEK BRG 3035A REPL | Martin | 2055000 | 419949.71 | 2055000 | 419949.71 | 0 | 1635050.29 | 1635050.29 | 4708280 | 0
1135073 | 1135998 | RSD AMES LK TRS BRG 1320A REPL | Truong | 2094000 | 107729.79 | 2094000 | 107729.79 | 0 | 1986270.21 | 1986270.21 | 12575002.5 | 0
1135073 | 1135999 | RSD UPR TOKUL CK BRG 271B REPL | Martin | 920000 | 169467.85 | 920000 | 169467.85 | 0 | 750532.15 | 750532.15 | 4728421.1875 | 0
1135073 | 1136000 | RSD BARING BRG 509A REPL | Truong | 1500014 | 18666.1 | 1500014 | 18666.1 | 0 | 1481347.9 | 1481347.9 | 14029436.4648 | 0
1135073 | 1136001 | RSD 277TH ST BRG 3126 REPL | Mileti | 533000 | 121911.46 | 533000 | 121911.46 | 0 | 411088.54 | 411088.54 | 2886511.4062 | 0

## CW CIP Data (hidden)
Master | Project | Project Name | PM | Life to Date Budget | Life to Date Expenditures | Current Year Adjusted Budget | Year to Date Expenditures | SumOfCommitment | LTD Balance | YTD Balance | Current Estimate | Baseleine Estimate
1027158 | 1027158 | RSD CW ROADWAY PRESERVATION | Moore | 1.4438e-10 | 0 | 1.4438e-10 | 0 | 0 | 1.4438e-10 | 1.4438e-10 | 0 | 0
1027160 | 1027160 | RSD BRG PRIORITY MAINTNCE | Roark | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1027161 | 1027161 | RSD CLEAR ZONE SAFETY PROGRAM | Bleasdale | -5.457e-12 | 0 | -5.457e-12 | 0 | 0 | -5.457e-12 | -5.457e-12 | 0 | 0
1027163 | 1027163 | RSD QUICK RESPONSE | Mitchell | 240260.65 | 0 | 240260.65 | 0 | 0 | 240260.65 | 240260.65 | 0 | 0
1027163 | 1125296 | RSD S 96 ST & 8 AVE S SINKHOLE | Truong | 1422409.02 | 1076335.96 | 547266.78 | 201193.72 | 0 | 346073.06 | 346073.06 | 1085170.5527 | 1038929.9258
1027163 | 1130162 | RSD SUNSET RD SW SLIDE REPAIR | Posey | 835149 | 770500.51 | 605078.33 | 540429.84 | 0 | 64648.49 | 64648.49 | 600000 | 633831
1027163 | 1130410 | RSD WESTSIDE HWY PERM RD RPR | Posey | 866265 | 830504.86 | 618850.51 | 583090.37 | 0 | 35760.14 | 35760.14 | 787400 | 0
1027163 | 1131582 | RSD NE WD/DVL CULVERT REPL | Shular | 1020000 | 994760.7 | 25517.44 | 278.14 | 0 | 25239.3 | 25239.3 | 1155000 | 1155000
1111172 | 1111172 | RSD FACIL PRESERVATION CW | Harris | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1111819 | 1111819 | RSD C W DRAINAGE PRESERVATION | Shular | 560360.82 | 0 | 560360.82 | 0 | 0 | 560360.82 | 560360.82 | 0 | 0
1111819 | 1126438 | RSD SWM2 XPIPE NE 124 ST&164 AVE NE | Truong | 1248190.04 | 1033368.68 | 215014.79 | 193.43 | 0 | 214821.36 | 214821.36 | 1040745.1855 | 1498143.0977
1111819 | 1126441 | RSD SWM2 S 96 ST STORMWATER PIPES | Truong | 2342895.35 | 1895282.2 | 1928213.61 | 1480600.46 | 0 | 447613.15 | 447613.15 | 1905096.9219 | 2082942.4082
1111819 | 1126443 | RSD SWM2 CROSSPIPE 229 DRIVE SE | Truong | 364375.63 | 364375.63 | 991.98 | 991.98 | 0 | -3.0013e-11 | -3.6835e-11 | 363258.6693 | 406885.7056
1111819 | 1127589 | RSD 165 ST FLD RSK RDUCTN | Karinen | 760146 | 209467.64 | 586385.78 | 35707.42 | 0 | 550678.36 | 550678.36 | 391713 | 0
1111819 | 1127590 | RSD 212 AV SE FLD RSK RDUCTN | Bleasdale | 409594 | 235859.8 | 225438.71 | 51704.51 | 0 | 173734.2 | 173734.2 | 409594 | 0
1124986 | 1124986 | RSD CW HRRRP | Mott/Sahagun | 835183.59 | 0 | 835183.59 | 0 | 0 | 835183.59 | 835183.59 | 4370500 | 0
1127270 | 1127270 | RSD CW SNOW&ICE MTRLS STORAGE | Cassidy | 74173.88 | 0 | 74173.88 | 0 | 0 | 74173.88 | 74173.88 | 0 | 0
1127270 | 1130455 | RSD STILLWTR SAND/SALT STORAGE | Harris | 362059.58 | 362059.58 | 9.0949e-12 | 0 | 0 | 0 | 9.0949e-12 | 264000 | 0
1129584 | 1129584 | RSD CWP QUICK RESPONSE | Mitchell | 3096478.68 | 0 | 3096478.68 | 0 | 0 | 3096478.68 | 3096478.68 | 0 | 0
1129584 | 1132218 | RSD TOLT BRG 1834A EMGY RPR | Jiang | 3779770.83 | 3764770.83 | 269332.67 | 254332.67 | 0 | 15000 | 15000 | 3771500 | 4500000
1129584 | 1132949 | RSD ISS HOB RD ENH SIGNAL | Zhen | 203316 | 193315.02 | 27948.11 | 17947.13 | 0 | 10000.98 | 10000.98 | 150000 | 0
1129584 | 1133864 | RSD NE NVLTY HILL RD SIDEWALK | Sahagun | 347559.23 | 347559.23 | -9.0949e-13 | 0 | 0 | 0 | -9.0949e-13 | 575000 | 0
1129584 | 1134845 | RSD GRNWTR BRG 3050A LD UPGRD | Roark | 47771.12 | 47771.12 | -1.819e-12 | 0 | 0 | 0 | -1.819e-12 | 40000 | 0
1129584 | 1136087 | RSD FOSS RIVER BRG 2605A PAINT | Martin | 640000 | 468199.02 | 640000 | 468199.02 | 0 | 171800.98 | 171800.98 | 640000 | 390000
1129584 | 1136631 | RSD JUDD CK BRD 3184 RPR | O'Day | 100000 | 0 | 100000 | 0 | 0 | 100000 | 100000 | 40000 | 0
1129584 | 1136633 | RSD PATTON DRD 3015 BKT RPR | Jiang | 60000 | 27049.57 | 60000 | 27049.57 | 0 | 32950.43 | 32950.43 | 40000 | 0
1129584 | 1136972 | RSD SW 108&8 AV SW RNDBT REVSN | McManus | 78000 | 66007.28 | 78000 | 66007.28 | 0 | 11992.72 | 11992.72 | 30000 | 0
1129584 | 1137364 | RSD WSD HWY SW DEGRADTN | Posey | 60000 | 32781.29 | 60000 | 32781.29 | 32781.3 | -5562.59 | -5562.59 | 20000 | 0
1129584 | 1137509 | RSD DOCKTON SEAWALL RPR | Roark | 630000 | 209054.9 | 630000 | 209054.9 | 0 | 420945.1 | 420945.1 | 630000 | 0
1129584 | 1137572 | RSD REDMOND RIDGE DR NE XNG | Hafele | 20000 | 0 | 20000 | 0 | 0 | 20000 | 20000 | 20000 | 0
1129584 | 1137577 | RSD 304 ST HAUL RD MITGN | Moore | 155000 | 0 | 155000 | 0 | 0 | 155000 | 155000 | 155000 | 0
1129584 | 1137584 | RSD MIDDLE FORK RD RPR | Cassidy | 76000 | 41832.96 | 76000 | 41832.96 | 0 | 34167.04 | 34167.04 | 76000 | 0
1129584 | 1137860 | RSD 2019 DVD PWLL RD RPR 33621 | Lyou | 100000 | 6511.62 | 100000 | 6511.62 | 0 | 93488.38 | 93488.38 | 100000 | 0
1129585 | 1129585 | RSD CWP ROADWAY PRESERVATION | Moore | 661068.13 | 0 | 661068.13 | 0 | 0 | 661068.13 | 661068.13 | 0 | 0
1129585 | 1129714 | RSD NE STILLWATER HILL RD | Linders | 845190 | 235176.7 | 845190 | 235176.7 | 0 | 610013.3 | 610013.3 | 4675000 | 5050000
1129585 | 1133219 | RSD VASHON HWY SW PAVE PRES | Moore | 4880000 | 4728758 | 156049.08 | 4807.08 | 0 | 151242 | 151242 | 4880000 | 5700000
1129585 | 1133220 | RSD 2018 CNTYWDE PAVE PRES | Moore | 4763000 | 4447489.29 | 4248262.8 | 3932752.09 | 0 | 315510.71 | 315510.71 | 4450000 | 4300000
1129585 | 1133757 | RSD 2018 BITUM SURF TREATMENT | Moore | 3390000.07 | 3234050.61 | 2464244.59 | 2308295.13 | 0 | 155949.46 | 155949.46 | 3235000 | 2900000
1129585 | 1134005 | RSD HRP MOUNTAIN VIEW RD NE | Moore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0
1129585 | 1134006 | RSD HRP BEACON COAL MINE RD S | Moore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0
1129585 | 1136086 | RSD 218TH AV SE RECONSTRUCTION | Sahagun | 877846 | 145014.92 | 877846 | 145014.92 | 0 | 732831.08 | 732831.08 | 5972000 | 0
1129585 | 1136351 | RSD CURB REPLACEMENT 3855 | Moore | 300000 | 102546.05 | 300000 | 102546.05 | 0 | 197453.95 | 197453.95 | 300000 | 0
1129585 | 1136352 | RSD 2019 CNTYWDE PAVE PRES | Moore | 3127798 | 2156750.5 | 3127798 | 2156750.5 | 73.03 | 970974.47 | 970974.47 | 3026000 | 3067000
1129585 | 1136934 | RSD HRP BCON MINE RD S | Moore | 212037.92 | 212037.92 | 212037.92 | 212037.92 | 0 | -2.9104e-11 | -2.9104e-11 | 500000 | 0
1129585 | 1136935 | RSD HRP 236A SE SE 384 ST | Moore | 326359.81 | 326359.81 | 326359.81 | 326359.81 | 0 | 0 | 0 | 500000 | 0
1129585 | 1137078 | RSD HRPSE GREENVALLEY RD | Moore | 315925.34 | 315925.34 | 315925.34 | 315925.34 | 0 | 0 | 0 | 300000 | 0
1129585 | 1137510 | RSD HRP SE EDGEWICK ROAD | Moore | 141309.41 | 141309.41 | 141309.41 | 141309.41 | 0 | 0 | 0 | 120000 | 0
1129585 | 1137996 | RSD 2020 CNTYWDE PAVE PRES | Moore | 4420000 | 0 | 4420000 | 0 | 0 | 4420000 | 4420000 | 0 | 0
1129586 | 1129586 | RSD CWP DRAINAGE PRESERVATION | Shular | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1129716 | RSD DIVISION 1 DRAINAGE | Shular | 668200 | 630230.29 | 389516.28 | 351546.57 | 0 | 37969.71 | 37969.71 | 600000 | 0
1129586 | 1129717 | RSD DIVISION 2 DRAINAGE | Shular | 359633.08 | 345907.92 | 129913.33 | 116188.17 | 0 | 13725.16 | 13725.16 | 600000 | 0
1129586 | 1129718 | RSD DIVISION 3 DRAINAGE | Shular | 5157800 | 5057116.66 | 1908140.41 | 1807457.07 | 0 | 100683.34 | 100683.34 | 600000 | 0
1129586 | 1129720 | RSD DIVISION 4 DRAINAGE | Shular | 1435738 | 1394418.88 | 160212.63 | 118893.51 | 0 | 41319.12 | 41319.12 | 350000 | 0
1129586 | 1129721 | RSD DIVISION 5 DRAINAGE | Shular | 1597900 | 1538698.03 | 688416.21 | 629214.24 | 0 | 59201.97 | 59201.97 | 250000 | 0
1129586 | 1129722 | RSD DIVISION 6 DRAINAGE | Shular | 130662 | 121528.82 | 10000.05 | 866.87 | 0 | 9133.18 | 9133.18 | 100000 | 0
1129586 | 1129723 | RSD DIVISION 1 SHOULDERING | Schwartz | 294621.12 | 280693.1 | 130000 | 116071.98 | 0 | 13928.02 | 13928.02 | 100000 | 0
1129586 | 1129724 | RSD DIVISION 2 SHOULDERING | Schwartz | 352559.76 | 352559.76 | 145992.7 | 145992.7 | 0 | 0 | 0 | 100000 | 0
1129586 | 1129725 | RSD DIVISION 3 SHOULDERING | Schwartz | 331863.77 | 331864.47 | 108842.62 | 108843.32 | 0 | -0.7 | -0.7 | 100000 | 0
1129586 | 1129726 | RSD DIVISION 4 SHOULDERING | Schwartz | 273810.94 | 253800.11 | 75164.68 | 55153.85 | 0 | 20010.83 | 20010.83 | 100000 | 0
1129586 | 1129727 | RSD DIVISION 5 SHOULDERING | Schwartz | 199242.81 | 200407 | 30000 | 31164.19 | 0 | -1164.19 | -1164.19 | 50000 | 0
1129586 | 1129728 | RSD DIVISION 6 SHOULDERING | Schwartz | 47968.52 | 37968.52 | 10000 | 0 | 0 | 10000 | 10000 | 50000 | 0
1129586 | 1131511 | RSD SAHALEE WY NE 46000 BLK | Posey | 160000 | 152705.94 | 17241.7 | 9947.64 | 0 | 7294.06 | 7294.06 | 400850 | 400850
1129586 | 1131526 | RSD SE PTRVSKY & 134 A SE | Posey | 440700.26 | 387073.6 | 145874.16 | 92247.5 | 0 | 53626.66 | 53626.66 | 3864000 | 3864000
1129586 | 1131671 | RSD SE PTRVSKY @ 151ST A SE | Posey | 130000 | 47805.29 | 94423.88 | 12229.17 | 0 | 82194.71 | 82194.71 | 165000 | 165000
1129586 | 1131672 | RSD SE PTRVSKY @ 20300BLK | Posey | 135000 | 15321.36 | 123277.19 | 3598.55 | 0 | 119678.64 | 119678.64 | 165000 | 165000
1129586 | 1131693 | RSD UNION HILL@225 BOXCULVERT | Truong | 823000 | 795984.85 | 35201.04 | 8185.89 | 0 | 27015.15 | 27015.15 | 861671 | 1100000
1129586 | 1132523 | RSD GREEN RVR RD S28728 DR IMP | Shular | 99491.68 | 106311.99 | 27480.82 | 34301.13 | 0 | -6820.31 | -6820.31 | 50000 | 0
1129586 | 1132710 | RSD DRAIN IMP SAHALEE-4800 | Posey | 100000 | 76988.45 | 40948.76 | 17937.21 | 0 | 23011.55 | 23011.55 | 382650 | 382650
1129586 | 1135876 | RSD BEAL RD SW | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1135878 | RSD CHERRY VALLEY RD | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129586 | 1135880 | RSD REINIG ROAD | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129587 | 1129587 | RSD CWP GUARDRAIL PRESERVATION | Mott | -3000000 | 0 | -3000000 | 0 | 0 | -3000000 | -3000000 | 0 | 0
1129587 | 1131274 | RSD 2017-18 GUARDRAIL PRESVTN | Mott | 4800000 | 2973882.08 | 4738755.43 | 2912637.51 | 0 | 1826117.92 | 1826117.92 | 3180771 | 4800000
1129587 | 1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | Mott | 3000000 | 91162.78 | 3000000 | 91162.78 | 0 | 2908837.22 | 2908837.22 | 4520000 | 4520000
1129588 | 1129588 | RSD CWP BRIDGE PRIORITY MAINT | Roark | -440785.45 | 0 | -440785.45 | 0 | 0 | -440785.45 | -440785.45 | 0 | 0
1129588 | 1133675 | RSD YORK BRG 225C RPR | Roark | 20218.16 | 20218.16 | 3625.6 | 3625.6 | 0 | 0 | -1.3642e-12 | 40000 | 0
1129588 | 1134048 | RSD BRAC WD BRG 1136E RPR | Jose | 322208 | 209073.74 | 298895.49 | 185761.23 | 0 | 113134.26 | 113134.26 | 269000 | 322208
1129588 | 1134049 | RSD BRAC LANDSBRG BRG 3075 RPR | Jose | 923533 | 582244.94 | 854761.73 | 513473.67 | 0 | 341288.06 | 341288.06 | 800000 | 943533
1129588 | 1136209 | RSD 2019 BRDIGE WASHING | Roark | 108561.32 | 108561.32 | 108561.32 | 108561.32 | 0 | 0 | 0 | 100000 | 0
1129588 | 1136212 | RSD SUNDAY CR BRG 364C RPR | Roark | 11537.69 | 11537.69 | 11537.69 | 11537.69 | 0 | 1.819e-12 | 1.819e-12 | 50000 | 0
1129588 | 1136453 | RSD FSH HTCH BRG 61B APRCH RPR | Roark | 25000 | 12231.52 | 25000 | 12231.52 | 0 | 12768.48 | 12768.48 | 35000 | 0
1129588 | 1137079 | RSD OVERFLW BR #3217 OVLY | Roark | 95943.15 | 95943.15 | 95943.15 | 95943.15 | 0 | 0 | 0 | 100000 | 0
1129588 | 1137161 | RSD STOSSEL BR 1032A GUSSETTS | Roark | 53977.68 | 53977.68 | 53977.68 | 53977.68 | 0 | 0 | 0 | 75000 | 0
1129588 | 1137385 | RSD PRESTON FRNT BRG 5046 OVLY | Roark | 76853.39 | 76853.39 | 76853.39 | 76853.39 | 0 | 0 | 0 | 0 | 0
1129588 | 1137752 | RSD FLMNG GYSR BRG 3024 PNTG | Martin | 650000 | 0 | 650000 | 0 | 0 | 650000 | 650000 | 650000 | 0
1129588 | 1137856 | RSD BRNG BR TMBR SCR RPR 2019 | Roark | 90000 | 0 | 90000 | 0 | 0 | 90000 | 90000 | 90000 | 0
1129588 | 1137858 | RSD2019 LK DRTHY LKJM BR359B | Roark | 22000 | 17508.74 | 22000 | 17508.74 | 0 | 4491.26 | 4491.26 | 22000 | 0
1129590 | 1129590 | RSD CWP HIGH COLLISION SAFETY | Karinen | 406337.86 | 0 | 406337.86 | 0 | 0 | 406337.86 | 406337.86 | 0 | 0
1129590 | 1131150 | HIGH COLLISION SIGNING AND STRIPING | Mott | 14071.06 | 14071.06 | 0 | 0 | 0 | 0 | 0 | 55000 | 0
1129590 | 1131152 | HIGH COLLISION MARKING REVISION | Mott | 193659.93 | 193659.93 | -9.0949e-13 | 0 | 0 | 0 | -9.0949e-13 | 200000 | 0
1129590 | 1131157 | HIGH COLLISION SIGHTLINE IMPROVEMENT | Mott | 150000 | 660.6 | 149339.4 | 0 | 0 | 149339.4 | 149339.4 | 150000 | 0
1129590 | 1131162 | HIGH COLLISION SIGNAL MODIFICATIONS | Zhen | 68997.89 | 68997.89 | 0 | 0 | 0 | 0 | 0 | 90000 | 0
1129590 | 1131163 | 2017 HIGH FRICTION SURFACE TREATMENT | Sahagun | 3269290 | 2319640 | 963258.17 | 13608.17 | 0 | 949650 | 949650 | 2340000 | 3145000
1129590 | 1132160 | RSD HIGH COLL MARKING REV2 | Mott | 18733.26 | 18733.26 | -3.638e-12 | 0 | 0 | -3.638e-12 | -3.638e-12 | 40000 | 0
1129590 | 1137862 | RSD 2020 HIGH FRCTN SFC TRTMT | Linders | 323200 | 1750.17 | 323200 | 1750.17 | 0 | 321449.83 | 321449.83 | 3232000 | 0
1129591 | 1129591 | RSD CWP SCHOOL ZONE SAFETY | Ashti | -36000 | 0 | -36000 | 0 | 0 | -36000 | -36000 | 0 | 0
1129591 | 1136576 | RSD 19-20 SCHOOL ZONE SAFETY | Hafele | 168509.87 | 163654.77 | 168509.87 | 163654.77 | 825.15 | 4029.95 | 4029.95 | 100000 | 0
1129591 | 1136580 | RSD S 360TH ST SCHOOL PTHWY | Ashti | 12000 | 1922.17 | 12000 | 1922.17 | 660.6 | 9417.23 | 9417.23 | 0 | 0
1129591 | 1136582 | RSD S 298TH ST SCHOOL PTHWY | Ashti | 2000 | 0 | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
1129591 | 1136646 | RSD 42ND AVE S SCHOOL PTHWY | Ashti | 2000 | 0 | 2000 | 0 | 0 | 2000 | 2000 | 0 | 0
1129594 | 1129594 | RSD CWP GUARDRAIL CONSTRUCTION | Bleasdale | -400000 | 0 | -400000 | 0 | 0 | -400000 | -400000 | 1350000 | 0
1129594 | 1136084 | RSD 2019-20 GUARDRAIL CONST | Mott | 1049211.09 | 101085.67 | 1049211.09 | 101085.67 | 0 | 948125.42 | 948125.42 | 1045000 | 1045000
1131333 | 1130707 | RSD FC SE 162 A @ 166 CT CDR | Lyou | 1100000 | 426520.03 | 892796.27 | 219316.3 | 0 | 673479.97 | 673479.97 | 2542600 | 2542600
1131333 | 1130708 | RSD FC DAVID POWELL RD RPR | Lyou | 2050000 | 1112189.13 | 1823851.34 | 886040.47 | 55 | 937755.87 | 937755.87 | 1500000 | 1916000
1131333 | 1130710 | RSD FC 380 PL @SR-164 CDR | Lyou | 190000 | 148565.63 | 105586.97 | 64152.6 | 0 | 41434.37 | 41434.37 | 900000 | 0
1131333 | 1130711 | RSD FC WD/DVL BRG 1136B/E SCR | Roark | 400000 | 277937.1 | 122062.9 | 0 | 0 | 122062.9 | 122062.9 | 0 | 0
1131333 | 1130712 | RSD FC DUVALL BRG 1136A SCR | Roark | 150000 | 142411.36 | 7588.64 | 0 | 0 | 7588.64 | 7588.64 | 0 | 0
1131333 | 1130714 | RSD FC PATTON BRG 3015 | Roark | 47523.56 | 47523.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1131333 | 1131333 | RSD CWP FLOOD CONTROL DISTRICT | Lyou | 688414.74 | 0 | 688414.74 | 0 | 0 | 688414.74 | 688414.74 | 0 | 0
1131333 | 1133600 | RSD FC FIFTEEN ML CR BRG#493C | Jose | 350000.01 | 233155.93 | 199395.86 | 82551.78 | 0 | 116844.08 | 116844.08 | 350000 | 0
1131333 | 1134986 | RSD FC GRN RVR RD SLIDE REPAIR | Lyou | 250000 | 167737.73 | 82262.27 | 0 | 0 | 82262.27 | 82262.27 | 250000 | 0
1131333 | 1134994 | RSD FC 428TH AV CULVERT RPLCMT | Shular | 724000 | 722079.56 | 1851.73 | -68.71 | 0 | 1920.44 | 1920.44 | 724000 | 0
1134093 | 1134093 | RSD CWP TRAFFIC SAFETY | LeSmith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1134093 | 1136709 | RSD TRAFFIC CALMING | Mott | 100000 | 45.74 | 100000 | 45.74 | 0 | 99954.26 | 99954.26 | 100000 | 0
1134093 | 1136711 | RSD ROADWAY LIGHTING | Mott | 75000 | 28294.93 | 75000 | 28294.93 | 0 | 46705.07 | 46705.07 | 75000 | 0
1134093 | 1136712 | RSD RADAR SPEED SIGNS | Kunihiro | 110000 | 14184.64 | 110000 | 14184.64 | 0 | 95815.36 | 95815.36 | 110000 | 0
1134093 | 1136715 | RSD LEFT TURN PHASING | Zhen | 100000 | 55702.56 | 100000 | 55702.56 | 0 | 44297.44 | 44297.44 | 100000 | 0
1134093 | 1136716 | RSD TRANSVERSE RUMBLE STRIPS | Mott | 84000 | 45.74 | 84000 | 45.74 | 0 | 83954.26 | 83954.26 | 84000 | 0
1134094 | 1134094 | RSD CWP OBSOLETE IT SYS RPLMNT | Yeatts | 550000 | 0 | 550000 | 0 | 0 | 550000 | 550000 | 0 | 0
1134094 | 1136930 | RSD CIP DBASE RPLCMNT | Crippen | 250000 | 0 | 250000 | 0 | 0 | 250000 | 250000 | 250000 | 0
1134094 | 1136931 | RSD SCALE DBASE RPLCMNT | Crippen | 200000 | 0 | 200000 | 0 | 0 | 200000 | 200000 | 125000 | 0
1134094 | 1136932 | RSD BIZDOC MAP VLT RPLCMNT | Crippen | 75000 | 0 | 75000 | 0 | 0 | 75000 | 75000 | 75000 | 0
1134094 | 1136933 | RSD CUTRL RES DBASE RPLCMNT | Crippen | 125000 | 0 | 125000 | 0 | 0 | 125000 | 125000 | 200000 | 0
1135045 | 1135045 | RSD CWP CLVRT RPLCMT FISH PASS | Cassidy | -737000 | 0 | -737000 | 0 | 0 | -737000 | -737000 | 0 | 0
1135045 | 1136228 | RSD PET RD AT 134TH CULVERT | Cassidy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135045 | 1136229 | RSD 180TH AT 408TH CULVERT | Mitchell | 292000 | 1321.2 | 292000 | 1321.2 | 0 | 290678.8 | 290678.8 | 0 | 0
1135045 | 1136230 | RSD FAIRWOOD E OF 151 CULVERT | Berryessa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135045 | 1136231 | RSD 185TH AT 179TH CULVERT | Cassidy | 12000 | 14630.92 | 12000 | 14630.92 | 0 | -2630.92 | -2630.92 | 0 | 0
1135045 | 1136232 | RSD 18430 NE 128TH WY CULVERT | Mitchell | 332000 | 9701.56 | 332000 | 9701.56 | 0 | 322298.44 | 322298.44 | 0 | 0
1135045 | 1136233 | RSD LAKE JOY AT 118TH CULVERT | Posey | 108000 | 119478 | 108000 | 119478 | 0 | -11478 | -11478 | 0 | 0
1135045 | 1136234 | RSD WD DUV AT 172ND CULVERT | Shular | 322000 | 25620.26 | 322000 | 25620.26 | 0 | 296379.74 | 296379.74 | 0 | 0
1135045 | 1136235 | RSD AVONDALE AND 144TH CULVERT | Mitchell | 332000 | 29818.88 | 332000 | 29818.88 | 0 | 302181.12 | 302181.12 | 0 | 0
1135045 | 1136236 | RSD 165TH AND 176TH CULVERT | Mitchell | 332000 | 5429.45 | 332000 | 5429.45 | 0 | 326570.55 | 326570.55 | 0 | 0
1135045 | 1136237 | RSD S 370TH ST CULVERT | Lyou | 12000 | 0 | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0
1135045 | 1136238 | RSD 33609 NE 24TH ST CULVERT | Quach | 12000 | 17290.38 | 12000 | 17290.38 | 0 | -5290.38 | -5290.38 | 0 | 0
1135045 | 1136239 | RSD 317TH AND THOMAS CULVERT | Quach | 12000 | 9921.23 | 12000 | 9921.23 | 0 | 2078.77 | 2078.77 | 0 | 0
1135045 | 1136240 | RSD 22233 NE 170TH PL CULVERT | Quach | 420000 | 268495.38 | 420000 | 268495.38 | 0 | 151504.62 | 151504.62 | 420000 | 420000
1135045 | 1136241 | RSD 28278 GREEN RVR RD CULVERT | Shular | 800000 | 11350.76 | 800000 | 11350.76 | 0 | 788649.24 | 788649.24 | 740000 | 0
1135045 | 1136419 | RSD SE 432ND CULVERT REPLACEMENT | Cassidy | 12000 | 11516.71 | 12000 | 11516.71 | 0 | 483.29 | 483.29 | 0 | 0
1135073 | 1135073 | RSD CWP 2019-20 Bridge Safety | Truong | 6040480 | 0 | 6040480 | 0 | 0 | 6040480 | 6040480 | 0 | 0
1135073 | 1135997 | RSD COAL CREEK BRG 3035A REPL | Martin | 2055000 | 419949.71 | 2055000 | 419949.71 | 0 | 1635050.29 | 1635050.29 | 4708280 | 0
1135073 | 1135998 | RSD AMES LK TRS BRG 1320A REPL | Truong | 2094000 | 107729.79 | 2094000 | 107729.79 | 0 | 1986270.21 | 1986270.21 | 12575002.5 | 0
1135073 | 1135999 | RSD UPR TOKUL CK BRG 271B REPL | Martin | 920000 | 169467.85 | 920000 | 169467.85 | 0 | 750532.15 | 750532.15 | 4728421.1875 | 0
1135073 | 1136000 | RSD BARING BRG 509A REPL | Truong | 1500014 | 18666.1 | 1500014 | 18666.1 | 0 | 1481347.9 | 1481347.9 | 14029436.4648 | 0
1135073 | 1136001 | RSD 277TH ST BRG 3126 REPL | Mileti | 533000 | 121911.46 | 533000 | 121911.46 | 0 | 411088.54 | 411088.54 | 2886511.4062 | 0

## CSAProduct Family Data
Project # | Project Name | Product Family | CSA | Ad Date | Construction Contract Advertisement | Construction Start | Current Project Phase | Additional Status Information
1129588 | 2019 Bridge Priority Maintenance | Bridge | SE King County; Snoqualmie Valley; Vashon/Maury | In House | Not applicable, In House Construction | Various dates for program work. | Status is varied for program work.
1136087 | Foss River Bridge #2605A Painting | Bridge | Snoqualmie Valley/NE King County Area | May 2019 | Q2 2019 | Q3 2019 | Implementation
1134049 | Landsburg Bridge #3075 Deck Repair | Bridge | Greater Maple Valley/Cedar River Area | May 2019 | Q2 2019 | Q3 2019 | Implementation
1134048 | Woodinville Duvall Bridge #1136E Deck Repair | Bridge | Snoqualmie Valley/NE King County Area | May 2019 | Q2 2019 | Q3 2019 | Implementation
1135997 | Coal Creek Bridge #3035A Replacement | Bridge | SE King County Area | Jan 2021 | Q1 2021 | Q2 2021 | Preliminary Design
1136001 | S 277th St. Bridge #3126 Replacement | Bridge | SE King County Area | March 2021 | Q1 2021 | Q2 2021 | Preliminary Design
1135999 | Upper Tokul Creek Bridge #271B Replacement | Bridge | Snoqualmie Valley/NE King County Area | Feb 2022 | Q1 2022 | Q2 2022 | Preliminary Design
1135998 | Ames Lake Trestle Bridge #1320A Replacement | Bridge | Snoqualmie Valley/NE King County Area | Jan 2023 | Q1 2023 | Q2 2023 | Preliminary Design
1136000 | Baring Bridge #509A Replacement | Bridge | Snoqualmie Valley/NE King County Area | Feb 2024 | Q1 2024 | Q4 2024 | Preliminary Design
1133600 | FCD Fifteen Mile Creek Bridge #493C Feasibility Analysis for addressing bank erosion and backwatering | Bridge | Four Creeks/Tiger Mountain Area | TBD | TBD | TBD | Preliminary Design
1136631 | Judd Creek Bridge #3184 Load Upgrade/Repair | Bridge | Vashon/Maury Island Area | TBD | TBD | TBD | Planning | Funded for design only. County will be seeking funding for construction.
1136453 | Fish Hatchery Bridge #61B Emergent Repair | Bridge | Snoqualmie Valley/NE King County Area | TBD | TBD | TBD | Planning
1133220 | 2018 CW Pavement Preservation | Roadway | Bear Creek/Sammamish Area; Four Creeks/Tiger Mountain Area; Greater Maple Valley/Cedar River Area | May 2018 | Q2 2018 | Q3 2018 | Implementation
1133757 | 2018 Bituminous Surface Treatment | Roadway | Greater Maple Valley/Cedar; SE King County Area River Area; West King County Areas | May 2018 | Q2 2018 | Q3 2018 | Implementation
1136352 | 2019 CW Pavement Preservation | Roadway | Bear Creek/Sammamish Area; Four Creeks/Tiger Mountain Area; Snoqualmie Valley/NE King County Area; West King County Areas | April 2019 | Q2 2019 | Q3 2019 | Implementation
TBD | 2020 CW Pavement Preservation | Roadway | Locations TBD | April 2020 | Q2 2020 | Q3 2020 | Preliminary Design
1136576 | 2019/20 School Zone Safety | Traffic Control/Safety | West King County Areas; Snoqualmie Valley/NE King County Area | In House | Not applicable, In House Construction | Various dates for program work. | Status is varied for program work.
1131274 | 2017/18 Guardrail Preservation | Roadside | Snoqualmie Valley; Bear Creek/Samamish; Greater Maple Valley/Cedar River. | Jan 2019 | Q1 2019 | Q2 2019 | Implementation
1131237 | SW 102 ST & 8 Ave SW Roundabout | Traffic Control/Safety | West King County Areas | May 2019 | Q2 2019 | Q3 2019 | Implementation
1130261 | SE 176 & SE 171 Way Roundabout | Traffic Control/Safety | West King County Areas | May 2019 | Q2 2019 | Q3 2019 | Implementation
1127589 | NE 165th St Flood Risk Reduction between 179th Place NE and 183rd Place NE south of Cottage Lake. | Traffic Control/Safety | Bear Creek/Sammamish Area | April 2020 | Q2 2020 | Q3 2020 | Final Design
1129599 | Renton Ave Phase III sidewalk construction between 68th Avenue S and S 112th Street | Roadside | West King County Areas | Jan 2021 | Q1 2021 | Q2 2021 | Final Design
1131157 | High Collision Sightline Improvements at S 360 St & 32 Ave S | Traffic Control/Safety | West King County Areas | In House | Not applicable, In House Construction. | Q4 2019 | Final Design
1136084 | 2019/20 New Guardrail Construction | Roadside | Bear Creek/Sammamish Area; Four Creeks/Tiger Mountain Area; Greater Maple Valley/Cedar River Area; Vashon/Maury Island Area | Dec 2019 | Q4 2019 | Q1 2020 | Final Design
1136085 | 2019/20 Guardrail Preservation | Roadside | Locations TBD by Q2 2020 | Jan 2020 | Q1 2020 | Q3 2020 | Preliminary Design
1129714 | NE Stillwater Hill Rd Reconstruction from SR 203 to NE Big Rock Road | Traffic Control/Safety | Snoqualmie Valley/NE King County Area | March 2020 | Q1 2020 | Q3 2020 | Preliminary Design
1134081 | Redmond Ridge NE Roundabout at NE Alder Crest Drive | Traffic Control/Safety | Bear Creek/Sammamish Area | April 2020 | Q2 2020 | Q3 2020 | Preliminary Design
1131235 | S 360 St & Military Road Roundabout | Traffic Control/Safety | West King County Areas | Jan 2021 | Q1 2021 | Q2 2021 | Preliminary Design
1136086 | 218th Ave SE Reconstruction from SE Auburn Black Diamond Road to SE Green Valley Road | Traffic Control/Safety | Bear Creek/Sammamish Area | March 2021 | Q1 2021 | Q2 2021 | Preliminary Design
1129598 | Issaquah-Hobart at May Valley Roundabout | Traffic Control/Safety | Four Creeks/Tiger Mountain Area | Nov 2021 | Q4 2021 | TBD | Preliminary Design | Funded for design only. County will be seeking funding for construction.
1134080 | NE Woodinville Duvall at West Snoqualmie Valley NE | Traffic Control/Safety | Bear Creek/Sammamish Area | TBD | TBD | TBD | Preliminary Design | Funded for design only. County will be seeking funding for construction.
1134079 | SE Kent-Kangley Rd at SE Landsburg Roundabout | Traffic Control/Safety | Greater Maple Valley/Cedar River Area | TBD | TBD | TBD | Preliminary Design | Funded for design only. County will be seeking funding for construction.
1134083 | Covington Way SE Intersection Improvements Study between SE Wax Road and the intersection with 164th Place SE | Traffic Control/Safety | SE King County Area | TBD | TBD | TBD | Preliminary Design | Funded for design only. County will be seeking funding for construction.
1136646 | School Pathway Project 42nd Ave South between S 278th Street and Valhalla Elementary School | Roadside | West King County Areas | Q2 2020 | Q2 2020 | Q3 2020 | Final Design
1136580 | School Pathway Project S 360th St between 32nd Avenue S and the property line of Sequoyah Middle School | Roadside | West King County Areas | Q2 2020 | Q2 2020 | Q3 2020 | Final Design
1136582 | School Pathway Project S 298th St between 36th Place S to 39th Place S | Roadside | West King County Areas | Q2 2020 | Q2 2020 | Q3 2020 | Final Design
1130991 | 2019 Drainage Preservation | Drainage | Bear Creek/Sammamish Area; Four Creeks/Tiger Mountain Area; Greater Maple Valley/Cedar River Area; Vashon/Maury Island Area; SE King County Area; Snoqualmie Valley/NE King County Area; West King County Areas | In House | Not applicable, In House Construction. | Various dates for program work. | Status is varied for program work.
1126441 | S 96th St Stormwater Pipes | Drainage | West King County Areas | Aug 2018 | Q3 2018 | Q2 2019 | Implementation
1130060 | 55 Ave S Culvert south of S 277th | Drainage | West King County Areas | Jan 2019 | Q1 2019 | Q2 2019 | Implementation
1130410 | Westside Highway near Cove Road | Drainage | Vashon/Maury Island Area | April 2019 | Q2 2019 | Q3 2019 | Implementation
1130162 | Sunset Road Slide Repair near 18711 Sunset Road SW | Drainage | Vashon/Maury Island Area | Job Order Contract August 2019 | Q3 2019 | Q3 2019 | Implementation
1130708 | Flood Control David Powell Road Repair A (Phase I) at 36621 SE David Powell Rd | Drainage | Snoqualmie Valley/NE King County Area | In House 2019 | Not applicable, In House Construction. | Q3 2019 | Implementation
1130708 | Flood Control David Powell Road Repair B (Phase II) on the 34500 block of David Powell Rd | Drainage | Snoqualmie Valley/NE King County Area | In House 2019 | Not applicable, In House Construction. | Q3 2019 | Implementation
1129595 | Drainage and Pavement Improvements on Old Cascade from Miller River Road to Miller River west bank | Drainage | Snoqualmie Valley/NE King County Area | Feb 2020 | Q1 2020 | Q2 2020 | Final Design
1129596 | Drainage and Pavement Improvements on Old Cascade to Miller River Bridge East | Drainage | Snoqualmie Valley/NE King County Area | Feb 2020 | Q1 2020 | Q2 2020 | Final Design
1130707 | Flood Control 162 Ave SE @ 166 Court Design of drainage project | Drainage | West King County Areas | March 2020 | Q1 2020 | Q2 2020 | Final Design
1125758 | 14900 W Snoqualimie Valley Road NE Culvert Replacement | Drainage | Snoqualmie Valley/NE King County Area | In House 2020 | Not applicable, In House Construction | Q2 2020 | Final Design
1131511 | Sahalee at 4600 block culvert improvement | Drainage | Bear Creek/Sammamish Area | In House 2020 | Not applicable, In House Construction | Q3 2020 | Final Design
1132710 | Sahalee at 4800 block drainage pipe replacement | Drainage | Bear Creek/Sammamish Area | In House 2020 | Not applicable, In House Construction | Q3 2020 | Final Design
1131526 | Petrovitsky Road and 134th Ave SE culvert improvement | Drainage | West King County Areas | March 2021 | Q1 2021 | Q2 2021 | Final Design
1131672 | Petrovitsky Road at 20300 Blk culvert improvement | Drainage | Greater Maple Valley/Cedar River Area | TBD | TBD | TBD | Final Design | Funded for design only. County will be seeking funding for construction.
1131671 | Petrovitsky Road at 151st Ave SE culvert improvement | Drainage | West King County Areas | TBD | TBD | TBD | Final Design | Funded for design only. County will be seeking funding for construction.
1130710 | Flood Control 380 Place at SR 164 Culvert Replacement | Drainage | SE King County Area | April 2021 | Q2 2021 | Q2 2021 | Preliminary Design
1136229 | 180TH AT 408TH culvert replacement | Drainage | SE King County Area | TBD | TBD | TBD | Planning
1136230 | RSD FAIRWOOD E OF 151 CULVERT | Drainage | West King County Areas | #N/A |  |  | #N/A | WLRD Project
1136231 | 185TH AT 179TH culvert replacement | Drainage | Bear Creek/Sammamish Area | Design On Hold | Design on Hold | Design On Hold | Planning | Design and construction of project contingent upon the availability of program funding.
1136232 | 18430 NE 128TH WY culvert replacement | Drainage | Bear Creek/Sammamish Area | TBD | TBD | TBD | Planning
1136233 | RSD LAKE JOY AT 118TH culvert replacement | Drainage | Snoqualmie Valley/NE King County Area | TBD | TBD | TBD | Preliminary Design
1136234 | RSD WD DUV AT 172ND culvert replacement | Drainage | Bear Creek/Sammamish Area | TBD | TBD | TBD | Planning
1136235 | RSD AVONDALE AND 144TH culvert replacement | Drainage | Bear Creek/Sammamish Area | TBD | TBD | TBD | Planning
1136236 | RSD 165TH AND 176TH culvert replacement | Drainage | Bear Creek/Sammamish Area | TBD | TBD | TBD | Planning
1136237 | RSD S 370TH ST culvert replacement | Drainage | West King County Areas | TBD | TBD | TBD | Preliminary Design
1136238 | RSD 33609 NE 24TH ST culvert replacement | Drainage | Snoqualmie Valley/NE King County Area | TBD | TBD | TBD | Final Design
1136239 | RSD 317TH AND THOMAS culvert replacement | Drainage | SE King County Area | TBD | TBD | TBD | Planning
1136240 | RSD 22233 NE 170TH PL culvert replacement | Drainage | Bear Creek/Sammamish Area | In House | Not applicable, In House Construction | Q3 2019 | Implementation
1136241 | RSD 28278 GREEN RVR RD culvert replacement | Drainage | West King County Areas | In House | Not applicable, In House Construction | Q3 2019 | Implementation
1136419 | RSD SE 432ND ST culvert replacement | Drainage | SE King County Area | CN On Hold | Construction On Hold | Construction On Hold | Preliminary Design | Funded for design only. County will be seeking funding for construction.