## Project Tracking
Project Information | [5 empty] | Project Financial Overview |  |  | Project Updates |  |  | Support Group Notes |  | Gate Review |  |  |  | Gate Tracking Notes | Gates
PM | ME | Work Unit | Project Number | Project Name | PM Meeting Report | Overview | Budget Updates | Grant Notes | Status | Construction Info | Next Steps | ROW | Permitting | Gate 1 Sponsor Charter | Gate 2 CDR | Gate 3 Baseline | DCM | Notes | Follow up needed with:
Hafele | Wally | Road & Traffic | 2021001 new #1142502 | Avondale Rd at Cottage Lake Elementary | Yes | Funding Source: CWP Traffic Safety Sub #1142502 set up 10/11/21 Lifetime Appropriation: $660,000 Q3 Performance: Schedule Delay -100% (Variance = -$5K) Project # delayed getting set up forecast is in 2021001 | Cost estimate in progress - Brendan to provide full report out at November PM Meeting |  | Phase: Preliminary Design in progress. Completed Oct 2021. Schedule Status: Update once information is gathered. Issues: Responsiveness of PSE to establish pole, issues getting them on board. | Start Date: Fall 2021 trying for April 2022 In house | Complete 30% Design Drainage concept complete per Brendan 10/6/21 |  | Tanner Cultural resources review completed August 2021 9/2/21 - ESJ requirements are waived per JK
Berryessa | WLRD | WLRD | 1136230 | Fairwood E of 151st Culvert WLRD Project is lead agency Consultant Design | No | Funding Source: FPP - WLRD is lead Lifetime Appropriation: xx Q3 Performance: below plan. Delays in getting consultant contract advertised and executed |  |  | Phase: Preliminary Design Consultant Contract: HRD WLRD/Rachel Berryessa is lead PM
Dulan | Jon | Drainage | 1131511 | Sahalee at 4600 blk | TBD Q2 2022 | Funding Source: CWP Drainage Preservation Lifetime Appropriation: $361,386 (CN out of division drainage) Q3 Performance: 42% to plan Additional Costs All 2021 costs ($4k) projected were for ROW. Spent $6k |  |  | Phase: Final Design 100% Design complete (rev A); environmental comments incorporated ROW acquisition complete, all permits acquired. Schedule Status: Delayed Lica will plan to report June/July, closer to CN CN pushed to 2022 Issues: See Next Steps | Start Date: Extended to 2022 In house | Working with Broch on comm plan, high ADT | 12/27/19 - waiting for replay from property owner Paylor Properties, LLC on TCE and PE offers. Per Leslie - Offer was forwarded to the owner via certified mail on October 29th. Offer package was returned to ROW on 1/13 as undeliverable. ROW now waiting before moving forward with the offer. Acquisition of TCE property rights expires prior to end of construction/required mitigation 5/29/20 - ROW sent TCE and drainage easement offer to property owner - haven't been responding. Maura sent a communication asking to respond in early June. 7/1/20 - Maura to call property owner this week to remind on offer package. Acquisition completed 4/6/21 - Implications if CN moves from 2021 to 2022? | Janine Waiting for WDFW apps permit application. Janine needs this signed so she can apply. Needs it from Leslie, who hasn't gotten these yet because she is too busy. Will send when she sends out TEC offers again. Rec'd HPA June 2021 - only good until Oct 2021 per 8/4 PM Meeting? | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates | Completed 10/1/21 | Baselined in 2017 per Prism 8/2021 - In House Construction pushed from 2021 to 2022 DCM requested 8/31/2021 Needs DCM for schedule change- sent request to Lica 8/31, Lica sent to Harriette 9/29/21
Jin | Larry | Bridges and Structures | 1138913 | Boise X #3055A - BSP | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $2,891,000 Q3 Performance: Schedule Delay -41% (Variance = -$123K) Competing staff priorities , DNRP project coordination | Anticipated additional funding needs--Pat/Henry/Jessy to make sure to loop Rose in of what budget increase may look like AFTER 30% Design complete | Federal Grant $1.9M BRAC CN obligtation date: 8/29/24 Can extend the date w/supplement | Phase: Preliminary Design CDR complete Dec 2022 Overlapping footprint with DNRP Foothills Trail project incorporated in design--schedule modifications to reduce conflict. Schedule Status: CN moved from 2023 to 2024 Issues: See Budget Update | Start Date: 2/15/2024 Full Road Closure Contractor: TBD | 30% Design to be completed early Q2 Planning on 30% team kickoff meeting in January | •Ad date 3/2023 •RW Scoping/Liaison phase – •RW meet with PM to discuss ROW impacts on 10/14/2021 11/16/21- ROEs – Private property owner expires 7/22/22 & Parks expires 8/31/22 | Tanner Fish Window: July 1 to Aug 31 USCG: Received confirmation of no jurisdiction Critical Areas Memo finalized July 2021 Pursuing using 4Culture for art on the bridge. Sightline was determined to NOT be an issue per Nov meeting w/4Culture | Completed prior to Gates | Completed 12/7/21 | Baseline planned May 2022 |  | 7/26/21 - Jamie sent to Joann/Rose for review via email 7/26 for initial review (prior to formal gate process) 8/10/21- Rose requested adtl review time - to complete 8/13/21. 8/16/21 - Joann and Rose finalized, PM to send to Harriette Sent to DocuSign 8/19
Hafele | Wally | Road & Traffic | 1136576 | School Zone Safety | No | Funding Source: School Zone Safety Lifetime Appropriation: Q3 Performance: Within 25% to plan (-19% and -$26K) | Exceeded 2021 budget by ~8k, but have ~12k remaining from 2019-2020 budget. |  | Phase: Design and Implementation 2021 Projects in Design: - Chief Kanim Middle School: submitted request for cultural resource review. Submitted work orders for flashing beacons. Cultural resources review completed. Signals buying parts to assemble flashing beacons. Sign work planned in August - Northwood Middle School: submitted request for cultural resource review. Submitted work orders for flashing beacons. Cultural resources review completed. Signals buying parts to assemble flashing beacons. Sign work planned in August Schedule Status: Varies by program work Issues: | Start Date: Varies for program work. | Complete sign work for Chief Kanim and Northwood Middle Schools in July 2021 See 9/9/21 email chain Brendan/Rose for more info Flashing Beacons/School Zones left. | Leslie's Priority List- 8th ave crosswalk - 1 parcel in negotiation 4/2/20 - Leslie working on sending a check to owners; anticipates having TCE in the next 30 days. As of May PM meeting, we have this TCE per Brendan. | Katie No NEPA required | Completed 4/12/21 | n/a | n/a | na/ | Currently with Rose as of 3/29/21. Signed per Harriette
Karinen | Wally | Road & Traffic | 1127589 | NE 165th St Flood Risk Reduction | Yes | Funding Source: CW Drainage Preservation (MOU w/ FCD for portion) Lifetime Appropriation: Q3 Performance: Not on Pat's report Forecast in PRISM is $505K for year. Only spent $62K through Q3 | Per 1/13/22 mtg - Marty will complete baseline within next month with CN 2024 with possibility to go in 2023 |  | Phase: Final Design (In House) Revisiting design--raising the road by 1.8 ft. Schedule Status: CN moved to 2022. now 2023 or 2024 WLRD modeling complete--had IDed that CN will be moved to 2022; discussions to move to 2023 ongoing with Rose and JoAnn Issues: Waiting on one ROE for private parcel. | Start Date: Moving to 2023 (but baseline in 2024) In-house | Completion of baseline map for us in estimating volume of compensatory storage. - need one last ROE Martin needs to baseline for CN in 2022 now 23?. (see gate notes) | Per 9/7/21 ROE meeting - ROE needs sent to Maura 8/13/21, at standstill until ROE is received ROEs sent out 9/8/21 - Parks ROE is still pending as of 10/5/21, recieved as of 11/4 From 10/5/21 ROW Meeting: 5 ROE’s sent out 9/8/2021. Parks ROE still pending 10/5/21. Maura following up week of 10/4/21. Maura to follow up with Jenn as needed if higher level Roads/Parks intervention needed . 12/14/21 Follow up sent to property owner 12/10/21 1/6/22 - need one addtl ROE per PM meeting | Grant Smith: Lead Work with permitting staff to clarify permitting needs (shoreline & flood cert. This is in-house.) To update TIR and Critical Areas Memo (WLRD is supporting this). Hec-ras report (hydraulics report) completed 7/17/20. Addendum for TIR updated to reflect report findings - show no impacts. Broch notified community of construction delay in November. 1/6/22- Responded to Permitting request for status on Grading permit | Completed prior to Gates | n/a? | 12/8 - Pat sent Martin some suggested edits - Marty answered - is this ready to submit yet??? - still in limbo? see Wally's email 12/14/21 - Meeing in Jan 2022 for addtl conversation | 7/9/21 - Schedule change. No need for DCM as we will use baseline instead | This is not being tracked on Spend Plan per Pat (funding source issues? - under 1 million) 7/8 - per Allison, Allison working with Martin to baseline this project. 7/9 - Martin to set ROW out by 1 year. Martin to fill out for mgmt. review by week of 7/12/21. Allison PM currently clarifying schedule w/ permitting & maintenance. 6/3 - Update - now permitting IS requiring compensatory storage - project delay while working with DNRP to resolve and determine ROW needs for storage | Pat
Karinen | Wally | Road & Traffic | 1131157 | High Collision Sightline Improvements S 360th St & 32nd Ave S | Yes | Funding Source: CWP High Collision Safety Lifetime Appropriation: $190,300 Q3 Performance: Schedule Delay -45% (Variance= - $20K) |  |  | SEE 1136580 for combined status Phase: 100% Design complete. CDR complete. Revising and resigning plans for upcoming 3/18/22 ad date Schedule Status: Moving sightline CN out to 2022 Issues: | Start Date: 5/28/2022 | Resign Plans. Ad Date March 22 | ROW completed 3/17/21 - PEs Sent offer to Ms. Earls in November - Second offer sent to Ms. Earles 1/28/2020 who replied on 2/14, so final offer was not sent. Per Leslie - PSE easement needed on private property - to be acquired by PSE ROW Negotiation Phase began at establishment of Just Compensation - 8/9/2019 First Offer to Owners 10/19/19 | Dean No NEPA required | Completed prior to Gates | Completed 4/1/21 | Completed 12/12/20 | Completed 10/19/21 | Trigger: moving sightline CN out to 2022? Ms. E TCE expires- will keep in 2021 w/ maint (Rose to confirm with Jeremy 8/16/21). 8/30/21 - Allison to follow up - Allison sent reminder 8/31/21. Allison reached out to Aileen 9/13/21. Wally to follow up 9/13/21 Request sent to PM 8/27/21 , reminder sent 8/31, 9/27/21 - Wally to follow up
Truong | Larry | Bridges and Structures unit Drainage Project | 1130705 | Cross Valley Study (FCD funding) SNW VLY MJR FL MIT Feasability Study | Yes - Quarterly | Funding Source: Flood Control District Lifetime Appropriation: $500K- 2021 Feasibility Study $500K - 2022 Feasibility Study Q3 Performance: Within +/- to Plan Had planned on having consultant on board by Q4 2021 | 10/11 -Estimate for Consultant Contract is $480K -Joann has concerns about scope creep - is reviewing. Meeting held 10/20/21 w/Lyou & management - update? |  | Phase: Feasibility Study 2021 - 2022 only Lyou sent TEAM charter out for KC internal review on 9/2/21. Will be consultant design Schedule Status: Consultant design to start June 2022 Issues: 12/8- Looking for new PM to take this over from Lyou. Political, being watched closely. Now Trinh Truong (Betsey will be helping) | Start Date: Feasibility Study Only | 1/10/22 Michelle Graham setting up team meeting w/John Lyou and team to go over transfer of knowledge |  |  | Completed 4/21/21 | n/a | n/a | n/a | Harriette sent out for signature by Harriette, then Pat will forward to FCD
Dulan | Jon | Drainage | 1136419 | FPP 432nd St Culvert In House Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $57,000 Q3 Performance: Within 25% No dollars projected, but additional expenditures for ROW costs (First American Title) No staff charges go to this projec # & in house design, $0 forecast | No CN funds, pending Rick's CN cost estimate. | 1/3/21 - Applying for Brian Abbot grant (for CN $1.4M) per Sarah. Submitted 1/13/22 to WDFW and RCO for review. Project selections announced 5/2/22 | Phase: Final Design 99% in progress Working on in house CN cost estimates Schedule Status: ROW and permiting on hold until CN is funded. Note that although we're at 99% - it still needs to be baselined Issues: Issues obtaining construction cost estimate from crews causing delay; Rose becoming involved per 1/5/2022 | Start Date: 2023 In house | Baseline project upon receiving updated CN cost estimates. 1/10/22 - Per Lindy, Terry DePriest will be working on the CN estimate | Per Leslie's Priority List - Adjacent private property owners refusal to allow the County on their property. Complex ROW ROW plan sent to Leslie 8/3/20. On hold until funding is identified | Janine Not all apps are done (5 out of 6 completed), will need corps permit ( need to update and date stamp) | Completed prior to Gates | Completed prior to Gates | 8/16 meeting - Lica review- cost est & sched w/ Rick/Jeremy, resend - still need as of 8/30 | Completed 1/25/21 | (Lica mentioned this at PM meeting on 5/5/21), turned into Harriette 6/15/21 - status? 7/7/21, Per Renton PM Meeting - Lica has met with Pat, waiting for Pat to set up meeting with Rose/Joann Trigger: schedule change Harriette sending out for signatures 1/25/21 | PM
Dulan | Jon | Drainage | 1138947 | FPP 284th Ave SE @46913 Culvert Replacement In House Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $845,000 Q3 Performance: Schedule Delay -36% (Variance = -$4K) Planned to be in Final Design by Q3 and spend $12K by end of 2021. No staff charges (ROW and permitting coordination) | Funded for 2022 CN; may need 100-150K more CN funds to build next summer--need to identify funding from fish passage |  | Phase: Preliminary Design CDR sent for signatures 11/19/2021--delay in getting that signed; PM to update PRISM schedule to accommodate . 1/10/22 Ready for docusign? Schedule Status: Issues: Drainage District #6 - concerns with ROE may impact schedule (see ROW notes) | Start Date: 7/5/2022 In house | Discuss need for more CN funding increase at baseline meeting (Pat aware) | 11/16/21 ROW Meeting - still need ROE from Drainage dist ROE-Received email response from Dist. Commissioner with Qs and concerns about project and impacts to property owners. Maura/team are working with Comms team to address concerns and respond to Dist Commissioner- Drake saying they may offer a virtual in-person meeting for more in depth communication 1/10/22 - Rec'd new ROW Plans and request for additnl ROE, In Meg's queue for evaluaiton |  | Completed prior to Gates | (need CN estimates for Iin house crews) 11/10 - Ryan says getting ready to send through - 11/17: Lica finalizing and preparing for Rose/Joann review. 12/13 Harriette should have per JC. Harriette sent to Rose/Joann 1/5/22 | Baseline planned Feb 2022 |  | Pat scheduled meeting w/Rose/Joann et al on 8/16/21 | Rose/Joann
Karinen | Wally | Road & Traffic | 1131235 | RSD S 360 ST & MILITARY ROAD ROUNDABOUT | Yes | Funding Source: Standalone Lifetime Appropriation: $4,150,000 Q3 Performance: Within Plan -24% (Variance= - $45K) | PSRC Contingency Funding Award - 2023 Congestion Mitigation and Air Quality Improvement (CMAQ) Awarded $2,703,125 for CN. Need to obligate CN by June 2023. | PSRC CN Grant CN obligation date: 6/1/23 Need to obligate 3 months prior to CN | Phase: Final Design 90% in progress, anticipated complete December, now January Schedule Status: Closely Monitoring Issues: See ROW notes. CN date was at risk due to ROW, ROW plans sent 9/2021 so should be ok | Start Date: 9/1/2023 Day Labor | Complete 90% Design end of Jan 2022 Project needs to be baseline--Pat working Martin - may need prism omnibus adjustment\ | Need to obligate CN by 6/2023 RW Scoping/Liaison Phase: •ROW plans sent to ROW team in September •ROE-All 15 original ROE’s expired. •7 additional ROEs sent 10/6/21 - 2nd request sent 11/15 12/14/21 - Sent ROW Plan comments to PM 11/30. 10 of 15 ROEs received to date. 1/6/22 PM Mtg update: Revising ROW plans per comments 1/7/22 - Rec'd updated ROW plans for review | Janel No NEPA required No foreseeable permitting issues, using local funds 8/5 PM Meeting - On ART priority list but not ready to submit paperwork yet | Completed prior to Gates | Completed prior to Gates | 9/27/21 - Pat coordinating w/PM still (may need prism adj from omnibus) |  | 7/8/21 - Pat is going to reach out to Martin and Aileen - Martin/Aileen hesitant to baseline - Amara is aware, Pat is reaching out to Aileen. 7/9/21 - Martin to fill out week of 7/12/21. PM sent draft 9/10/21. Possibly federalize project? Would move CN out to 2023 (PSRC Contingency fund) Martin didn't realize he need s to baseline (currently at 60%) - Allison to send him baseline docs per April PM meeting. Allison sent out request 4/6/21, Allison sent reminder to Martin 5/19/21, still not done as of 6/3 - now federalized -AT RISK for obligating CN by 6/2023 - will obtain more info after getting ROE to complete survey (as of 6/3, Maura has everything she needs from Martin - (Allison meeting w/Martin 6/4/21). | Pat
Karinen | Wally | Road & Traffic | 1134081 | Redmond Ridge Roundabout | Yes | Funding Source: Standalone State/WSDOT-CN Lifetime Appropriation: $1,200,00 Q3 Performance: Schedule Delay -72% (Variance = -$22K) Delays due to ROE | Requested $300K in 2nd Omnibus | Project has been awarded WSDOT Local Program construction funds. | Phase: Final Design 99% in progress - 100% and TIR anticipated to complete 12/2021--Jan 2022 Schedule Status: Delayed Moving to 2022 to accommodate for design, ROW, and permits. Issues: See ROW & Permitting notes | Start Date: 6/6/2022 Day Labor Per 11/18 CN ad mtg - Lydia to follow up w/Macile on these requirement and how they apply to this project | Re-sign plans Jan 2022 Rose wants PM to evaluate impact to schedule to determine if we want to push up priority. | ROW to be completed by 1/10/22 - on track ROW Appraisal Phase: Meg on track to have appraisals competed by 10/25/21 Cindy still needs updated ROW plan from Martin as of 10/5/21 - Wally to check with Martin 1/11/22 Consultant should have offers ready for review this week 1/6/22 - revising ROW plans; hopefully done by March per 1/6/2022 | Dean -> Katie No NEPA required. Need C&G permit - will require drainage review. In ART queue for permit - set to be complete April 2022 (as of 9/2/21) - will extend CN to 2023 if not expedited . 9/2021 - Joann is working with ART on prioritizing. 10/4 update Joann still working on moving that up. (should be okay - they have contingency built in) | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates | Pat reviewing - follow up - 9/27/21 (Pat to update budget piece and send to Marty) - 10/11/21 Pat will follow Marty on redmond ridge and where dan left off. 11/1 - Pat will follow up. Never completed | 7/1 - pat to review DCM to see if adtl finance info is required before finalizing form - 7/8 with Pat Trigger: schedule/budget change Emailed Dan forms 2/4/21 for sched change to 2022 CN. Plan is to advertise in late 2021 and CN in 2022 (Complete DCM after budget meeting on 2/16/21) 3/3 asked H if she had update - Waiting for meeting with Pat 3/8 - Pat sent revised budget spreadsheet and will talk to Dan about moving forward (Susan sent email 3/17/21) - Pat/Wally said they need to work out a few more details -5/27 - need update (sent group email) - 6/3/21 Dan sent email to Pat asking if okay to proceed - Macile saying that won't know until we go to council in the fall? | Pat
Dulan | Jon | Drainage | 1140905 | FPP 17401 SE 240th Street SE Culvert Consultant Design | Yes | Funding Source: FPP Program Lifetime Appropriation: $400,000 Q3 Performance: Schedule delay -100% (Variance = -$20K) ROE delays. Planned to have drilling done and consultant on board. Will be below plan at year end | CN not funded | Possible infrastructure Fed funding for CN? | Phase: Planning Consultant design; likely won't have signed contract until April Schedule Status: Delayed; moved to 100% design complete 5/30/2023 Behind schedule on drilling and obtaining ROEs.Contract will not be executed until 2022 Issues: ROW delay; obtained 2 and waiting on 2 | Start Date: N/A Contractor (TBD) will be a bridge CN not funded | Final Draft SOW sent December 2021; LOE still in progress. Plan is to issue NTP to design consultant Q4?--did this happen? | RW Scoping/Liason phase -ROE - 5 requests sent 7/22/21 -as of 10/5/21 - 2 signed, 1 denied 12/14/21 update - will discuss next steps w/PM in meeting scheduled 12/10/21 | Katie | FPP Charter | Planned for Q3 2022 |  |  | 1/25/21 - Rex Hung emailed projects are set up and funded in Oracle EBS Will be one sponsor charter under FPP for 2021/2022 biennium. Notate in prism
Dulan | Jon | Drainage | 1132710 | Sahalee at 4800 blk | Yes | Funding Source: CWP Drainage Preservation Lifetime Appropriation: $100,000 (CN out of division drainage) Q3 Performance: No forecast for 2021 |  |  | Phase: Final Design 100% Design complete, mitigation plan needed. Schedule Status: Extended ROW delays have cause extended schedule--DCM completed June 2021--Joann and Leslie said ROW needs to be done before permitting can be complete. Waiting for permits and ROW (Drainage Easement and TCE), acquisition in progress per 11/29/2021 Issues: ROW delay | Start Date: 6/1/2022 In house | PM working on mitigation plan--this is needed before permits can be applied for. ROW--schedule to be complete 1/2022. | 10/5/21 Meeting AOS completed Offers being prepared - Maura to send out by mid October Monitoring period is 5 years/TCEs good for 7 12/14/21 Offer package for Sue parcel in process. Meeting scheduled with PM to talk about existing easments and city of Sammamish. If PE is needed from city, city will have to present to and get approval by City Council | Janine Need apps form or TCE - ROW to send to Janine so she can start working on permits. 1/5 Needs ACOE permit per Janine - can not obtain until - "I need the mitigation plan prior to applying for the ACOE permit. and the TCEs prior to being able to get the WDFW permit" | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates |  | Baselined in 2018 per Prism
Lyou | Jon | Drainage | 1130706 | NE 8th Lake Allen Outlet | Yes | Funding Source: CWP Flood District Lifetime Appropriation: $1,800,000 Q3 Performance: -84% to plan (anticipated to remain below plan for year) Delays starting design due to lack of ROEs |  |  | Phase: Preliminary Design CDR in progress Schedule Status: Delayed due to issues obtaining ROEs (new requests sent 12/10/21) Issues: Note that there is high level of public resistance (could impact private properties); recieved email complaint from public member on how long project is taking PM is retiring - who is new PM? | Start Date: TBD 2022/23 per JC In house | Scheduled to select alternative 1/31/2022 - delayed, need new PM assigned | Now 35 ROE requested. Full set of ROEs sent out 6/24. New ROE Received and sent to PMs 8/2/21 10/5 ROW Meeting - ROW team preparing to send out another round of ROE letters and plan on door knocking 2 weeks after mailing 11/16/21 - Will send out ROEs again week of 11/22/21. New ROEs sent 12/10/21 | Tanner Make sure Tom is looped in on ROE timelines. | Completed prior to Gates | Planned Jan 2022 - Need new PM assigned! |  |  | Design anticipated to start in Q2? 2021 - previously 2020. Need to hold public meeting and determine ROE needs (some parcels may have easements) Sponsor charter is signed by KC team -> need approval from FCD - Pat will follow up as of 6/28/21 - she says already approved, Pat will send copy
Lyou | Jon | Drainage | 1130710 | SE 380th Culvert (FCD Funding) | Yes | Funding Source: CWP Flood Control District Lifetime Appropriation: $747,666 Q3 Performance: Schedule Delay -44% to plan (Variance= - $64K) Originally planned to complete 100% design by June 2021 | 9/30/21 - received FCD approval for 60% design |  | Phase: Final Design - Working on 90% anticipated to be done Oct Nov Jan 2022--unlikley, need to update in PRISM Schedule Status: Delayed Moved Ad to 3/2022 - Schedule at risk per ROW meeting 11/16. Issues: Access for design work per temporary engineer (Abbas) working on project | Start Date: June 2022 Contractor: TBD Still TBD whether in house 2022 , or ad 2023 - as of 1/27/22 | Complete 90% Design-new temporary engineer (Abbas); plan preparation will be shared among available engineers Delay to 2023? On hold due to repriorizing Old Cascade? (per 1/13/22 team meeting) May go in house in 2022 | ROW Complete date 12/17/21 - Cindy concerned will not make per 11/16/21 meeting (drop dead ROW date is end of April per Ryan) Current Phase: Acquistion 10/21/21 Update: Property owners are considering offers 12/14/21 - door knocking next week - schedule still at risk per Cindy - 1/11/22 - getting some progress! | Janel There is a Fish Window Sec 106 requires field survey per Tom 1/3/22 - Per Jon C, Tribe is asking for a bridge with LWD underneath. Joann is proposing to have further discussions with Tribe | Completed prior to Gates | Completed prior to Gates | Completed 1/28/21 | Completed 6/23/21 Need new DCM if pushing CN to 2023 | 1/26/21 UPDATE - PRISM updated - John confirmed 1/27->Amara finalize Baselined w/FCD. Did not get updated/baselined in PRISM. Susan and Allison to meet with John Lyou 1/19/21 1/26/21 and update forecast in PRISM to match FCD baseline dollars (reverse engineer to have escalated $ match FCD total) - then inform Amara it is ready to baseline - Amara needs done by 28th! Completed Trigger: Schedule change - moving CN to 2022 (baselined at 2021) . 1/12/21- Allison/Susan met w/John to review DCM. John to reach out to Enviro/Emily, ROW (need TCEs), Maintenance (capacity to CN in 2021) - Lyou sent draft for review to Allison/Susan 3/4/21 - Joann/rose asking for (4/5/21 Jon says they have been submitted? - Susan sent email to Lyou - he says revision is with Rose/Joann for Review) - 4/13 - Rose worked with Lyou to revise - should be sending out soon - 4/28 - H sending via DocuSign this week 5/27 - Per Jon w/Rose and Joann 6/7/21 - Harriette to investigate
Lyou | Jon | Drainage | 1136237 | FPP S 370th Culvert In House Design | Yes - ON HOLD | Funding Source: Fish Passage Program Lifetime Appropriation: $57,000 Q3 Performance: Within 25% to plan No staff charges go to this project # & in house design, $0 forecast | No CN funding. Funding for CN uncertain due to no fish in region |  | Phase: Planning/Preliminary Design In House Design 30% in progress--needs update in PRISM, date 12/1/2021 Schedule Status: On hold Design engineer supporting division drainage project design NO report out until we can sort out staff capacity issues. Issues: No fish in region, uncertain future for CN per Ryan 9/30/21 | Start Date: TBD In house | Needs flood hazard certification Need DCM? | Will require a PE and TCE. ROE request reopened. Kilarney Woods property DENIED ROE request 11/16 1/11/22 - no new activity | Janel Permitting scheduled to be competed 5/2021. | Completed prior to Gates | Completed 1/25/21 | Planned 11/30/21 - DELAYED due to staff capacity. Need new PM assigned. CN currently out 10 years. IDE |  | CDR Dates not exact. Joann/Rose working on as of 1/12/21. 1/25 complete per Joann - Joann to send copy to Harriette
Karinen | Wally | Road & Traffic | 1136580 | S 360th Street School Pathway | Yes | Funding Source: CWP School Zone Safety Lifetime Appropriation: Q3 Performance: Schedule Delay (CN) Analyze w/1131157 | Fully funded via emergent funds, high collision safety master, and 21/22 budget pro |  | Phase: 100% Design and CDR complete DCM completed 10/14/21 Schedule Status: Procurement delays pushed main CN to 2022 Issues: procurement delays - see schedule status | Start Date: 5/28/22 In-house; Ms. Earls portion of the work CN ad date now 3/18/22 | 10/5/21 - KC Maintenance planned to install fence by end of October- done Follow up on Victor email--7/26/21 Victor email--feels we should be able to install fence and leave small buffer; he recommended that Marty make arrangements with survey to layout the fence location and cut lines to verify | ROW completed 3/17/21 - PEs Leslie was working on appraisals; was informed of delay 3/4/20 Updated ROW plans with updated scope and get new legal descriptions for negotiations w/ fire district. Ms. Earls would like to be notified before KC Maintenance installs fence on her property | Dean No NEPA required Need to revisit enviro review per Mandana 9/4/20 - met with the environmental engineer in September on site to evaluate trees and 20-ft landscape buffer | n/a | n/a | n/a | See 1131157 | See 1131157
Linders | Wally | Road & Traffic | 1134079 | SE Kent Kangley Rd at Landsburg Rd SE Roundabout | No | Funding Source: Standalone Lifetime Appropriation: $100,000 Q3 Performance: Additional Costs 41% (Variance = $1K) |  |  | Phase: On hold Schedule Status: Issues: | Start Date: 7/18/2022 Day Labor |  |  | Janel No NEPA required Only SEPA is required for temporary fix, no impact to cultural resources | Completed prior to Gates |  |  |  | Currently on hold while working on interim (1141625)
Linders | Wally | Road & Traffic | 1129599 | Renton Ave S. Sidewalk Phase 3 | Yes | Funding Source: Standalone Lifetime Appropriation: Q3 Performance: -44% Schedule Delay (Variance= -$51K) Delays with ROE needed for Survey and APE (ROE was rec'd 9/8/21) | Short by 300k. Requested in 2nd Omnibus 2021. 9/2/21 - Rec'd $300K Reet Funding | WSDOT PE & ROW 2020 Ped & Bike Program (TIB) CN $2M No obligation timeline. ROW cert not req'd prior to Ad. Okay if date extention | Phase: Final Design 99% in progress - to be completed Jan 2022 Schedule Status: Moved from 2021 to 2022 to accommodate for design, ROW, and permits. Ad date 4/2022 Issues: See ROW notes. See Gate notes. Issues (staff changes) with acquiring C&G Permit--Joann and Rose aware. | Start Date: 6/14/2022 60 working days Day Labor Requirements | Per Jan 2022 PM Meeting: Starting Spec Package Jan 2022 ROW to be completed 2/2022 ROW appraisal and negotiation to be completed February 2022. | ROW Completion Date 2/28/22 ROW Negotiation Phase: 1/11/22 update - see ROW meeting notes. SPU needs a plan change - may need council approval per SPU - Cindy trying to get clarifiation? •ROE needed (1 KC housing parcel) to determine APE – Received and sent to Project Team 9/8/21 | Katie No NEPA required (unless we get STP funds) Applied for Seattle Street Improvement Permit for improvements within City limits. 10/4/21 - no longer in ART program per Joann, is almost completed and permitting work will be completed in time. Project support requested prior to creation of ART program 1/6/22 - Plans being reviewed for C&G by Permitting | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates | Completed 3/18/21 | Trigger: schedule change 1/28 Team Meeting - NO CN in 2021. Waiting for grant award to determine CN AD date. May be 2022 or 2021 with delayed CN start to 2022. Emailed Dan forms 2/4/21 for sched change to 2022 CN - 3/3 asked if H she had update - Waiting for Aileen signature - Pat suggests to wait until we receive the official approval, decided to go ahead and complete since schedule is moving out regardless of grant approval (should know by Q2 2021) - all sigs done 3/16 - mark as complete after distribution list goes out
Linders | Wally | Road & Traffic | 1129714 | NE Stillwater Hill Rd | Substantially Complete | Funding Source: CWP Roadway Preservation Federal (PE, CN) Lifetime Appropriation: Q3 Performance: -66% Schedule Delay Variance= -$1.8M CN Procurement delays Planned on $4M for 2021 | Increased construction costs - more info to come from Joann and project team | FHWA PE & CN - $3.6 million | Phase: Implementation Contract executed with Interwest 6/30/21 Schedule Status: On track CN began 7/19/21; substantial completion on 10/19/21 Punch List items sent to contractor, review in field on 11/2. Issues: See Budget notes. | Start Date: 7/1/2021 Contractor: Interwest | John--need WSDOT inspection (Dawn/Jeff working on) and change order for DBE | ARD acquisition in process. Per Leslie as of June PM meeting, ROW is on schedule (due Sept 1) 10/13/20 Stillwater Meeting - ROW can only certify if 8 weeks before ad date (mid-December). Aaron can send obligation paperwork by mid-December (then there's a 4-week review process), does not need to be approved in mid December. Considered obligated when Aaron sends all paperwork. Pat needs to have funds in place by Jan to keep on schedule. | Janel Delays in obtaining permits pushed out CN schedule. NEPA required. SEPA completed 2/20. We need clearing and grading - NOT contingent on ROW cert. Applying for NPDS permit (Nov/Dec 2020) - C&G received 12/16/20 - NPDES received 1/6/21
Linders | Wally | Road & Traffic | 1134083 | Covington Way SE at 164th Pl SE Improvement | Substantially Complete | Funding Source: WSDOT Grant Lifetime Appropriation: Q3 Performance: Uplanned Costs +28% (Variance =+$23K) Due to addtl costs. Added geotech report to maximize grant funding as directed by upper management |  | WSDOT Grant | CDR COMPLETE 2021 (CDR ONLY) Phase: CDR completed 6/3/21. Will begin working on sightline improvements on east curve w/project #1138330 - Last report out was July Schedule Status: Issues: |  |  |  |  | Completed prior to Gates | Completed 6/30/21 |  |  | Received via DocuSign - Not set up under new gate procedures - just file and distribute? Sent email to Amara/Allison/Harriette 6/22/21 - Amara needs cover sheet? - some confusion, see email chain 6/24 - follow up with Jon - who? (Joann has signed Harriette sent out 6/30/21
Jose | Larry | Bridges and Structures | 1138914 | Fifteen Mile Creek Bridge #493C | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $4.4M Q3 Performance: Invoice Posting -30% Working with Stantec on invoicing, per Janel 11/3 (Variance - $155K) Baseline: Completed 9/2021 | Rec'd $2.808M in 2nd Omnibus If obgligated by Sept 2022, CN can be 100% funded (Larry and Jesse aware) (per Sarah - CN is not automatically 100% as previously thought) | Federal Grant Local Bridge Program PE, ROW, CN ROW obligated CN obligation date: 12/31/22 (100% if by 9/21/22) -ROW acq is critical path | Phase: Final Design w/Stantec Design Consultant 90% Coordination Mtg held Sept 2021 99% Design in progress (Dec - consultant stream re-design rec'd and sent to KC team for review, finalize in Jan 2022) Schedule Status: See ROW NOTES - may need revision and Uncertainty about market condition and property owner cooperation for ROW Issues: See Permitting. ROW acquistion process--closely monitoring. | Start Date: 1/16/2023 Full Road Closure Contractor: TBD | 100% Design anticipated to be completed July 2022 | ROW Completion Date: 5/2022 ROW obligation date 9/20/21 for full funding - obligated 9/3/21 1/11/22 update: Plan revisions likely, will create new PE on one or two properties. This may require new review and approval by WSDOT of the ROW Plans- Appraisal on hold pending decision on plan revision . Will be critical path for CN obligation by 9/2022. 9/20/21 - Sent JK a Lessons Learned form to fill out in regard to grant contingency amounts | Katie APE approved by DAHP 2/4/21 Section 106 is complete Eco Charette still in progress as of 8/11/21 10/4/21 - in ART pre-submittal phase per Joann 10/21/21 - Update from Larry at CN Ad mtg - Tribe is recommending that County purchase land in lieu of adding large woody debris. - Not likely to happen, don't want to set a precedent (will look into possiblity of WLRD purchasing) | Completed prior to Gates | Completed prior to Gates | Completed and shared 9/20/21 | working on DCM for budget increase - still as of 8/30. Is it necessary?? | July 2021 - Starting 90% Design | Pat
Martin (Hiromal acting) | Larry | Bridges and Structures | 1135999 | Upper Tokul Creek Bridge #271B - Bridge Safety Program | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $5,046,000 Q3 Performance: Within +/- 25% (-5% & -$20K) | On track Contract expires 12/31/21 - incorporating into amendment to be executed mid Dec Bedrock depth is unknown, may have adtl costs when removing footings |  | Phase: Final Design Received 100% PS&E from DEA 11/2/21 - KC finished internal review 12/1/21 Joann signed plans 1/6/22. Working w/Jerry on spec package Schedule Status: On-track ART currently reviewing C&G - can be issued prior to ROW being complete per BSP mtg on 12/9/21 C&G permit received first week Jan 2022 Issues: Hiromal acting PM during parental leave | Start Date: May 2022 Ad date changed back to FEB 2/28/22 in PRISM now Contractor: TBD | Complete 100% Design-anticipated 12/31/2021 -signed 1/21/22 - BSP meeting conversations about moving forward with procurement process without ROW (not go to ad - just move forward)- Lydia saying will need to obtain written approval from Tricia - CN ad may be pushed into March - Larry to set up mtg week of 1/24 to discuss w/Joann & Rose | ROW complete date 11/30/21 - may be ROW Negotiation Phase: Consultant has presented offers to the property owners 1/11/22 - continued progress but schedule at RISK. We are moving forward with ready to ad package. 1/21/22 -Snoqalmie is signed. Weyerhauser working issues w/tenants. Hamerlys - waiting response from updated (option to pull out offer and pull design and work in ROW - do as change order) | Grant ART will start reviewing C&G in end of Nov per QPU 9/28/21 10/4/21 - currently in review per Joann at ME meeting - should be done mid October (TingTing already rec'd comments per Bridge meeting 10/11/21) - still in review as of 12/9 - can be issued prior to ROW being complete - should be finalized week of 1/4/22 C&G application completed 7/21/21 SEPA Completed July 2021 HPA issued 10/1/21 Flood Hazard Cert approved by WLRD (no analysis required) Corps Permit - no permit letter required from USACE 3/24/21 | Completed prior to Gates | Completed prior to Gates | Completed 4/1/21 |  | In process of baselining - PDO to send updated form - sent latest update to TingTing 1/28/21 - 2/23/21- TingTing setting up meeting with Larry/Pat to review baseline. Meeting scheduled 3/25/21 w/Rose&Joann for final review, TingTing sent out instead of Harriette, 4/1/21 - Susan sent to Harriette for distribution, and saved baseline doc in SharePoint folder
Martin (Hiromal acting) | Larry | Bridges and Structures | 1141001 | NE Tolt Hill Bridge Approach Repair | Yes | Funding Source: Quick Response FHWA Emergency Relief Lifetime Appropriation: $508,541 Q3 Performance: Schedule Delay -40% (Variance = -$28K) | $200K Consultant Contract with DEA 1/24 - per mtg w/Sarah , CN costs increasing and added ROW now | FHWA grant awarded 3/2021 (PE&CN) CN oblig 9/20/22 Would need 100% ready for WSDOT review by 6/22 Yellow RISK See In House CN notes in CN column | Phase: Planning Contract executed w/DEA and NTP issued 10/13/21. Kickoff meeting 11/1/21 Design at 20% - preparing design charrette to accelerate schedule to meet WSDOT requirements - Schedule Status: Issues: Concerns regarding ability to complete schedule in time | Start Date: 3/27/23 Set up as "in house", in PRISM - Hiromal to fix 1/21/22 CN must be obligated by 9/20/22 | Meeting with Rose/Joann 1/25/22 to discuss Preferred Alternative 30% anticipated to be completed by 3/31/22 Accelerating schedule to meet WSDOT requirements. | 11/9 team meeting w/grants -> Leslie and team is researching aquatic lands easement records to see if it needs to be completed before we obligate for CN. Leslie coordinating with Trinh/Katie to help find records 11/16/21 - ROW is researching docs for acquistion on WADNR property from prior bridge CN 12/14/21 update: continuing research. Current info indicates that ROW acq may be needed on WADNR property 1/11/22 - WSDOT researching files from bridge construction to verify status of acquisition files may not be available until week of 1/24/22. Could be risk to schedule - yes! SEE EMAIL, may need ROW funding | Section 106 is already complete per Tom 11/9 ESA should be no effect per Katie 11/9/21 grant meeting = Will know more about permitting needs/timeline after project footprint defined closer to 60% | Completed prior to Gates | Doing "Design Charette" to accelerate schedule. No gate 2? | Planned 3/2022 |  | This Sponsor Charter was signed prior to the PM assignment to Martin in December 2020
Martin (Trinh acting) | Larry | Bridges and Structures | 1135997 | Coal Creek Bridge | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $6,620,500 Q3 Performance: Schedule Delay -49% (Variance - $237K) Planned to spend $2.7M total in 2021 | Additional budget need in 2022 likely due to extended temp bridge rental - budget okay because CN contract came in low per Trinh 9/2021 | Federal (FHWA) PE,ROW,CN | Phase: Implementation- Active Construction KPFF design engineer.Actual NTP sent 9/24/21 Schedule Status: Delayed Contractor to submit CN suspension for 2021 Leave temporary roadway/bridge in place until Q2 2022 - Suspension in effect as of 10/29/21 Issues: Delayed construction due to fish window limitations/delay in procuring materials. Trinh acting PM during parental leave | Start Date: 10/25/21- installation of temporary detour/bridge Bridge removal & replacement moved to May 2022 Contractor: Active Construction | urgent repairs to steel floor beams - BPM project to do floor beam repair $20,000 - Rec'd submittal from contractor in Jan and will install week of 1/24/22 | Needed flood easement to accommodate 0-rise Subconsultant assigned to the bulk of the work, including appraisals. Certification received 3/10/21 9/1 TCEs ending in 2023 per TingTing - should be okay with delayed construction\ 1/21/22 BSP meeting - Relocation expense payments are expected. Consultant will work with relocated prop owner | Katie Fish Window - June 16 - Sept 30 Wet Season - Oct 1 - April 30 8/2021 Katie coordinating with team on constructing for two seasons of construction below OHWM 9/1 - TCEs end in 2023, should be okay with delayed CN Compliance issues with TESC per Katie at 12/9 BSP mtg - Katie meeting w/Contractor | Completed prior to Gates | Completed prior to Gates | Completed 12/15/20 | DCM Not needed as now in CN Phase | Per 7/29/21 Pre-Con meeting - Active said there are long lead times on materials (Rebar - out to October) which will be outside of the fish window. Will issue a limited NTP for prep work but CN is essentially delayed until 2022
Moving design to Traffic Group with Mott as PM | Larry | Bridges and Structures | 1141044 | 2021 CW Pavement Preservation | Yes | Funding Source: CWP Pavement Preservation Lifetime Appropriation: $2,500,000 Q3 Performance: Schedule Acceleration +121% (Variance = +$934K) Added striping work to the contract | Potential change order based on price increases for paint and asphalt ($455/ton at bid opening, now $495/ton) |  | Phase: Implementation NTP executed 7/7/2021 Schedule Status: On track Work has been suspended as of 11/19/21 until weather conditions improve Issues: See Budget Updates | Start Date: 7/7/21 Contractor: Lakeside Industries | Substantial Completion in 5/2022 Note on PM status: Moore's old position to be split up between Resident Engineer and PM for design (Linda) in Wally's group. Send Broch information on award and tribal communication efforts/updates |  | Dean received nighttime variance request from permitting division in March 2021 | Completed prior to Gates | n/a | Completed prior to Gates |  | Rec'd complete via DocuSign 6/21/21 - needs to be distributed and saved in SharePoint (sent email reminder to Harriette 6/28/21
Linders | Wally | Road & Traffic | 1134080 | NE Woodinville Duvall Rd at West Snoqualmie Valley Rd Roundabout | Yes | Funding Source: Standalone Lifetime Appropriation: $150,000 Q3 Performance: Within +/- 25% to plan (-9% and -$2K) Prioritizing other projects | No CN funding. |  | Phase: Planning -- KPFF 10% complete Discussing agricultural land acquistion due to new design concept--Oct/Nov 2021 Schedule Status: Issues: Day labor restrictions | Start Date: TBD No CN funding 9/2/21 Consensus to move schedule 10 yr. out - completed | 1/6/22 - PM Meeting: ROW group continue discussions of roundabout layout with PAO Complete Preliminary Design 10/2023 | Per 9/7 ROE need meeting - need 1 ROE by Dec 2021 - Linders will send email request Survey additional area for new limits of roundabout will be needed in Q3/Q4 2021 - sent request to ROW team? 1/6/22 - PM Meeting: ROW group continue discussions of roundabout layout with PAO May require agricultrual land acquisition. | Grant No NEPA required 10/2020 - Jose wants time to review | Is this done? Says to be completed 9/2022 in PRISM |  |  |  | In Prelmin design planning to complete 2023 CDR planned 9/2023 | Pat
Lyou | Jon | Drainage | 1129595/96 | Old Cascade Miller Bridge | Yes | Funding Source: Standalone Lifetime Appropriation: $2,300,000 Q3 Performance: Within 25% to plan May be under for year -no designer to work on this project - but all of planned $ was for ROW 3rd and 4th Q. |  | Federal & State (FEMA)PE & CN 2022 extension submitted - verbal approval per SG 10/21 - Submitting scope change to OEM. Per Sarah planning to submit by mid Dec | Phase: Final Design 100% Design in progress. 90% Design review meeting scheduled 1/27/22 Schedule Status: tight schedule - team pushing to make 2022 CN dates Issues: Need design completed and ready to review by OEM/EMD asap | Start Date: 7/2022 Day Labor Extended Team meeting held 1/13/22 - Yes, we are moving forward with 2022 CN see Meeting Notes | Timeline from 1/13/22 meeting •5/5/22 Advertise •3/24/22 Ready to Ad sent to procurement •3/17/22 Send bid package (100% plans/specs) to OEM/EMD for review (1 week review) •3/1/22 Final Plans/Specs to be submitted to Jerry •2/03/22 Send 90% Plans/Specs to OEM/EMD for review (2 week review) | ROW - could delay the permit application time. (APPS form delay for HPA, US Forest Services wild life survey - need to conduct this fall and next spring - won't be completed until mid spring). Forest service will let us know in October November (shape file is complete, sent to Leslie M - confirm with Leslie if this has been sent) if we need survey. Leslie sent materials to consultant but have not heard from US forest service. Leslie to contact US forest service or consultant for status. Per Jon C at 8/3/21 ROW Meeting - any changes to culvert #6 should not require adt'l ROW. PEs may still be needed 10/5 - Cindy still working on issues with BNSF and USFS. Will need a few minor changes to the ROW plan - Cindy working w/Lyou ROW on track to complete and have the check cut by end of Jan per 12/14/21 ROW Meeting (1/5 PM meeting - making revisions now per John Lyou) 1/11/22 - USFS sent addtl requirments for thier rOW needs. Will take a couple weeks to complete and transfer documents | Janine NEPA required Need signed TCE or apps form to apply for HPA per Jamie. Redesign culvert--Old castle to confirm if they can do the shortened lid (over 1000ft). Likely not to be significant impacts to permitting per Janine/Grant. Clearing and grading permit will not require drainage review. WDFW HPA requires signed apps form. Dropping culver #6 will not impact mitigation | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates | 1st DCM-6/23/21 2nd DCM - Joanne coordinating with JK as of 9/27/21 to talk about getting extension if scope changes need to delete budget $800k ask - ->Grants Team then needs to submit to OEM. NEVER COMPLETED | Trigger: schedule moving CN out to 2022 due to ROW negotiation delays -8/9/21 - Rose/Joann editing DCM prepared by John L - in progress as of 8/16/21. Harriette/Janice to check in on current DCM status 9/13/21 9/27/21 - Joann needs to connect with JK on whether or not extension will be possible with scope change | Rose/Joann
Mitchell | Jon | Drainage | 1131526 | Petrovitsky Road and 134th Ave SE | Yes | Funding Source: CWP Drainage Preservation Fish Passage-CN Lifetime Appropriation: $530,700 Q3 Performance: -17% Within Plan (Variance= -$2K) Planned to complete design in 2021 Mark posting to wrong #? | Mark M posting to wrong project #? Reached out to Pat for clarification via email 1/19/22 | Per 9/30/21 ad meeting: Pursuing BRIC grant funding -invited to do full application per Joann (working with JVS) - now applying next round per PM mtg 1/5/22 - missing key data pieces. Looking at HMA too per Sarah 11/21 | Phase: Final Design Consultant--OTAK; directed to pause work while Procurement reviews waiver materials; Final negotiations with consultant for Amendment 14 completed for projects A & B ONLY. Projects C & D will be completed in-house Schedule Status: Delayed Extended contract with OTAK to 12/31/2022 Issues: Issues with consultant contract caused delay. | Start Date: 2023 or later Design Consultant: OTAK for A & B; C & D in house. Contractor: TBD | Submit Scope of Work; LOE and ROW for Amendment 14. Processing Amendment 14 and re-starting project design. | Per Rose, 5/6/20 - directing Leslie to get TCEs even though we don't have CN funding. •Permanent drainage easements have been defined. TCEs- likely 2 years out to CN, need about 5 years for monitoring. Need TCEs to complete survey work. Will then go back again if needed for more TCEs when we go to CN. Per 5/11/ Petro meeting, Going to do TCEs for survey work (Norton to talk to Janel and Tanner on the Lynn property to clarify what adt'l areas we need to complete survey work. To develop a ROW plan for TCEs for survey work, to include legal descriptions, to send over to Leslie). Will then also do a TCE for construction. 6/8/20 - may not need any additional access other than existing drainage easement from an environmental and archeological perspective. Otak did request additional access to develop cross sections. Sent ROW plan and legal descriptions to Leslie for 2 TCEs 7/31/20. | Emily - need to have coord mtn with Janel at 60% - To review 60% plans w/ Muckleshoot Tribe when complete. Per Tanner 3/16/20 - current boundaries for ROW would be sufficient. Permit apps need to be in no later than June 2020 - Janel and Norton to confirm? Need permit plan set, need corps permit plan - these are included in the amendment. Janel is not going to prioritize until CN funding schedule is confirmed. | Completed prior to Gates | Completed prior to Gates | 8/4 - finalizing SOW/LOE would need IDE? No CN funding |  | Baseline on hold -REQUEST BASELINE EXEMPTION? | PM
Mitchell | Jon | Drainage | 1131671 | Petrovitsky Road at 151st Ave SE | Yes | Funding Source: CWP Drainage Preservation Lifetime Appropriation: $102,800 Q3 Performance: -88% Schedule Delay (Variance= - $17K) Had planned to complete final design in 2021 | 11/3 - May have KC finish up plans to save $ per Mark - okay since CN is in house |  | Phase: Final Design Project removed from consultant contract; Will be done with KC team. Schedule Status: See project 1131526 Create in-house design team to complete projects C & D. Issues: Availability of KC staff to complete project design--will be monitored. | Start Date: 2/1/2024 In house | Need to follow up with Emily about the status of permits. | Per Leslie- 10/11/19 2nd request for ROEs. (sent 11/6/19). No Construction Funding (risk to moving forward to obtain TCEs) WLRD parcel and one private property (2 total) Norton to finalize ROW plans April 2020. Leslie estimate ROW complete May 2021. Amendment w/Procurement as of 8/23/21 – ROW okay to proceed with appraisal per Ryan | Emily Apply for permits (corps) in March/April 2020. Hear by May 2021 - follow up on the status of permits w/ Emily Programmatic C&G | Completed prior to Gates | Completed prior to Gates | 8/4 - finalizing SOW/LOE |  | Baseline on hold - REQUEST BASELINE EXEMPTION? | PM
Mitchell | Jon | Drainage | 1131672 | Petrovitsky Road at 20300 Blk | Yes | Funding Source: CWP Drainage Preservation Lifetime Appropriation: $91,200 Q3 Performance: -92% Schedule Delay (Variance= -$32K) Had planned to complete final design in 2021 | 11/3 - May have KC finish up plans to save $ per Mark - okay since CN is in house |  | Phase: Final Design Project removed from consultant contract; Will be done with KC team. Schedule Status: See project 1131671 Issues: Availability of KC staff to complete project design--will be monitored. | Start Date: 2/1/2024 In house |  | Per Leslie- 10/11/19 2nd request for ROEs. Sent ROW plan and legal descriptions to Leslie for 2 TCEs 7/31/20. Amendment w/Procurement as of 8/23/21 – ROW okay to proceed with appraisal per Ryan | Emily Programmatic C&G | Completed prior to Gates | Completed prior to Gates | 8/4 - finalizing SOW/LOE |  | Baseline on hold - REQUEST BASELINE EXEMPTION? | PM
Mitchell | Jon | Drainage | 1136229 | FPP 180th Culvert Consultant Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $292,000 Q3 Performance: Schedule delay -91% to plan (Variance=-$50,066) Planned to have design complete by end of 2021 | No CN funding. |  | Phase: Preliminary Design Consultant- KPFF CDR in 3rd draft form, awaiting comments from Muckleshoot; no commitmment on when this will be completed. Will reach out Jan 2022. Working with survey to develop plans for TCEs Schedule Status: Under suspension 8/25/2021--Janel sent notice of suspension to KPFF to put work on hold due to delay of progress with Muckleshoot comments on preferred alternative. Issues: Schedule delay due to Muckleshoot input | Start Date: TBD High priority from exec's office Not CN funded | Muckleshoot Planning is currently reviewing CDR alternatives--hoping a solution comes | Drop dead date per KPFF to obtain ROE is June 1st 2020 per Mark M - working to obtain TCEs during design as an alternative. Will potentially need construction easements. South part of project is on Muckleshoot land, non-responsive so far - may need to go to condemnation. Denied upstream and downstream ROEs. Mark initiated ROW with Leslie on 5/6/20. Need a 3-4 year TCE or a PE. Jon says we may need condemnation- should we suspend design, move forward w/o TCE or reconsider lidar? Submitted info to survey to develop legal descriptions for stream access (TCEs). Per June 2020 project-specific meeting, Mark requested TCEs for design to extend to CN (slated 2022), but CN not funded. Leslie to develop plan for TCEs for design work. | Steve The anticipated preferred alternative has a more significant impact on tribes, may need to present to tribal council per Tom - may want to modify the scope to include lengthening the culvert and modifying the bridge to realign the road, which is significant scope creep. Could be significant delays as we wait to hear from the tribes - likely will need a presentation to the tribes per Jon and Tom 1/5 - Martin Fox/Muckleshoot will want bridge w/LWM per Jon C | Completed prior to Gates | CDR in 3rd draft form awaiting comments from Tribe - ON HOLD |  | SO sent email to MM 8/4/21, MM sent to Harriette 8/10/21 -Not needed? In Prelim Design | Mark sent out revision 6/29 - Susan had a couple more minor corrections. Allison instructed Mark to route to Harriette and cc PDO, Amara when he does Trigger: schedule and budget change due to unexpected coordination issues with outside agency (tribes) 3/16 - Mark still working on it, sent draft 5/28, Pat sent back budget correction - 6/2/21 Rose sent to Allison to have Mark do a few corrections on justification and editing justification 6/7/21 - Allison to work with Mark 6/11/21- 6/22 Allison following up with Mark to see if completed.
Mitchell | Jon | Drainage | 1136231 | FPP 185th at 179th Consultant Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $422,000 Q3 Performance: Schedule delay -74% to plan (Variance= -$77K) Plan was to have 100% design completed by end of 2021 Will be behind for 2021 | No CN funding |  | Phase: 30% Design in progress. Consultant is KPFF--prepared amendment to extend Phase I of contract 11/30/21 CDR - Rose doing final review of revised CDR and then sigs as of 1/26/22 - KPFF need to extend schedule - dependant upoin this being signed by Jan 22! Schedule Status: Issues: contract issue - extension and SCS One lane road for 125 households--need to be creative | Start Date: 2023 or later Contractor: TBD Sole access to 125 houses | Complete CDR, BOD; move to Complete 30% Design Prepare and negotiate final scope of work and level of effort for Phase II | Potential to impact 4f property - increases complexity of acquisition. 2 ROEs required have been obtained. Sent ROW team information to obtain adt'l ROEs for H/H modeling data in July 2020 - received in February 2021 | Grant | FPP Charter | Per 8/4 MSR - scheduled to complete Sept - 2021 - sent to internal KC project team to review 10/22/21- 12/28 sent another revision draft to KC team for review by 1/7/22 |  |  | CDR anticipated to be complete by Q2 Email request sent to PM 8/4/21 | PM
Mitchell | Jon | Drainage | 1136232 | FPP Bear Creek 128th Culvert Consultant Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $362,000 Q3 Performance: Invoice posting -108% (Variance = -$97K) | No CN funding |  | Phase: Final Design Consultant--TetraTech 99% in progress, anticipated complete 6/30/2022. Schedule Status: Suspended Consultant contract was on hold due to improper invoice postings from 2020 work. Consultant is responding to SCS coordination and preparing amendment. Contract end date extended to 6/30/2022. Issues: | Start Date: 2023 or later | Consultant preparing quantitative justification for amendment. Review their respones under SCS usage letter. Janel (&KC Finance) working w/Tetratech on extension to resolve outstanding invoicing issues. | All 3 culverts have ROW needs. Per Leslie, Avondale property acquisition schedule information is too aggressive Amendment for Bear Creek Basin (combined 3; consultant contract) for subconsultant work to prepare LiDAR data (needed for hydraulic report). ~10k. An additional 5k was requested (Amendment 2) for additional work. Not using drones for lidar data. Per Leslie, ROW is forecasted for 10/20/21 as of 10/7/20. may not align with new delivery schedule based on tribal delays. | Grant Held EcoCharrette and ESJ meetings in July 2020. Consultant submitted JARPA applications for all 3 projects in March 2021 | FPP Charter | Completed 1/25/21 | STATUS? 9/27/21 - Pat to follow up w/Mark, she has some questions for him - 10/11 working on it - need to move some phase 2 charges into phase 3 | n/a - baseline instead | Trigger: schedule change 2/23-About to baseline - replaces DCM? Allison followed up 9/13/21 | Pat
Mitchell | Jon | Drainage | 1136235 | FPP Bear Creek Avondale Culvert Consultant Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $332,000 Q3 Performance: Invoice posting delays -143% to plan (Variance = -$129K) | No CN funding |  | Phase: Final Design Consultant--TetraTech 99% in progress, anticipated complete 6/30/2022 Schedule Status: See project 1136232 Issues: | Start Date: 2023 or later | Janel (&KC Finance) working w/Tetratech on extension to resolve outstanding invoicing issues. | All 3 culverts have ROW needs. Per Leslie, Avondale property acquisition schedule information is too aggressive Amendment for Bear Creek Basin (combined 3; consultant contract) for subconsultant work to prepare LiDAR data (needed for hydraulic report). ~10k. An additional 5k was requested (Amendment 2) for additional work. Not using drones for lidar data. Per Leslie, ROW is forecasted for 10/20/21 as of 10/7/20. may not align with new delivery schedule based on tribal delays. | Grant Held EcoCharrette and ESJ meetings in July 2020. Consultant submitted JARPA applications for all 3 projects in March 2021 | Completed prior to Gates | Completed 2/8/21 | STATUS? 9/27/21 - Pat to follow up w/Mark, she has some questions for him - 10/11 working on it - need to move some phase 2 charges into phase 3 | n/a - baseline instead | 1/25/21 CDR changes accepted/re-routed via DocuSign; need to send to distribution list Allison followed up 9/13/21 | Pat
Mitchell | Jon | Drainage | 1136236 | FPP Bear Creek 165th Culvert Consultant Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $362,000 Q3 Performance: Invoice posting delays -92% to plan (Variance = -$115K) | No CN funding |  | Phase: Final Design Consultant--TetraTech 99% in progress, anticipated complete 6/30/2022 Schedule Status: See project 1136232 Issues: | Start Date: 2023 or later | Janel (&KC Finance) working w/Tetratech on extension to resolve outstanding invoicing issues. | All 3 culverts have ROW needs. Per Leslie, Avondale property acquisition schedule information is too aggressive Amendment for Bear Creek Basin (combined 3; consultant contract) for subconsultant work to prepare LiDAR data (needed for hydraulic report). ~10k. An additional 5k was requested (Amendment 2) for additional work. Not using drones for lidar data. Per Leslie, ROW is forecasted for 10/20/21 as of 10/7/20. may not align with new delivery schedule based on tribal delays. | Grant Held EcoCharrette and ESJ meetings in July 2020. Consultant submitted JARPA applications for all 3 projects in March 2021 | Completed prior to Gates | Completed 1/25/21 | STATUS? 9/27/21 - Pat to follow up w/Mark, she has some questions for him - 10/11 working on it - need to move some phase 2 charges into phase 3 | n/a - baseline instead | 1/8/21 - CDR In review w/Joann & Rose (complete w/Avondale) Allison followed up 9/13/21 | Pat
Mitchell | Jon | Drainage | 1139716 | FCD - S Langston Rd at 125th Ave S Drainage | Yes | Funding Source: Flood Control District Lifetime Appropriation: $778,416 Q3 Performance: Schedule Delay -38% (Variance = -$63K) Projected consultant would be on board by Q2 |  | FCD | Phase: Preliminary Design Design Consultant--Four Elements Contract documents went through December 2021; need to execute. Schedule Status: On track Might be tight--need to monitor. Will need FCD approvals - what specific approvals are req'd? Issues: Issue with volume of ROES needed/and potential easements. Need ROEs to begin survey work. See ROW notes. | Start Date: 2/13/2023 Contractor: Yes, but possibly in-house (maint could support if needed) Can be done in Winter per Joann K (no fish window) | Anticipating Jan 2022 start design; Mark watching schedule pending what consultant says - needs to | Originally requested 48 ROEs--PM made list of definitely need/may need 10/5 - ROW Meeting Sending out another round of ROE requests & door knocking 12/14 update - rec'd 2 ROEs 12/7/21 (12 now remaining) May need to acquire title reports per Leslie at 1/5/22 PM meeting | Steve No Fish Window - can be done in Winter per Joann | Completed prior to Gates | Update anticipated date after Mark onboards consultant |  |  | Design anticipated to start in Q2? 2021 - previously 2020. Need to hold public meeting and determine ROE needs (some parcels may have easements) approved in 2021 , Pat to send copy Consultant design - negotiations in progress w/Four Elements as of July 2021
Quach | Jon | Drainage | 1129586 | Drainage Preservation Program | Yes | Funding Source: CWP Drainage Preservation Lifetime Appropriation: Q3 Performance: Within +/- to Plan -25% (Variance=-$599K) Per 10/19 Drainage Meeting - anticipating to be on track to spend all of budget by end of year |  |  | See Drainage MSR TAB below for current status report | Start Date: Varies for program work In house |  | See latest ROW Meeting Notes for current updates |  | Programmatic Charter | n/a | n/a | n/a
Linders | Wally | Road & Traffic | 1136086 | 218th Ave SE Preservation | Yes | Funding Source: CWP Roadway Preservation Federal- PE&CN Lifetime Appropriation: $877,846 Q3 Performance: +39% Addtl Costs (Variance = + $50K) Extra staff time needed to complete drainage design. Budget is still okay per JL Baseline: Completed 9/24/21 | 2nd Omnibus - requesting $500K Stormwater portion will be expensed under division drainage. (set up 10/12/21= 1142478 - open jan 2022) Adtl 458k due to higher estimate than grant application. | PSRC CN Grant Will need to be obligated by Feb 2022 - sending in ob paperwork per sarah 1/3/2022 PS&E corrections by Jerry sent to WSDOT 12/20/21- 1/24, Jim working on obligation package | Phase: Design 99% in progress Baseline complete 9/24/21 Joanne signed PS&E 9/28/21 Schedule Status: On track CN start moved to 5/2022 to accommodate for rainy season and grant obligation timelines Issues: - | Start Date: 5/16/2022 Contractor: TBD | Complete Pre-Ad Checklist by early December January | ROW Complete per 12/14/21 meeting •Received 5 out of 5 ARDs as of 10/19/21 -May need to get TCEs instead? per Wally 12/13 - meeting w/ROW team 12/14 •SUP is in Parks review of the parking section that Roads has requested to use for staging area. 10/21 - Parks reports that SUP is currently being processed by Property Management and Business Revenue Section 11/15/21 - Rec'd Parks edited SUP, sent to RES for finalizing | Katie NEPA completed in October 2020. Permits in progress--received C&G comments in July 2021, submitted responses in August 2021--waiting on approval. Rec'd C&G permit approval 11/23/21 | Completed prior to Gates | Completed prior to Gates | Completed 9/24/2021 |  | 7/19/21 - Pat working on details to finalize 8/5 - Jon L to follow up with Pat In process of implementation per PM (hold? Budget revisions in progress?) 2/4/21 - to be completed after budget revisions. No DCM needed at this time since baseline is in progress. Pat scheduled final baseline meeting 5/27/21, Next Steps- Pat confirming amounts to be transferred between grant phases (unlikely to get Wsdot agreement to transfer between phases), Will need to transfer funds from Drainage Pres to project for fall omnibus - plan still to go to ad next spring and need to be obligated around Feb. Pat is tracking - any update? - Per Wally at ROW meeting mid June -> ad date may need to move out? 7/1/21 - still with Pat, okay to baseline? - PM now Jon Linders - 7/8 with Pat, - Pat needs a decision from ?? on which direction they want to go with transferring grant funds between phases (max $50k without having to send request to PSRC for approval) Pat sent email 7/9/21 -
Linders | Wally | Road & Traffic | 1137862 | 2020 High Friction Surface Treatment | Yes | Funding Source: CWP High Collision Safety Lifetime Appropriation: $3,581,400 Q3 Performance: Schedule Delay -99% (-$1.99M) Planned to spend $3M by year end. Wally would like to see new 2021 est based on revsd sched | C/O to add adtl maintenance repair work (funding from Maintenance) 9/2021 - $385K transferred from emergent needs fund . | HSIP Federal Grant (PE, CE/CN) Sarah is coordinating with the agency to document CN delay. | Phase: Implementation Pre-con with ACCWC; waiting on CN schedule Schedule Status: Delayed Coordinating with construction to schedule pavement repair in 2021 - likely pushed to 2022 per Jon L 11/18/21 Issues: See Budget notes | Start Date: 9/1/2021 Need an updated CN date--it is actualized in PRISM Contractor: American Civil Constructors West Coast HFST can only be applied May-Sept | Discuss budget shortfall with Pat Working on change order for SE 218th St concrete panel repair from heat-related damage (funding from maintenance) after pre-con | No ROE or ROW required | Katie NEPA required SEPA signed and completed 9/2/20 NEPA signed and executed 9/23/20 Rec'd CN Hrs. variance permit 1/14/21 | Completed prior to Gates | Completed prior to Gates | Completed prior to Gates | 2020-12-03 | Executing Construction contract August 2021
O'Day | Larry | Bridges and Structures | 1136631 | Judd Creek Bridge #3184 Load Upgrade/Repair | Substantially Complete | Funding Source: Quick Response Lifetime Appropriation: $128,000 Q3 Performance: Costs posted between 1136631 and 1139236 (Within 25% looking at both) |  |  | Phase: SUBSTANTIALLY COMPLETE 2021 Schedule Status: On-track Construction started 3/30; Final inspection 4/23 Extended consultant work order to end of 2021 Issues: | Start Date: 7/1/2021 Contractor: KPFF, Combined Construction | Closeout. | No ROE or easements required. Possible noise mitigation/noise waiver for work done at night. | Tanner Completed SEPA categorical exemption in June 2020. Submitted apps for C&G and noise waiver in June 2020. | Completed prior to Gates | Completed prior to Gates | n/a - in Implementation |  | In process of implementation per PM - Make note in file for no baseline
Jiang | Larry | Bridges and Structures | 1136633 | Patton Bridge Repair | Substantially Complete | Funding Source: Quick Response Lifetime Appropriation: Q3 Performance: Within 25% to plan (+4% and +$18K) |  |  | Phase: SUBSTANTIALLY COMPLETE May 2021 Schedule Status: Issues: | Start Date: |  |  |  | Completed prior to Gates | Completed prior to Gates | n/a - in Implementation |  | In process of implementation per PM - Make note in file for no baseline
Linders | Wally | Road & Traffic | 1141625 | SE Kent Kangley Rd at Landsburg Rd SE Turning Radius Improvements | Yes | Funding Source: CWP High Collision Safety Lifetime Appropriation: $80,000 Q3 Performance: Planning to spend 10K for year total (Q3+Q4) Design is being billed to a diff number 1131140 (operating #) | Local funds only for CN |  | Phase: Final Design - 90% completed 11/18/21 Schedule Status: On track Issues: Acquisition of Parks property--to be completed March 2022. | Start Date: 7/18/2022 Going out to contract | Complete 100% Design Feb 2022 Start Spec Package Jan 2022 Advertise 5/3/2022 | ROW to attend 90% coord meeting 11/18/21 12/14/21 - Valuations in process 1/11/22 Appraisal almost complete, waiting on title report | 10/4/21 - Joann to follow up with ART team on status. Right now they have scheduled to review in April. Should be okay, they have contingency built in per Joann 8/2021 - Confirmed project will need C&G permit Dec 2021 - rec'd final permit 12/29/21 |  | 8/18- completed through DocuSign -need to distribute | Completed 8/31/21 (AT) |  | Completing CDR/design memo for interim project-8/23 Jon sent baseline to Harriette for DocuSign routing CDR 80% complete as of 7/1/2021
Mott | Wally | Road & Traffic | 1134093 | Traffic Safety Program | Yes | Funding Source: CWP Traffic Safety Program Lifetime Appropriation: Q3 Performance: -58% (Variance= -$384K) Will we be okay by end of year? Will be $130K behind in rumble strips per Pat Large adj to 1136715 Left Turn phasing due to charge errors per 1/19/22 email |  |  | See Traffic Safety Report TAB below for current status report Need to add to spreadsheet "Overhead Flasher Upgrade to LED Stop Signs" - federal grant funded project (sent Linda email request 1/18/22) | Start Date: Varies for program work. |  | No design changes planned as of 8/10/21- moving forward with ROW acquisition. |  | Completed 4/5/21 | n/a | n/a |  | Currently with Rose as of 3/29/21
Quach | Jon | Drainage | 1136233 | FPP Lake Joy Culvert Replacement Consultant Design | Substantially Complete | Funding Source: Fish Passage Program Lifetime Appropriation: $1,252,000 Q3 Performance: Additional Costs +443% (Variance = + $842K) | Pat transferred money into project (based on update crew chief CN estimate) DCM completed - still need baseline? |  | Phase: Completed on 10/15/2021. Consultant--XL Tech Schedule Status: Guardrail completed 10/18, Striping completed 10/19 Issues: Ombudsman concern re: trucks, Jeremy addressing | Start Date: Construction began 7/19/2021 In house | Need an update if we are planning to finalize baseline and DCM for additional budget need. Mitigation is next | ROW includes HOA. Ryan finalizing ROW plan - final changes on TCE legal descriptions to be finalized week of 1/11/21. Survey said no needed changes as of 1/12/21. ROW offers went out 3/25 to property owners, all property acquired 5/19/21 | Grant programmatic permitting/streamlined JARPA Grant is reviewing permit plan set as of early July 2020. Norton to follow up with grant 8/6/20. KC staff reviewing final TIR as of 7/15/20 Rec'd ACOE permit 5/19/21. Fish window - 7/1/21 - 9/15/21 Rec'd ACOE permit 5/19/21. Received HPA 7/14/21 | FPP Charter | n/a | Pat to follow up with Dieu - should baseline because FPP project - NEVER COMPLETED as of Jan 2022 | 10/18/21 - Dieu sent to Harriette to route for sig - Harriette routing 11/8/21 - Pat filling out cover sheet 11/15 and will send to H - H sent out for sigs 11/18 COMPLETED 11/29 | Decided to use DCM to move forward with funding 7/12/21 - Pat to work with Dieu to fill out --- n/a now??? CN In House 2021? 2/24/21 - Jon C having Dieu move forward with baselining for 2022 CN 3/9/21-Dieu reviewing w/Jon C & Pat- goal is to complete by 4/15/21 (Pat scheduled final review mtg w/Joann/Rose on 3/31/21 -moved out to April 29th - Maintenance $estimate is high) (7/8/21 - We will execute DCM 9/13/21 Pat to follow up with Dieu
Premachandra | Larry | Bridges and Structures | 1136001 | S 277th Street Bridge Replacement #3126 | Substantially Complete | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $2,656,100 Q3 Performance: Invoice Posting (-40% Variance= - $357K) Culvert invoice still needs to be processed; waiting on slab issue before other invoices are received | Increased cost relating to change orders for contaminated material disposal and possibly approach slab (per convo w/Trinh 9/23/21) Request for addtnl $280K will be submitted mid Dec |  | Phase: Implementation NTP with Active Construction 7/21/21 Design Engineer of Record: Stantec Substantial completion reached 11/19/21 Working on mitigation/restoration pre-final plan markups Schedule Status: On track Issues: See budget notes. | Start Date: 7/1/2021 Contractor: Active Construction | Jan is last report out | Nearby property owners have not been historically amenable to County work on property. All work will be done in ROW. Constructability concerns at the north end of the project. Discussed with ROW in June. May need TCEs. Survey to stake area and ROW to assess constructability within the ROW. | Janel Rec'd all permits in April 2021. No NEPA required. SEPA completed June 2020. Shoreline Substantial Development permit is exempt - project will qualify for this process per the permitting division as of 7/7/20. Will impact schedule - move to 2022?.) and C&G Permits in July 2020. Fish window (July 1 - September 15) - 10/6 obtained fish window extension to end of September 2021 Submit all permit application in October 2020 | Completed prior to Gates | Completed prior to Gates | Completed 12/14/20 |  | Completed prior to standard distribution implementation
Roark | Larry | Bridges and Structures | 1129588 | Bridge Priority Maintenance | Yes | Funding Source: Lifetime Appropriation: $65,000 (2021) Q3 Performance: -49% (Variance= -$419K) 2 proj moved out to 2022 2 urgent repair added Some invoices delayed Projected to be approx $200K short at year end from plan for BPM per Ben |  |  | See Bridge Priority Maintenance Tab for full update | Start Date: Varies for programmatic work | Fish Hatchery- Per 8/18 Bridge unit meeting: Moving forward with installing gates and will be coordinating with Tom/archeological during excavation. Removal completed July 2021 |  | Status is varied for program work | Completed 6/2/21 | n/a | n/a | n/a
Mott | Wally | Road & Traffic | 1138918 | 16th Ave SW Non-Motorized Improvements | Yes | Funding Source:CWP High Collision Safety Lifetime Appropriation: $1.5M Q3 Performance: Within +/- 25% to Plan (+12% +$10K) | Encroachments on private property from 2006 Roads project originally increasing costs 11/4- Will need to ask for more $ from urgent funds due to design cost overruns AND ask for extension 2nd Omnibus-$500K , now standalone | WSDOT 2019 State HSIP Grant Federal (Traffic Calming) May return Fed funds to make ROW process easier? - Mtg scheduled 1/7/212to discuss | Phase: Final Design. In progress. Schedule Status: Moved CN to 2024. Public outreach--potential backlash; translated website/posters in 7 languages and public comment end of February. Issues: Will need extension on April 2023 obligation date. | Start Date: 03/01/2024 No Ad Date? Set up for In house CN in PRISM, need to fix? | Complete 60% design-3/31/22--might be tight. Now says 5/2022 Linda to update CDR and baseline dates for current schedule in PRISM--currently says N/A - confirm? | RW Scoping/Liaison phase - -Researching property and ROW history – Leslie and Linda M coordinating, working w/ survey •May be able to remove Sars property. Title report on Saars received 9/7/21 reviewed by Survey and ROW and PM – Expanded team meeting to be scheduled •Rcv’d for ROW $.5M in 2nd Omnibus (pending budget process) 11/10/21 - Meg provided estimates for cost associated with removal of parking for 2 properties. 1/11/22 no new updates | Katie 1/6/22 PM Meeting - Katie preparing APE | Completed prior to Gates | Linda had marked n/a - will put in date - Q3? | Linda had marked n/a - will put in date |  | Linda to prepare a Design Memo. 7/1/21 PM Meeting - made aware that Linda had marked CDR and baseline as N/A - they need to be completed - action item | PM
Quach | Jon | Drainage | 1136239 | FPP 317th and Thomas Culvert In House Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $57,000 Q3 Performance: Within 25% to plan No staff charges go to this projec # & in house design, $0 forecast | CN not funded; likely CN cost is $1.1 million | Not moving forward with 2020 FEMA CN grant funding opportunity. | Phase: Preliminary Design Working on CDR and design plan options Schedule Status: On hold On hold to support division drainage design work. Planning to move to Consultant Design per WLRD needs report? Says would start in June, RFP Pending Issues: | Start Date: TBD In house | Complete CDR 11/30/2021 - NO delayed | Most ROE's obtained (one downstream owner did not grant access). Likely to need TCEs per Ryan - 4/1/20 | Katie | FPP Charter | 7/27 - Dieu says will be delayed until Nov. - Now delayed to March 2022 |  | Completed 1/26/21 | CDR anticipated to be complete June 2021 per MSR - project has had competing priorities needing to complete work for drainage crews DCM Trigger: schedule change Harriette sending out for signatures 1/25/21 Sent email request 7/29/21 | PM
Mott/ Dovey | Wally | Road & Traffic | 1141111 | 2019-2020 CW Guardrail Preservation - Tier 3 & Bridges | Yes | Funding Source: CWP Guardrail Preservation Lifetime Appropriation: Q3 Performance: Within +/- 25% to Plan No cost forecast until Q4 ($75K) CN moved out to early 2022 | Budget is short--need to move $ from CW pot to residual from 1136085 to 1141111 to fully-fund. - 10/7 Still working w/Pat Per Tier 4&5 mtg on 10/12/21 - just identifying (not designing) complete list of locations by end of year (Dan D) |  | Phase: Final Design. 99% in progress; incorporating elements from coordination meeting for pre-ad send out. Schedule Status: Moved Tier 3 ad to 10/21/21 11/30/21 1/2022,3/22 bridges will be advertised Q2 2022. Issues: Ongoing meetings with utlility relocations, seeing some movement. | Start Date: 2/28/2022 4/15/22 | Tier 3 on track to advertise 3/10/22 |  | 10/7 PM MSR: Meeting w/EU staff to review changes to roadways included in the package | n/a | n/a | n/a
Jiang | Larry | Bridges and Structures | 1139286 | Bridge Load Upgrade Safety Program | No | Funding Source: Lifetime Appropriation: Q Performance: 1139286 & 1141464 are analyzed together on spend plan |  |  | Phase: Schedule Status: On schedule per Bridge Unit meeting 10/11/21 Issues: | Start Date: | Completed 26 bridge load ratings total for 2021 |  |  | Completed prior to Gates | n/a | n/a |  | Completed via DocuSign 4/26/21 - Mark complete after Harriette distributes to masses (sent Harriette reminder 6/28/21
Quach/Shular | Jon | Drainage | 1136238 | FPP NE 24th St Culvert In House Design | Yes | Funding Source: Fish Passage Program Lifetime Appropriation: $57,000 Q3 Performance: Within 25% to plan No staff charges go to this projec # & in house design, $0 forecast | See grant notes - CN funded by FCD | 9/2021- Rec'vd $950K Flood Reduction Grant (FCD) funding for 2023 CN funding | Phase: Final Design 90% in progress. PM working on CDR. Schedule Status: Delayed. Ryan needs to revise CN sched from 10 years out to 2023. Issues: Extensive flooding on North of NE 24th St associated with recent beaver activity, local utility will not be able to relocate the waterline that passes through project site | Start Date: Summer 2023 In house | Need to complete CDR- before continuing work on design. (Still need CN cost estimate to complete CDR as of 12/13) Final design anticipated to be complete March 2022 Ryan to update CN schedule, per new funding. | Requests submitted to ROW in November 2019. (still valid per Ryan 10/5/21) 3 parcels - TCEs EU requested new apps form for new ROE work related to beavers per Ryan 10/5 - Leslie/team need to review w/WDFW/EU 11/16/21 - pending for final RW plan showing PE on Girl Scouts property - moving ahead with valuations. No update for 12/14/21. No updates 1/11/22 | Janine Corps permit in process as of 3/4/20 - need BOD before we can apply for this per Janine as of 10/7/20 ACOE permit in process as of late march 2020. Per Janine - can't submit permits until plans have been completed. Corps permits has NOT been submitted. | FPP Charter | Request sent 7/29/21 11/1/21 - JC to check w/Ryan - 11/10 - Ryan says working on it. Needs a CN cost estimate to include in the CDR |  | Completed 1/26/21 | Baseline on hold -need CDR first! Currently anticipated to be completed May 2021? DCM Trigger: schedule change Harriette sending out for signatures 1/25/21 | ME
Lyou | Jon | Drainage | 1130709 | SE 384th St @ 176th FCD Funded Not to be confused with 1139811 (CRAB funded) | Start March 2022 | Funding Source: FCD Lifetime Appropriation: $xx EAC per Sponsor Charter:$1.6M Q3 Performance: No forecast for 2021 - new | Subproject under 1131333 CWP FCD FCD will review Gate 1, 2 and 30,60,90 design |  | Phase: Preliminary Design to start 1/3/22 Schedule Status: Waiting for ROEs to start project Issues: Not to be confused with 1139811 which is SE 384th St at 176th too, but CRAB funded | Start Date: July 2023 (per WLRD needs report) Feb 2024 per Sponsor Charter | Final Design to start 9/2022 | FCD will need to review ROW if applicable. ROE's sent 11/16 - no responses as of 12/14/21 |  | Completed 12/28/21 | Planned April 2022 - Need to revise Scheud and new PM assigned
Lyou | Jon | Drainage | 1139811 | SE 384th St @ 176th Ave SE Drainage Improvement | Start Q2 2022? | Funding Source: Standalone Lifetime Appropriation: $1,150,001 Q3 Performance: No forecast for 2021 - new | CRAB approved partial award of $800K to begin project Total project EAC= $1,150,000 | State CRAB (RAP) Grant Potential 90% rec'd 7/2021 Design obligated 9/2021 | Phase: Planning: Will be consultant design Schedule Status: Waiting for ROEs to start project. PRISM schedule needs to be updated Issues: Not to be confused with 1130709 which is SE 384th St at 176th too, but under the FCD program | Start Date: July 2023 per Charter | Need RFP for consultant - timeline? Sponsor charter states prelim to start 7/2021, Final to start 1/2022 Need to start design within one year of receiving CRAB grant | Per Sponsor Charter: ROW may be complex due to Muckleshoot Tribe owning land where culvert is located 9/28/21 - Lyou sent ROE request to Maura for 6 diff properties 12/14/21 update: ROEs sent 11/16/21 - no responses yet but communication with one property owner has occurred. |  | Completed 9/24/21 | Planned Feb 2022 - Need to revise Scheud and new PM assigned |  |  | Just awarded $800k for design in 21/22 (funds available July 2021 Can request adtl funding in 23/24 automatically. Need to start Design w/in 1 year and CN within 6 years of signing contract (see email approval from Sarah 6/16/21) 6/24/21 - Pat is going to work on setting up charter
Linders | Wally | Road & Traffic | 1139145 | SE Green Valley Rd and 218th Ave SE Intersection Improvement | Start April 2022 | Funding Source: Standalone STP grant Lifetime Appropriation: $675,000 Q3 Performance: No forecast for 2021 - new |  | Awarded $454K for PE&ROW (discussed in Grants meeting - from Puget Sound Regional Council (PSRC)) - rec'd fund authorization | Phase: Design to begin 2022 1/6/22 Found out Linders is PM. Kickoff meeting scheduled 2/24/22 start reporting our April 2022 Schedule Status: Issues: | Start Date: 2024 | Prelim Design to start 12/22 Final Design to start 10/22 Acquisition to start 10/22 |  |  | Completed 1/10/22 | Planned to complete Aug 2022 |  |  | Awarded $454K for PE&ROW (discussed in Grants meeting - from Puget Sound Regional Council (PSRC)) Pat looking into whether PE is starting in 2021 or 2022 (CN in 2024) - No expenditure projections expected for 2021. Will be starting design in 2022
Wang | Wally | Road & Traffic | 1129598 | Issaquah-Hobart at SE May Valley Rd Roundabout/Intersection | Yes | Funding Source: Standalone Lifetime Appropriation: Q3 Performance: -71 % Schedule Delay (Variance= -$43K) Originally planned to have consultant on board by Q3 2021 | Needs CN funding. | No grant funding at this time | Phase: Preliminary Design Consultant- Transpo; negotiations Jan-March 2022 Schedule Status: CN extended to 2024 to coordinate with 15 mile creek. Issues: CN TBD--see Budget notes. | Start Date: 6/19/2024 Advertise 4/21/24 Contractor: TBD | Consultant Onboarding expectted April 2022- Transpo Final Design to start Sept 2022 | ROE and easements required Sent ROE renewal request to property group in August 2021 (Per 9/7 ROE priority meeting -need 23 for site visit - request 8/20/21) | Katie NEPA required. |  | Planned to complete April 2022 - need to update and push out?
Quach/Shular | Jon | Drainage | 1138339 | FCD S 106th St (18th Ave S) | Yes | Funding Source: FCD Funds Lifetime Appropriation: $151,000 Q3 Performance: Schedule Delay -100% (Variance = -$25K) Planned ROW costs (no staff labor) |  |  | Phase: Final Design 100% Design in progress, designed plans approved 10/15/21 12/29 Dieu sent CDR for final review to Ryan - then should be routed for signatures--sent by 1/5/22 for review from Rose/Harriette Schedule Status: Extended Issues: | Start Date: 8/1/2022 In house | Send final design plans to Cindy/ROW when complete. | Per 10/5 ROW Meeting - Will need ROW plan updates from final design. Ryan hoping to have ready by end of week. (Appraisal will continue while they wait) 10/5/21 - Cindy will be working on relocation plan for property with motor home. ROW completion date - hoping for 3/31/22 - on track as of 10/5, still on track as of 11/16 meeting 12/14/21 - Valuations complete and in review. Review to be completed week of 12/13/21. Review complete - final reports expected 1/20/22 | Janine No NEPA required ACOE permit application in process as of 8/5/20. When will application be complete? 10/6 - In progress per MSR. Still in progress per Dec 2021 MSR, still in progress jan 2022 pm meeting Per Jon C 4/3/20 - will have an HPA. Likely will have a window for construction but if we can stay out of the water we may be able to do it outside of this. | Completed prior to Gates | 1/5/22 - in review w/Rose/Joann | baseline exemption? This is FCD project | Per 8/3/21 ROW meeting - moving to 2022 In House CN - Ryan to complete as of 9/1 - NEVER COMPLETED | 2/8/21 - Jon C says should be sending out to Harriette to circulate for review next week 3/9/21 - update, Jon C reviewed and wanted corrections. Dieu trying to find time to complete (will need more review) Roads signed off, Pat sent to FCD as of 2/1/21 (2/10 - FCD is very backlogged ) - pat to check, Pat to send to Harriette 6/28/21 Email request sent 8/3/21 Allison to follow up with Ryan 9/13/21 to fill out DCM | Rose/Joann
Dulan | Jon | Drainage | 1140906 | FPP 156th Ave SE and SE 240 Street SE Culvert In House Design | Start Q2 2022? | Funding Source: Fish Passage Program Lifetime Appropriation: $100,000 Q3 Performance: Within 25% (-7%) No staff charges go to this projec # & in house design. Planned to spend $10K total for 2021 |  |  | Phase: In House design to start Q2 2022? Schedule Status: CN extended to 2023 to coordinate with 15 mile creek. No schedule until more infor available from procurement | Start Date: TBD |  | R/W Scoping/Liason Phase -5 ROEs sent -3 out of 5 signed as of 10/5/21 -Will discuss next steps w/PM in meeting scheduled on 12/10/21 |  | FPP Charter | Planned Feb 2022 - Need to revise Sched |  |  | 1/25/21 - Rex Hung emailed projects are set up and funded in Oracle EBS Will be one sponsor charter under FPP for 2021/2022 biennium.
Truong | Larry | Bridges and Structures | 1135998 | Ames Lake Trestle Bridge #1320A - Bridge Safety Program | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $2,094,100 Q3 Performance: Within +/- 25% (-23% & -$61K) Plan to be on track for year end |  | State CRAB PE,CN Received 2700K CRAB grant total Did not receive Fed funding in 2021 | Phase: Final Design- 90% in progress Projected complete March 2022 Consultant Design: Jacobs 90% design package being reviewed by team Schedule Status: On-track Issues: | Start Date: 6/6/2023 Contractor: TBD | 90% Coordination Mtg Feb 2022 (may happen earlier), expected to finalized Mar 2022 | Ad date 3/2023 RW Scopin/Liaison Phase -No ROW activity needed on this project at this time 12/14/21 Updated ROW plans completed by Jake 1/18/22 Hydraulic analysis - may need flood easements per BSP meeting conversations 1/21/22 | Katie Fish window 7/15 - 9/30 No NEPA required Held Ecocharette meeting in August. Jacobs working on submitting corps drawings for review end of October 2021 - (delayed still as of 11/16/21 - need to have LWM design completed first) | Completed prior to Gates | Completed prior to Gates | Completed 3/3/21 |  | In process of baselining - 1/27 Susan/Trinh - completing as test- will send draft doc to Amara 2/19 - Meeting w/Pat,Larry,Trinh,Susan to review . 2/22 Pat set up meeting 3/1/21 w/Joann/Rose to get final review before sending out for signature . Approved - Trinh will be sending out to H soon
Truong | Larry | Bridges and Structures | 1136000 | Baring Bridge #509A - Bridge Safety Program | Yes | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $1.595M Q3 Performance: Within +/- 25% (+8% & +$16K) May be under due to amendment delays at year end per Trinh | Project is currently $3.8 million over budget ($1.6M submitted in 2nd Omnibus 2021); waiting for approval by Council to execute amendment #5 |  | Phase: Final Design -- 90% in progress Consultant Design: HNTB Need to execute Amendment #5, resume 90% after (hoping to execute early Jan 2022) Schedule Status: Delays due to amendment #5 execution. Continued design delays could jeopardize permit and ROW acquisition Issues: Budget See Budget Updates | Start Date: 4/26/2024 Contractor: TBD | Execute Amendment #5; rec'd approval of omnibus. Finalizing justification and anticipate Jan 2022 execution | Ad date 11/2023 RW/Scoping/Liason Phase: Snare parcel -early acquisition in progress 12/14 - No addtn'l ROW activity at this time | Katie No NEPA required. Snoqualmie Tribe NEW temporary structure now triggering TWO additional indivdiual corps permits that will EACH require public notification and appeal process (now up to FOUR public appeal processes) | Completed prior to Gates | Completed prior to Gates | Per 8/10/21 meeting - okay to baseline - Trinh needs more info on extra ROW plan prep costs |  | In process of baselining - 1/27 Susan/Trinh - completing as test- will send draft doc to Amara 1/29 - Trinh to review with Larry & Pat first (baselining at $2M higher than currently appropriated - will need money moved over from master project) Holding meeting 2/3 to discuss and finalize. - Decided to wait until Amendment #5 is more finalized - and footprint identified (end of March?) Will meet again 3rd week of March. 4/1 Pat set up meeting with Rose/Joann 4/20/21 - delayed and moved to May 11th - Now looking for additional funding before baselining. Pat set up meeting 8/10/21
Wang | Wally | Road & Traffic | 1138330 | 164th Place SE and SE Covington Sawyer Rd Sightline Improvements | Yes | Funding Source: CWP High Collision Safety Lifetime Appropriation: $100,000 Q3 Performance: Admin Only planned to spend $20K on ROW. Staff are not supposed to charge to this project yet all costs of $24K are currently staff - I sent email to Pat 11/1/21 | Using IDE for baseline. No CN funding | Keep separate from 1134083, which is state grant funded. | Phase: Final Design started Dec 2021 Began work after CDR for 1134083 completed (WSDOT funded). Schedule Status: ROW pending. ROW request for the Johnson property pending. Sent ROE extension request for 2 ROEs in August. Issues: | Start Date: 5/28/2023 Contractor: TBD | Complete ROW Plan Jan 2022 60% Design to be completed March 2022 Needs new CDR? Separate from WSDOT funded CDR produced for 1134083?--sent 12/10/21 | 1 of 2 ROEs received 12/14/21 update - Follow up email sent to remaining property owner 12/10/21 | Dean 1/6/22- Starting to prepare Permitting plan and preapplication | Pat thinks not needed- will verify | Needs CDR ? Okay to use from previous project?- send request to PM? | 11/17/21 - Jun reached out for info on baseline process - I sent to him and cc'd Pat (reminded him we need CDR first - will need to do IDE form - No construction funding - baseline form being reviewed Dec 2021, meeting 2/3 to review |  | New project based on previous study. Needs new CDR and sponsor charter? because study was state funded and it needs to be separate | PM
Wang | Wally | Road & Traffic | 1140858 | 244th Ave NE Winter 2020 Storm/Slide Repair | Yes | Funding Source: Quick Response Lifetime Appropriation: $577,466 Q3 Performance: Schedule Delay -84% (Variance = - $124K) Consultant originally planned then changed to in house |  | FHWA Emergency Repair Concerns about meeting FHWA completion requirements - (currently risk (RED) of needing to return funds per Sarah 1/24/22 | Phase: Pre-Design. In House Design. Started Prelim design 12/16/21 Schedule Status: Ad date too aggressive? Jun says ok, accounts for 2 months of procurement review. Issues: | Start Date: 6/22/23 Ad date 4/2023 Project must be completed in 2023. CN must be oligated Sept 20,2022 - basically ready to go to ad | In Prism - CDR to be completed 12/15/21 1/14/22 - are we on track?--PM to revise Final Design to begin 2/28/22?? | RW Scoping/Liaison phase – • Received 1 of 1 ROE from property owner – sent to PM • Project Kick-Off meeting held 9.22.21 • Received draft schedule 9/20/2021 • Sent schedule comments to PM 9/23/2021 • Received revised copy of the draft schedule 10/4/21 – • More plan revisions in the works to reflect Permanent Easement to accommodate beaver as of 10/21/21 | Section 106 is completed per Tom Janine is EU lead | Completed prior to Gates | starting CDR Jan 2022 - need to update PRISM date | 11/17/21 - Jun reached out for info on baseline process - I sent to him and cc'd Pat (reminded him we need CDR first) |  | This Sponsor Charter was signed prior to implementing the gate process Design is obligated as of 9/1. Project must be completed in 2023 | PM
Wang | Wally | Road & Traffic | 1136234 | FPP Woodinville Duvall at 172nd Culvert Consultant Design | Yes | Funding Source: Fish Passage Program (now standalone 12/21) Lifetime Appropriation: $4.9M Q3 Performance: Invoice posting and schedule delays -123% (Variance = -$270K) 3 invoices just got approved ($44K) and may have another coming soon | $4.9M REET Funding opproved in 2nd omnibus 12/2021. Changes status to a standalone project |  | Phase: Preliminary Design (Consultant- KPFF) 60% Design Review in progress Jan 2022 Working on baseline Schedule Status: Goal to meet next summer CN with new funding Issues: 12/6 - PM duties moved to Jun in Traffic. | Start Date: 6/20/2022 Moving to 2023 per Project Mtg 1/11/22 - Jun to fill out DCM Contractor: TBD Per Ryan, will be 1 month full road closure. | Next Milestone: Complete 60% Design by Feb 2022. Complete 100% Design 4/2022 - Future amendment to keep consultant in loop about CN. | ROW Appraisal Phase: •RW Appraisal phase in process. - Meg started valuations, is waiting on updated ROW with before area for one parcel •Still bringing to 100% design - ROW date has not changed. •No design changes planned as of 8/10/21- moving forward with ROW acquisition. 11/16/21 - Rose signed/approved valuations->prepare offer packages. 12/14/21 Update: offer packages going out this week. Offer packages Sent 12/14/21 At Nov PM Meeting - Ryan says they are going for 2022 CN right now | Katie SEPA required No C&G so will not go through ART per Joann at ME mtg 10/20/21. Just need HPA and Corps permit. FISH WINDOW = 7/1/22 to 9/30/22 | Completed prior to Gates | Rose/Joann reviewed and approved as of 10/29/21 - Gate completed. Just have sig page, file too large. Susan to work w/Jon to get final CDR from consultant and gate docs ready | Need to baseline | 7/19/2021 New DCM requested to capture CN moving from 2022 to 2023. 1/24/22 - KPFF is working on revised sched | Consultant will be revising CDR within the next week per Jon C 6/28 - marked as complete in PRISM Harriette sending envelope out 1/11/21 (2 -/1/21 - in review with Rose/Joann) 2/8 Rose needed cost estimate breakdown - Jon to forward - done (2/17 - in Joann's to do) - 3/8 update - Rose/Joann sent comments to PM to make revisions (3/16 - revisions still be worked on. 3/22 - revisions still being working on 4/12 - still working ) 4/19 - with consultant, expect to be resubmitted this week - 6/2/21 Jon thinks it's with Rose/Joann to sign - 6/7 Joann still working on 6/7/21 - In Joann's queue - still needs changes, questions answered as of 6/23/21 per Joann - Ryan needs to forward info to Ryan - Pat is tracking (We do need guidance from Joann/Rose on how to move forward before amendment can be approved and invoices paid) Trigger: schedule/budget 1/25/21 Harriette sending out for signatures, 1/29/21 - Pat sent comments to Ryan for changes (May need to refill out - PDO needs copy) . 2/2/21 - Pat sent PDO copy (Allison sent revised form to Ryan) 3/8 - Ryan sent email asking for update - SO replied asking if revision had been completed per Pat's email (In ME meeting, Pat said she needs to call and talk to Jon C about it) - 3/8, Ryan replied to Pat needing clarification on why Pat modified/increased the design budget by $20K (Susan sent status update inquiry to Pat/Ryan on 3/17/21 (Ryan and Pat are meeting 3/18) - 3/25/21 emailed Pat/Ryan asking for update, Pat replied that they are working on finalizing and will send out revision. 4/12/21 - still working on per Pat) - Jun sent revised form to Pat for review on 5/5/21, Jun sent revised form to Harriette to send out for DocuSign 5/17/21. completed 5/27/21 - distributed?? 6/15 now ON HOLD?? 6/21/21 - Rose wants to wait until outcome from meeting discussing design and how far we want to go with the consultant - will know more 6/29 meeting - then Pat will be able to go ahead with giving approval to Janel for moving forward w/the amendment. 7/7/21 ME Meeting - agreed that Harriette will find and resend (Allison sent Cover Sheet to Ryan to complete 7/7/21) - 7/9 Allison to check with Ryan (Jun can sign) 7/12/21 Joann wants to run by Ruth and Tricia before signing so they are aware contract change is coming - Joann okay'd to move forward with consultant amendment per 7/19 ME huddle - SIGNED 7/19/21 | ME
| Wally | Road & Traffic | 1142035 | RSD ECE Countywide Unincorporated King County ADA Ramps | TBD | Funding Source: Grant Lifetime Approrpriation: 1.5M |  | Need more info. Got heads up from Pat | Need more info. Got heads up from Pat |  |  |  |  | 12/6 - Pat will need to create sponsor charter |  |  |  |  | Pat
Zhen | Wally | Road & Traffic | 1139146 | RSD Rainier Ave S and Lakeridge Drive Intersection Improvement | Start Q2 2022? | Funding Source: Lifetime Appropriation: $400K EAC = $1.4M Q3 Performance: Schedule Delay -92% (Variance - $65K) Delays due to ROE. Will not have consultant on board until end of Q4 at the earliest (originally thought they would design in house) |  |  | Phase: Planning Consultant Design-Perteet (originally thought it would be in house); consultant design for prelim Needs Project Sponsor charter completed Schedule Status: Plan to begin desgin Q2 2022 Issues: Project will be high impact to residences nearby; community outreach pertinent. | Start Date: May 2023 No CN funding | Kickoff meeting scheduled 1/27/22 Final CDR May 2022 Final Design complete Dec 2022 | Leslie/Maura lead Construction is dependant upon ROW needs. Currently May 2023 - could be pushed out From kickoff meeting 1/27/22: Field meeting with prop owners on one prop scheduled 2/24/22 |  | 1/10/22 - Pat preparing Charter Kickoff meeting scheduled 1/27/22 |  |  |  | 3/25/21 per Pat, in queue. Planning on starting work 2nd Q (consulant hired December 2021) | Pat
Jose | Larry | Bridges and Structures | Operating | Berrydale OX Crossing | No Operating Budget | Funding Source: CWP Bridge Safety Program Lifetime Appropriation: $0 Q3 Performance: Staff time is being charged to operations for the CDR | All charges go to operating at this time | Federal Grant for alternative study only | Phase: Henry Jin and team reviewing CDR as of 10/11. Anticipate it will be ready for review by end of 2021 Schedule Status: Issues: | Start Date: |  |  |  |  | Completing CDR. Anticipate being ready by end of 2021 (meeting w/Rose 11/16 for a briefing) |  |  | Not in PRISM/CIP. Using operating budget for study/CDR | ME
Jin | Larry | Bridges and Structures | TBD | Duvall Slough Bridge #1136B Re-Deck Project | Start March 2022 | Funding Source: subproject under CWP Bridge Priority Maintenance (May move to standalone 23/24 budget) Lifetime Appropriation: Q Performance: | Preliminary Budget: $1,987,800 per Charter | Fed Bridge Program Grant July 2021 (BPM) $1,719,447 Roads match $268K 100% funding if CN authorized by 12/2024 obligating PE feb 2022 per Sarah | Phase: Planning Sponsor Charter signed 10/7/21 Preliminary Design scheduled to begin 3/2022 12/13 - Currently working on getting PE obligated so that they can begin design (per Bridge Unit meeting on 12/13/21) Schedule Status: Issues: | Start Date: Oct 2023 per Charter (100% funding if CN by 2024) |  |  |  | Completed 10/7/21 |  |  |  | Received $1,987,800 in Federal Highway Bridge Program funding for Design and Construction. Design is anticipated to start August 2022, CN in 2024 (will be under BPM program? - or will need to work w/PSB if standalone) 8/23 Leave in BPM - move to standalone next budget cycle per Rose
Jose | Larry | Bridges and Structures | WLRD | North Fork Bridge #122I Feasibility Study | No | Funding Source: FCD Lifetime Appropriation: Q Performance: |  | 10/29/21 - Potential for HMA grant opportunity per Jessy 11/22-submitted pre-application. Want to move forward to final app due in April - still TBD , meeting w/consultant | Phase: Feasability Study being done by TranTech. NTP issued April 2021 Status briefing meeting scheduled w/Rose 11/16/21 Schedule Status: Issues: | Start Date: | Feasability study in progress and anticipated to be complete Feb 2022 per Jessy email 1/18/22 |  |  | Completed prior to Gates | n/a? | n/a |  | Roads signed off, Pat sent to FCD as of 2/1/21 WLRD Project #1131340 FCD returned to Roads w/ signatures 3/5
Mott | Wally | Road & Traffic | 1142993 | 2022 Pavement Preservation | Yes New | Funding Source: CWP Roadway Preservation Lifetime Appropriation: $2M Qx Performance: | Project set up and money transferred 1/6/22 |  | Phase: Advertise in Spring 2022 Schedule Status: Issues: | Start Date: Anticipate Summer 2022 Contractor: | Linda to update in PRISM |  |  | n/a | n/a | n/a | n/a

## Drainage
Updates from 1/5/22 Meeting
Update from January 25, 2022
Drainage Update Meeting Agenda (add bold when updating)
Current Drainage Construction Projects:
  75th Avenue SW @ #25613 Phase I (#5-46835) – construct a new underground drainage collection system. Construction started last Tuesday January 17th. Construction is at the SW 257th Street intersection. Curb inlet and DI pipe project over existing utility lines. Potholing with vactor truck ahead of construction. Working with utility companies on needed service line relocations. 800 feet project length. The project is on Maury Island. Informational project flyer was sent out to Gold Beach area residents recently.
Recent Completed Drainage Construction Projects:
  SE 165th Street @ #16316 (#3-142036) – construction occurred on January 10-13, 2022.
  Snow response from Christmas through Friday January 7, 2022.
  Renton Avenue South @ 74th Avenue South (#3-45723, #3-2228) – project constructed in December 2021.
Upcoming Drainage Construction Projects with Signed Plans Ready for Construction:
  80th Avenue South B/T South 114th Street and South 113th Street (#3-148801) – replace deteriorated pipe with steel plate over it in Skyway. One block of pipe and CB replacement. Utility pole hold may be required at South 114th Street. Plans signed on December 10, 2021.
  SE 145th Street @ 167th Avenue SE (#3-149891) – replace rusted out non-functioning underground drainage system. Drainage crew potholed underground utility line locations on SE 145th Street in fall 2021. Pothole results have been recently evaluated by design staff and revisions are being made to the plans. Plans were signed on October 15, 2021.
  Preston Fall City Road SE 1,000 FT SW of D/W #7831 (#2-135814). Pipe end repair and CB replacement with cross culvert replacement. Underground phone line on west side of road adjacent to the CB replacement. Plans signed on February 8, 2021. Need to post the construction timeline on the Road Alert.
  SE 322nd Street @ 194th Avenue SE (#4-46516, #4-2131) – replace deteriorated cross culvert and remove two abandoned cross culverts. Need to construct when no flow from Lake Morton. Plans signed on September 3, 2021.
  93rd Avenue SW @ #16402 (#5-159949) – replace cross culvert with collapsed concrete pipe section near the outlet on Vashon Island. Two day construction to occur in spring 2022 when dryer. Plans signed on September 3, 2021.
Drainage Projects being Designed:
  SW 257th Street @ 76th Avenue SW (#5-164602) – install an underground pipe system to drain a low ponded road area. Adjacent to the 75th Avenue SW project. Drainage crew may construct this project in conjunction with 75th Avenue SW Phase I soon. Plans are being finalized presently.
  75th Avenue SW @ #25613 Phase II (#5-46835) – construct a new underground drainage conveyance system draining to Puget Sound. Construction on the entrance road to the Gold Beach neighborhood. DI pipe has been ordered. Plans are being finalized and will be signed soon.
  SW 256th Street @ 79th Avenue SW (#5-112742) – install system to drain ponded stormwater area in the ninety degree road curve. Near the 75th Avenue SW project
  SW 110th Place @ #2835 (#3-45724, #3-2229) – add a CB and conveyance pipe in cul-de-sac to solve a drainage collection problem. Plans are finalized and will be signed soon.
  Avondale Road NE @ #15926 (#1-396756) – school pathway project at Cottage Lake Elementary School. Separate funding for construction. April 2022 construction during spring break week.
  Vashon Highway SW @ #16624 (#5-63552) – replace three CB’s and connecting pipes.
  177th Place SE @ SE Lake Holm Road (#4-154514) – add an underground drainage collection system. Plans are in the final design phase.
  80th Avenue South @ #13444 (#3-151429) – add a drainage collection system. Project design started – design scope of work being confirmed.
  SE 157th Street @ #25803 (#3-157994) – install a new drainage conveyance system. Draft plans have been completed.
  15th Avenue SW @ SW 100th Street (#3-147728) – replace catch basins in White Center.
  SE 129th Street @ #47018 (#2-151748) – resolve a shoulder drainage ponding and maintenance problem in a residential neighborhood south of the Mt. Si Road near North Bend.
  SE Reinig Road @ 396th Avenue SE (#2- 53206) – replace inlet side CB and cross culvert. Heritage tree corridor – inlet side CB to be shifted away from large tree. Plans are being revised. Met on 9/27/21 on the design and a field meeting occurred on Wednesday October 6th. Flood certification required.
  SE Reinig Road, 300 Feet West of 428th Avenue SE (#2- 55122) – replace cross culvert. Plans being finalized. Flood certification may be required.
  180th Avenue SE @ #13825 (#3-147138) – install a new underground drainage collection system and replace cross culvert. Plans are waiting to be finalized.
  SW Ellisport Road, 330 Feet West of #8522 (#5-399480) – seepage out of pavement – uphill and adjacent to previously fixed area in 2016. Seepage active in August 2021 but not now in wet December. Construction to occur in the future when seepage is active.
New Topics:
Slide Repair Projects
  Burma Road SW @ #13311 Slide Repair project (#7-401552, Oracle#1138229)
  Vashon Highway SW @ #29831 Slide Repair Project (#7-401609, Oracle #1138216)
  Cunliffe Road Pavement-Slope Failure near Winghaven Park (Oracle #1138230)
  Middle Fork Road @ 9.7 miles
  NE Old Cascade Highway (Oracle #1138237)
  Monster Road (Oracle #1138217)

## Traffic Safety Report
Need to add Overhead Flasher Upgrade to LED Stop Signs - federal grant funded

## Bridge Priority Maintenance
Updates from Jan 2022 PM Meeting
From Larry on 10/20 in response to Q3 results:
So we have a lot of dynamic things happening here: Here is a suggested explanation:
Contractor bids for the Judd Creek Bridge repair project came in under the engineers estimate so we were able to complete the project below the estimated amount.
Two planned 2021 deck repair projects (Whitney Bridge 3025 epoxy overlay and Green River Bridge 3216 epoxy seal) got delayed until 2022 due to supply chain disruptions for the raw materials (epoxy).
A number of repair projects that were planned for Q2 (Cedar Mountain Bridge 3165 abutment repair) and Q3 (Soos Creek Bridge 3109 approach repair, Rutherford Slough 920a approach repair, and North Fork Bridge 122I expansion joint repair) were moved to Q4. The charges for these have not fully posted.
Two recent urgent repair projects (Issaquah Creek 83D scour repair and Boise Creek 3052 spall repair) were recently completed but charges have not yet posted.
Two other planned repair projects for 2021 were removed from this year’s work.
Novelty Bridge 404b approach repair - This was planned to be funded out of BPM but ended up getting charged to a different maintenance budget.
Smith Parker Bridge 615a paint repair – This was removed from BPM. During UBIT inspection the paint loss was determined to be too severe for spot painting repairs, the bridge was then moved onto the priority list for a full repainting.
Pat - There is a lot here because of the dynamic nature of BPM, feel free to clean up if necessary.
Thank you,
Larry

## CN Ad Sched
2022/23/24 CIP Coordination and Ad Schedule
Project Name | Project Number | Contract Number | Fed. Aid | 30% Complete |  | 60% Complete |  | 90% Complete |  | Advertisement Date |  | PDO Notes 1/20/2022 | Impl. Phase Forecast | Managing Engineer | Project Manager | Notes:
|  |  |  | Forecast | Actual | Forecast | Actual | Forecast | Actual | Forecast | Actual
2021 ADVERTISEMENTS
NE Stillwater Hill Road/Kelly Road | 1129714 |  |  | 2019-05-29 | 2019-05-29 | 2019-08-15 | 2019-08-15 | 2019-10-10 | 2019-10-10 | 2021-03-09 | 2021-03-25 | Construction w/Interwest began 7/19/21 Substantial Completion reached 10/20/21 | 3912622 | Archuleta | Linders
S 277th St @ Mullen Slough - Bridge Replacement | 1136001 |  |  | 2020-02-12 | 2020-02-25 | 2020-05-18 | 2020-05-18 | 2020-08-20 | 2020-08-20 | 2021-04-19 | 2021-04-26 | Construction w/Active Construction started 7/21/21 | 1750730 | Jaramillo | Premachandra
2021 Countywide Pavement Preservation | 1141044 |  |  | 2021-04-19: 2021-04-29; 2021-04-26: 2021-05-03 | Construction w/Lakeside Industries started 7/12/21 |  | Jaramillo | Moore
Coal Creek Bridge 3035A Replacement | 1135997 |  | Yes | 2019-07-15 | 2019-07-15 | 2020-03-25 | 2020-03-25 | 2020-09-14 | 2020-09-14 | 2021-04-29 | 2021-05-13 | Provisional NTP w/Active Construction executed 7/30/21 Construction to be done in 2 stages (temp bridge), anticipated to complete in 2022 Federally funded | 4257794 | Jaramillo | Martin
2020 Countywide HFST | 1137862 |  | Yes | 2020-07-09 | 2020-07-10 | 2020-09-01 | 2020-09-01 | 2020-10-13 | 2020-10-13 | 2021-04-29 | 2021-06-14 | Contract Executed 8/26/21: American Civil Constructors West Coast (+14%) 11/18 - Per Jon L CN most likely will not start until 2022 Planning Pavement repair to start August 2021 - carryover HFST to 2022 HSIP Federal Grant - 16 locations | 3160846 | Archuleta | Linders
Traffic Illumination?? | [11 empty] | Linda Mott's Project, needs project number and budget transfer
2022 ADVERTISEMENTS
2020 Roadway Lighting | 1141401 |  |  | 2021-04-19: TBD | Part of Traffic Safety Program Service request sent to Procurement - No ad date set as of 1/20/22 (okay to delay to winter per Aileen) | 260912 | Archuleta | Mott
218th Ave SE Roadway Preservation | 1136086 |  | Yes | 2020-02-20 | 2020-02-20 | 2020-09-17 | 2020-09-17 | 2021-03-04 |  | 2/1/22 TBD |  | Bid Package/Procurement- After obligation rec'd -> approx 8 weeks out for ad date WSDOT reviewed PS&E package & corrections sent back to them 12/20/21 $2.6M CN grant (PSRC) - Baselined 9/24/21 Grant will need to be obligated by Feb 2022 | 5143180 | Archuleta | Linders
Upper Tokul Creek Bridge 271B Replacement | 1135999 |  |  | 2020-06-30 | 2020-05-28 | 2020-12-31 |  | 2021-06-30 |  | 2022-02-28 |  | 100% Design plans signed 1/6/22 - Working on spec package (Jerry sending to PM 1/20/22 for final review) ROW in negotiations - schedule at risk - critical path Bridge Safety Program - 2022 CN | 3543272 | Jaramillo | Martin (Premachandra)
2019 - 2020 Guardrail Preservation - Tier 3 | 1141111 |  |  | 2021-04-19: 2022-03-10 | Ad date moved to October November January March Jerry rec'd final docs from Linda 1/18/22 Joann signing Mylars by end of Jan 2022 Construction to start April 2022 | 1400000 | Archuleta | Mott
S 360th St - School Pathway and High Collision Sightline Improvement | 1136580 |  |  | 2019-08-01 | 2019-08-02 | 2020-07-07 | 2020-07-15 | 2020-10-13 | 2020-10-15 | 3/18/22 |  | Current Status on final plans (Jerry still needs) and specs (easy update) Moved out to 2022 per 7/12/21 Ad meeting - winterize project School Pathway combined w/Sightline project | 213102 | Archuleta | Karinen | w/ 1131157
| 1131157 |  |  | 2020-02-25: 2019-02-28; 2020-05-18: 2020-07-15; 2020-08-20: 2020-10-13; 2020-08-20: 2020-10-15 |  | 130752 |  |  | w/ 1136580
Redmond Ridge Dr @ NE Alder Crest Dr | 1134081 |  |  | 2019-06-19 | 2019-06-19 | 2019-08-29 | 2019-08-29 | 2019-11-06 | 2019-11-06 | 4/1/22 |  | 100% PS&E and TIR to be completed and signed Jan 2022 1/20/22 - Jerry needs addtl info from PM 1/11/22 - ROW Consultant preparing offers for review $800K State grant (Rec'd $300k in 2nd Omnibus) Subject to Day Labor Restrictions/Requirements | 1271845 | Archuleta | Karinen
Renton Ave Phase III - Sidewalks | 1129599 |  | Yes | 2018-11-15 | 2018-11-15 | 2019-03-05 | 2019-03-05 | 2019-05-23 | 2019-05-23 | 2022-04-12 |  | 100% Design in progress- to be completed Nov 2021 Jan 2022 Prelim Spec Package sent to Jerry 1/10/22 1/11/22 -ROW in negotiations (SPU needs ROW plan change) 1/6/22 - Permitting reviewing C&G Rec'd $2M TIB grant for CN (no obligation date - okay if extended) Rec'd addtl $300K in REET funding | 2115272 | Archuleta | Linders | State funding
380th Place @ SR 164 | 1130710 |  |  | 2021-07-16 | 2020-07-16 | 2021-01-15 |  | 2021-03-26 |  | TBD |  | 90% Design in progress Jan 2022 - Design on hold- ROW delays and engineer reassignment to Old Cascade TBD (by end of Jan) whether moved to Maintenance Crews in 2022, or Contractor in 2023 | 498058 | Cassidy | Lyou | Maintenance Construction?
2022 Countywide Pavement Preservation | 1142993 |  |  | 2021-04-19: Spring 2022? | Linda reported that plans are on schedule for spring advertisement at Jan PM meeting |  | Archuleta | Mott
SE Kent-Kangley at Landsburg (interim fix) | 1141625 |  |  | 2020-05-18: Archuleta; 2021-04-19: 2022-05-03 | 100% Design to be completed Feb 2022. Prelim Spec Package sent to Jerry 1/10/22 1/11/22 - ROW appraisal package almost complete Construction scheduled July 2022 | 378641 | Archuleta | Linders
Old Cascade Hwy (Miller Riv Br - West) | 1129595/96 |  | Yes | 2017-10-30 | 2017-10-30 | 2018-01-26 | 2018-03-30 | 2020-12-18 |  | 5/5/22 |  | 90% Design Review meeting scheduled 1/27/22 Multi-discipline project team meeting regularily to help meet CN 2022 schedule FEMA grant - rec'd verbal approval for 2022 extension Will need to submit 90% plans to EMD (FEMA) after permits secured | 530000 | Cassidy | Lyou | w/ 1129596
Old Cascade Hwy (Miller Riv Br - East) | 1129596 |  | Yes | 2017-10-30 | 2017-10-30 | 2018-01-26 | 2018-03-30 | 2020-12-18 |  | 3/31/22 5/5/22 |  |  | 1780000 | Cassidy | Lyou | w/ 1129595
NE Woodinvile-Duvall Rd at NE 172nd St - Culvert | 1136234 |  |  | 2020-02-12: 2021-01-15; 2020-05-18: 2021-05-28; 2020-08-20: 2021-08-06; 2021-04-19: AD TBD Oct? CN 2023 | 60% Design in Progress 1/11/22 - Multi-discipline project team met and approved CN move to 2023 Wang to complete DCM Received $4.9 Reet Funding/2nd Omnibus | 3969320 | Archuleta | Wang | Construction 2023?
Fifteen Mile Creek Br no. 493C Replacement | 1138914 |  | Yes | 2020-02-12: 2021-07-15; 2020-05-18: 2021-07-15; 2020-08-20: 2022-03-07; 2021-04-19: 2022-11-15 | 90% Design coordination mtg held Sept 2021 - CONSULTANT design - on track ROW obligated 9/3/21 100% CN obligation if by 9/21/22 | 4207749 | Jaramillo | Jose
2023 ADVERTISEMENTS
S Langston Rd at 125th Ave S - Drainage | 1139716 |  |  | 2020-05-18: Cassidy; 2020-05-18: Cassidy; 2020-08-20: Mitchell; 2021-04-19: 2023-01-30 | Design Consultant - Four Elements design to start in Jan 2022 - delays may move out CN sched? FCD Project - will need approvals - unrealistic schedule No fish window (can be done in winter per Joann) Could possibly be in-house? - Joann following up with Jon 10/2021 |  | Cassidy | Mitchell | Maintenance Construction?
Ames Lake Trestle Bridge Replacement | 1135998 |  |  | 2020-10-15 | 2020-10-15 | 2021-06-09 |  | 2022-02-03 |  | 3/3/23 |  | 90% Design in progress to be completed Feb March 2022 90% Design Review meeting scheduled 2/17/22 $2700K CRAB, did not receive Fed grant BSP - CN 2023 | 7,603,090 8,410,000 | Jaramillo | Truong
Covington-Sawyer Rd Sightline Imp. | 1138330 |  |  | 2021-04-19: 2023-03-04 | 60% Design in Progress - expected to complete March 2022 Construction 2023 - NO CN funding per Pat as of 1/20/22 | 507514 | Archuleta | Wang
2023 Countywide Pavement Preservation | [11 empty] | placeholder |  | Archuleta | Mott
NE Tolt Hill Bridge Approach Repair | 1141001 |  |  | 2021-04-19: 2023-03-27 |  |  |  |  | Set up as "in house" crews in PRISM - to be corrected
244th Ave NE Emergency Roadway Repair | 1140858 |  | Yes | 2021-04-19: 2023-04-20 | Started Prelim Design Dec 2021 - CDR anticipated to be completed Dec 2021 - now Feb?? Concerns about schedule - enough time for FHWA paperwork/requirements FHWA Emergency Repair (11/15/21 - Sarah says grant risk is "yellow") |  | Archuleta | Wang
S 360th St & Military Rd S - Roundabout | 1131235 |  | Yes | 2020-09-23 | 2020-09-23 | 2021-02-23 |  | 2021-07-01 |  | 2023-06-27 |  | 90% Design completed September November December January 2022 Received $2.7M PSRC grant for 2023 CN (obligate by 6/1/23) ROW issues okay now that ROW plans sent to team Sept 2021 | 2,929,670 3,200,495 | Archuleta | Karinen
Boise X Connection Br. No 3055A Replacement | 1138913 |  | Yes | 2020-02-12: 2021-07-01; 2020-05-18: 2021-11-01; 2020-08-20: 2022-03-01; 2021-04-19: 2023-10-17 | 30% Design to be completed June 2021 3/2022 - IN HOUSE design CDR completed 12/2021 Moved CN year from 2023 to 2024 | 1898612 | Jaramillo | Jin
Baring Bridge No. 509A Replacement | 1136000 |  |  | 2019-07-16 | 2019-07-16 | 2020-12-25 | 2020-12-25 | 2022-06-06 |  | 2023-11-16 |  | 90% Design to start October. Anticipated to be completed June 2022 - Delays Not applying for Fed Grant at this time Requesting $1.6M in 2nd Omnibus | 10,327,389 12,341,456 | Jaramillo | Truong
2024 ADVERTISEMENTS
SE Petrovitsky Rd & 134th Ave SE | 1131526 |  |  | 2018-08-01 | 2018-08-02 | 2019-06-15 | 2019-08-16 | 2019-12-31 | 2020-01-13 | 2024-03-15 |  | 90% Design completed - Consultant Contract on hold, pending amendment Pursuing BRIC grant funding - 1/5/22 update - not pursing, will apply next round NO Construction Funding | 4800000 | Cassidy | Mitchell
Issaquah Hobart @ May Valley Rd Roundabout/Intersection | 1129598 |  |  | 2021-04-19: 2024 | Design Consultant expected to be onboarding in April 2022 No Construction Funding |  | LeSmith Archuletta | Sahagun Wang | Needs update (Const Ad before 90%?)
16th Ave SW Pedestrian Improvements | 1138918 |  | Yes | 2020-02-12: 2021-05-31; 2020-05-18: 2021-07-30; 2020-08-20: 2021-10-01; 2021-04-19: 2024 | 60% Design in progress - utilizing consultant to review alternatives ROW challenges -Leslie D working on research May return Fed funds to make ROW process easier? Ad date moved out to 2023 - moved to 2024 - need to confirm | 804032 | Archuleta | Mott | No ad date in Prism
2024 Countywide Pavement Preservation | TBD |  |  | 2018-08-01 | 2018-08-02 | 2019-06-15 | 2019-08-16 | 2019-12-31 | 2020-01-13 |  |  | Placeholder |  | Archuleta | Mott

## Gate Follow Up
Current gates in progress as of 1/19/22
CDR (Gate 2)
In Final Review (what is current status?)
  1138947 FPP 284th Ave SE – in review w/Rose&Joann – Joann sent to Lica for edits – then send to Michelle (1/24/22 - Lica making edits, Rose want to review again)
  1138339 FCD S 106th (18th Ave S) – in review w/Rose&Joann – should be done today -1/24/22 edits sent back to Dieu
  1136231 FPP 185th at 179th – in review w/Rose&Joann? – Rose/Joann discussing. Will be signed by end of next week. -1/24/22-still reviewing, should be done this week 1/26-Rose received final revision and will review 1/26/22 to move forward for signatures
    (Consultant contract extension is based on CDR getting signed off in Jan 2022) - Rose and Joann are aware
Coming up for review – send PM updated process/reminder email
  1136238 NE 24th Street Culvert – Needs CN estimate to finish (beyond 90% design) – Terry working on it
  1140858 244th Ave NE – scheduled to complete CDR Jan 2022?
Baseline (Gate 3)
Started review process w/Pat- (current status? Need reminder email sent to PM?)
  1127589 NE 165th St Flood Reduction – In 99% Design - Martin finalizing with 2024 CN
  1131235 S 360 St & Military Roundabout – In 90% Design, Pat coordinating with PM and Aileen
  1136232 FPP Bear Creek Projects – In 99% Design - Mark working with Pat - Budget has now been adjusted, can finalize - would be NO CN funding form
  1136000 Baring Bridge – In 90% Design – Trinh waiting for info on addtl ROW costs -amendment was signed today - CN moving out 1 to 2 years
In progress – send PM updated process/reminder email
  1136419 FPP 432nd St Culvert - In 99% Design, Need CN estimate to complete CDR
  1136234 Woodinville Duvall at 172nd Culvert- In 60% Design – New PM Wang
    Complete after DCM moving CN from 22 to 23 is signed?
Design Change Management Forms
1130710 SE380th Culvert – CN moving to 2023?
  ROW delays and design on hold to work on Old Cascade per 1/13/22 team meeting.
  Lyou project. Jon/Ryan to fill out? PDO to help set up?
  TBD – can construct in 2022 if done in house – can ROW be completed? - awaiting decision from Maintenance team (still TBD as of 1/24/22)
1136234 Woodinville Duvall at 172nd Culvert – to capture CN move from 22 to 23
  In progress. Wang was sent new process email - follow up 1/24/22 - Jun is getting updated schedule from KPFF

## ART priority list
Joann shared 10/20/21 -
*only includes projects that need C&G permits (i.e. Woodinville FPP not needed)
ART Monthly Meeting – November 1, 2021
Attendees: Alisa, Ron, Ramon, Ty, Lindsey, Jon, Stephanie, Ty, José, Francisco, Mohamed
2022 workplan is complete, with the exception of a few chances that need to be made.
Given Alisa is leaving, she included a transition plan in this month’s MBR. Her and Ty will be finding someone at Permitting that can help the ART team with moving submittals through the queue.
  Project managers may need to take a more active role in reaching out to reviewers in the interim.
  Alisa will be sending out intro emails
  Priority List/Big issues should got to Ty and Mark
  Recruitment for replacement has been posted
Went over this month’s activities
  Note when reviewing schedule – ART has struggled with scheduling time for resubmittals. Alisa is hoping to add some time in 2022 for this. She included a new color (see colo0r code in the attachment) for resubmittals in 2022 and a new “resubmittal window” which is a way to build this time into the schedule. It is not necessary to get your resubmittal in during this window – it is just a method of adding this time in the schedule. This will hopefully help maintain some additional stability into the schedule. She would love to hear suggestions on how to handle this.
    Jon asked if the reasons re-submittals have been consistent? Alisa thinks it is usually due to non-compliance to one of the things in the core requirements (sometimes minor, sometimes not). Ramon noted that it is usually consistency that he looks at (with stormwater and road standards requirements).
Some discussion about resource sharing at Permitting/ART. This was a re-hash of some previous conversations.

## Data Validation
Data Validation
PM
ME
Harriette
Pat
Rose/Joann