## ag-grid
PROJECT |  |  |  | TEAM | DETAILS | SCHEDULE (Current) | [7 empty] | SCHEDULE (Performance/Reference) | [7 empty] | REPORTING (Baseline)
Phase | Number | Name | Program | Project Manager | Portfolio Category | Gate 1 | Gate 2 | Gate 3 | 30% Design | 60% Design | 90% Design | NTP Issued/Start Con | Project Substantial Completion | Gate 1 (Performance/Reference) | Gate 2 (Performance/Reference) | Gate 3 (Performance/Reference) | 30% Design (Performance/Reference) | 60% Design (Performance/Reference) | 90% Design (Performance/Reference) | NTP Issued/Start Con (Performance/Reference) | Project Substantial Completion (Performance/Reference) | Schedule Variance
PLANNING | 1026798 | RSD EMRGNT NEED-EXISTING PRJ |  | Mitchell, Patricia | Quick Response | [7 empty] | 2024-12-14 08:00
PLANNING | 1026799 | RSD CIP GRANT CONTIGENCY |  | Mitchell, Patricia | Contingencies
OPERATIONS | 1026800 | RSD CAP PROJ O S FUND 3860 |  | Mitchell, Patricia | Administrative
PREDESIGN | 1027163 | RSD QUICK RESPONSE | RSD QUICK RESPONSE | Mitchell, Patricia | Contingencies
IMPLEMENT | 1111819 | RSD C W DRAINAGE PRESERVATION | RSD C W DRAINAGE PRESERVATION | Shular, Ryan | Drainage
OPERATIONS | 1114792 | RSD ROADS-COUNTY ROAD CONST |  | Mitchell, Patricia | Administrative
CLOSEOUT | 1116885 | RSD WOODINVILLE DUVALL ITS |  | McManus, Aileen | Traffic Control | [7 empty] | 2017-05-04 07:00
CLOSEOUT | 1124986 | RSD CW HRRRP | RSD CW HRRRP |  | Roadway
IMPLEMENT | 1125758 | RSD W SNOQ VLY RD/NE124-W/D RD |  | Shular, Ryan | Roadway | 2018-11-08 08:00 | 2019-05-14 07:00 |  | 2019-01-18 08:00 | 2019-03-01 08:00 | 2019-03-25 07:00 | 2020-09-01 07:00 | 2020-10-01 07:00
DESIGN | 1127271 | RSD PRESTON MAINT FACILITY |  | Sugui, Rey | Maintenance Facilities |  |  | 2022-12-31 08:00 | 2022-12-31 08:00 | [6 empty] | 2020-01-31 08:00 | 2020-01-31 08:00
IMPLEMENT | 1127273 | RSD FAILED ENV & HVAC REHAB |  | Knauer, Jennifer | Maintenance Facilities | 2016-11-03 07:00 | 2017-01-10 08:00 | 2017-04-20 07:00 | 2017-03-31 07:00 | 2017-09-16 07:00 | 2018-08-22 07:00 | 2020-02-16 08:00 | 2022-12-30 08:00 | 2016-11-03 07:00 | 2017-01-10 08:00 | 2017-04-20 07:00 | 2017-03-31 07:00 | 2017-09-16 07:00 | 2018-08-22 07:00 | 2020-02-16 08:00 | 2021-12-31 08:00 | 0%
DESIGN | 1127589 | RSD 165 ST FLD RSK RDUCTN | RSD C W DRAINAGE PRESERVATION | Karinen, Martin | Drainage | 2016-03-03 08:00 | 2016-08-05 07:00 | 2022-02-28 08:00 | 2016-08-05 07:00 | 2016-10-27 07:00 | 2017-04-14 07:00 |  | 2024-10-15 07:00 | 2016-03-03 08:00 | 2016-08-05 07:00 | 2016-08-05 07:00 | 2016-08-05 07:00 | 2016-10-27 07:00 | 2017-04-14 07:00 |  | 2021-10-03 07:00
CLOSEOUT | 1127590 | RSD 212 AV SE FLD RSK RDUCTN | RSD C W DRAINAGE PRESERVATION | Bleasdale, Don | Drainage | 2016-03-02 08:00 | 2016-01-04 08:00 |  | 2016-01-04 08:00 |  |  |  | 2018-11-15 08:00
IMPLEMENT | 1129582 | RSD EMERGENT NEED 3855 |  | Foote, Mark | Administrative
IMPLEMENT | 1129583 | RSD GRANT CONTINGENCY 3855 |  | Foote, Mark | Administrative | [7 empty] | 2020-12-31 08:00
IMPLEMENT | 1129584 | RSD CWP QUICK RESPONSE | RSD CWP QUICK RESPONSE | Mitchell, Patricia | Roadside | [7 empty] | 2020-12-31 08:00 | [7 empty] | 2020-12-31 08:00
IMPLEMENT | 1129585 | RSD CWP ROADWAY PRESERVATION | RSD CWP ROADWAY PRESERVATION | Moore, Paul | Roadway
IMPLEMENT | 1129586 | RSD CWP DRAINAGE PRESERVATION | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage |  |  | 2019-01-08 08:00 | 2019-01-08 08:00 |  |  |  | 2018-12-31 08:00 |  |  | 2019-01-08 08:00 | 2019-01-08 08:00 |  |  |  | 2018-12-31 08:00
PLANNING | 1129587 | RSD CWP GUARDRAIL PRESERVATION | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside | 2017-08-02 07:00 | 2017-08-02 07:00 | [6 empty] | 2017-08-02 07:00 | 2017-08-02 07:00
IMPLEMENT | 1129588 | RSD CWP BRIDGE PRIORITY MAINT | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures | [7 empty] | 2020-12-31 08:00 |  |  | 2020-06-09 07:00 | 2020-07-07 07:00 |  |  |  | 2020-12-31 08:00
IMPLEMENT | 1129590 | RSD CWP HIGH COLLISION SAFETY | RSD CWP HIGH COLLISION SAFETY | Mott, Linda | Traffic Control |  |  |  | 2018-11-15 08:00 | [7 empty] | 2018-11-15 08:00
IMPLEMENT | 1129591 | RSD CWP SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | Hafele, Brendan | Traffic Control |  |  |  | 2018-03-01 08:00 |  |  |  | 2020-12-31 08:00 |  |  |  | 2018-03-01 08:00 |  |  |  | 2020-12-31 08:00
IMPLEMENT | 1129592 | RSD EMERGENT NEED 3865 |  | Foote, Mark | Administrative
IMPLEMENT | 1129593 | RSD GRANT CONTINGENCY 3865 |  | Foote, Mark | Administrative | [7 empty] | 2020-12-31 08:00
PLANNING | 1129594 | RSD CWP GUARDRAIL CONSTRUCTION | RSD CWP GUARDRAIL CONSTRUCTION | Mott, Linda | Roadside | 2018-01-30 08:00 | 2017-05-01 07:00 | 2017-06-30 07:00 | 2017-06-30 07:00 |  |  |  |  | 2018-01-30 08:00 | 2017-05-01 07:00 | 2017-06-30 07:00 | 2017-06-30 07:00
DESIGN | 1129595 | RSD OLD CASCADE/MILLER BR WEST |  | Lyou, John | Bridges & Structures | 2017-04-24 07:00 | 2017-08-30 07:00 | 2017-12-19 08:00 | 2017-10-30 07:00 | 2018-03-30 07:00 | 2020-12-16 08:00 | 2022-07-11 07:00 | 2022-10-14 07:00 | 2017-04-24 07:00 | 2017-08-30 07:00 | 2017-12-19 08:00 | 2017-10-30 07:00 | 2018-03-30 07:00 | 2020-12-16 08:00 | 2022-06-01 07:00 | 2022-10-14 07:00 | 135.3%
DESIGN | 1129596 | RSD OLD CASCADE/MILLER BR EAST |  | Lyou, John | Bridges & Structures | 2017-04-24 07:00 | 2017-08-30 07:00 | 2017-12-21 08:00 | 2017-10-30 07:00 | 2018-03-30 07:00 | 2020-12-16 08:00 | 2022-07-11 07:00 | 2022-10-14 07:00 | 2017-04-24 07:00 | 2017-08-30 07:00 | 2017-12-21 08:00 | 2017-10-30 07:00 | 2018-03-30 07:00 | 2020-12-16 08:00 | 2022-06-01 07:00 | 2022-10-14 07:00 | 135%
PREDESIGN | 1129598 | RSD ISS HBRT RD@MAY VLLY IMPRV |  | Wang, Jun | Roadway | 2019-02-19 08:00 | 2022-04-30 07:00 | 2023-01-30 08:00 | 2022-10-23 07:00 | 2022-11-30 08:00 | 2023-06-06 07:00 | 2024-06-19 07:00 | 2024-09-11 07:00 | 2019-02-19 08:00 | 2020-12-31 08:00 | 2021-06-30 07:00 | 2021-02-23 08:00 | 2021-07-22 07:00 | 2022-01-06 08:00 | 2023-06-19 07:00 | 2023-09-11 07:00
DESIGN | 1129599 | RSD RENTON AVE PH III SIDEWALK |  | Linders, Jon | Roadside | 2018-05-10 16:50 | 2019-02-15 17:50 | 2019-01-29 08:00 | 2018-11-15 08:00 | 2019-03-05 08:00 | 2019-05-23 07:00 | 2022-06-14 07:00 | 2022-09-08 07:00 |  |  | 2019-01-29 08:00 | 2018-11-15 08:00 | 2019-03-05 08:00 | 2019-05-23 07:00 | 2022-06-14 07:00 | 2022-09-08 07:00 | 56.76%
IMPLEMENT | 1129714 | RSD NE STILLWATER HILL RD | RSD CWP ROADWAY PRESERVATION | Linders, Jon | Roadway | 2019-02-14 08:00 | 2019-03-04 08:00 | 2019-05-30 07:00 | 2019-05-30 07:00 | 2019-08-15 07:00 | 2019-10-10 07:00 | 2021-07-19 07:00 | 2021-10-19 07:00 | 2019-02-14 08:00 | 2019-03-04 08:00 | 2019-05-30 07:00 | 2019-05-30 07:00 | 2019-08-15 07:00 | 2019-10-10 07:00 | 2021-07-19 07:00 | 2021-11-24 08:00 | 2.94%
IMPLEMENT | 1129716 | RSD DIVISION 1 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129717 | RSD DIVISION 2 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129718 | RSD DIVISION 3 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129720 | RSD DIVISION 4 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129721 | RSD DIVISION 5 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129722 | RSD DIVISION 6 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129723 | RSD DIVISION 1 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129724 | RSD DIVISION 2 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129725 | RSD DIVISION 3 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129726 | RSD DIVISION 4 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129727 | RSD DIVISION 5 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129728 | RSD DIVISION 6 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
IMPLEMENT | 1129841 | RSD CIP OVERSIGHT 3855 |  | Foote, Mark | Administrative
IMPLEMENT | 1130303 | RSD CIP OVERSIGHT 3865 |  | Foote, Mark | Administrative
PLANNING | 1130705 | RSD FC SNQ VLY MJR FL MIT STDY | RSD CWP FLOOD CONTROL DISTRICT | Truong, Trinh | Drainage | 2021-04-22 01:37 | 2022-04-01 01:37 | 2022-07-30 01:37 | 2022-07-01 01:37 |  |  |  |  | 2021-04-22 01:37 | 2022-04-01 01:37 | 2022-07-30 01:37 | 2022-07-01 01:37
PLANNING | 1130706 | RSD FC NE8ST@ALLEN LAKE OUTLET | RSD CWP FLOOD CONTROL DISTRICT | Lyou, John | Drainage | 2020-12-19 01:11 | 2022-02-01 01:11 | 2022-04-29 07:00 | 2022-03-25 07:00 |  |  |  |  | 2020-12-19 01:11 | 2022-02-01 01:11 | 2022-04-29 07:00 | 2022-03-25 07:00
IMPLEMENT | 1130707 | RSD FC 162 AVE SE @ SE 166 CT | RSD CWP FLOOD CONTROL DISTRICT | Lyou, John | Drainage | 2017-04-14 07:00 | 2017-12-15 08:00 | 2018-02-26 08:00 | 2018-02-12 08:00 | 2019-01-30 08:00 | 2020-04-07 07:00 | 2020-08-19 07:00 | 2020-11-06 08:00 | 2017-04-14 07:00 | 2017-12-15 08:00 | 2018-02-26 08:00 | 2018-02-12 08:00 | 2019-01-30 08:00 | 2020-04-07 07:00 | 2020-08-19 07:00 | 2020-11-06 08:00 | 5.19%
CLOSEOUT | 1130708 | RSD FC DAVID POWELL RD RPR | RSD CWP FLOOD CONTROL DISTRICT | Lyou, John | Drainage | 2017-04-03 07:00 | 2017-06-23 07:00 | 2018-07-04 07:00 | 2017-07-24 07:00 | 2017-10-25 07:00 | 2018-04-24 07:00 | 2019-07-03 07:00 | 2019-11-22 08:00 | 2017-04-03 07:00 | 2017-06-23 07:00 | 2018-07-04 07:00 | 2017-07-24 07:00 | 2017-10-25 07:00 | 2018-04-24 07:00 | 2019-07-03 07:00 | 2019-11-22 08:00 | -3.95%
DESIGN | 1130710 | RSD FC 380 PL @SR-164 CDR | RSD CWP FLOOD CONTROL DISTRICT | Lyou, John | Drainage | 2018-03-29 07:00 | 2020-01-24 08:00 | 2020-09-08 07:00 | 2020-07-16 07:00 | 2021-02-24 08:00 | 2022-02-18 08:00 | 2022-06-30 07:00 | 2022-10-28 07:00 | 2018-03-29 07:00 | 2020-01-24 08:00 | 2020-09-08 07:00 | 2020-07-16 07:00 | 2021-02-24 08:00 | 2021-10-22 07:00 | 2022-06-01 07:00 | 2022-10-28 07:00 | 87.5%
CLOSEOUT | 1130962 | RSD BLK DMND-RVNSDL RD SLD RPR | RSD QUICK RESPONSE | Shular, Ryan | Contingencies | [7 empty] | 2018-09-28 07:00
CLOSEOUT | 1131132 | RSD 2017-18 NEW GRDL CONSTRUCT | RSD CWP GUARDRAIL CONSTRUCTION | Bleasdale, Don | Roadside | 2018-01-30 08:00 | 2017-07-28 07:00 | 2017-07-31 07:00 | 2017-07-31 07:00 |  |  | 2018-05-14 07:00 | 2018-09-20 07:00 | [8 empty] | 47.5%
DESIGN | 1131157 | RSD HGH COLLSN SIGHTLINE IMPV | RSD CWP HIGH COLLISION SAFETY | Karinen, Martin | Traffic Control |  | 2017-11-16 08:00 | 2020-12-12 08:00 | 2019-02-28 08:00 | 2020-07-15 07:00 | 2020-10-15 07:00 | 2022-05-28 07:00 | 2022-08-28 07:00 |  | 2017-11-16 08:00 | 2020-12-12 08:00 | 2019-02-28 08:00 | 2020-07-15 07:00 | 2020-10-15 07:00 | 2021-09-28 07:00 | 2021-10-28 07:00 | 22.14%
IMPLEMENT | 1131162 | RSD HGH COLLSN SIGNAL MOD | RSD CWP HIGH COLLISION SAFETY | Zhen, Haiyan | Traffic Control
CLOSEOUT | 1131163 | RSD HGH FRICTION SURF TMT | RSD CWP HIGH COLLISION SAFETY | Sahagun, Dan | Traffic Control |  |  | 2017-12-20 08:00 | 2017-05-23 07:00 |  |  | 2018-08-01 07:00 | 2018-11-15 08:00 |  |  | 2017-12-20 08:00 | 2017-05-23 07:00 |  |  | 2018-08-01 07:00 | 2018-11-15 08:00 | -32.16%
DESIGN | 1131235 | RSD S 360ST&MILITARY RD RNDABT |  | Karinen, Martin | Traffic Control |  | 2019-12-06 08:00 | 2021-10-15 07:00 | 2020-09-23 07:00 | 2021-04-08 07:00 | 2022-02-15 08:00 | 2024-04-28 07:00 | 2021-06-11 07:00 |  | 2019-12-06 08:00 | 2021-02-23 08:00 | 2020-09-23 07:00 | 2021-04-08 07:00 | 2021-09-03 07:00 | 2023-09-14 07:00 | 2021-06-11 07:00
HOLD | 1131236 | RSD S LANGSTON RD&59 AV RNDABT |  | McManus, Aileen | Traffic Control
IMPLEMENT | 1131333 | RSD CWP FLOOD CONTROL DISTRICT | RSD CWP FLOOD CONTROL DISTRICT | Lyou, John | Drainage | [7 empty] | 2020-01-31 08:00 | [7 empty] | 2020-01-31 08:00
CLOSEOUT | 1131387 | RSD 2017 CW PVMNT PRESERVATION | RSD CWP ROADWAY PRESERVATION | Moore, Paul | Roadway |  |  | 2017-03-24 07:00 |  |  |  |  | 2018-10-09 07:00 | [8 empty] | 10.98%
CLOSEOUT | 1131508 | RSD DIV 4 FACLTY IMPRVMT 17-18 | RSD FACIL PRESERVATION C/WIDE | Kosai-Eng, Joann | Maintenance Facilities
DESIGN | 1131511 | RSD SAHALEE WY NE 46000 BLK | RSD CWP DRAINAGE PRESERVATION | Dulan, Lica | Drainage | 2018-11-08 08:00 | 2019-07-16 07:00 | 2017-11-30 08:00 | 2017-07-27 07:00 | 2017-11-20 08:00 | 2018-01-10 08:00 | 2022-08-01 07:00 | 2022-10-01 07:00 | 2018-11-08 08:00 | 2019-07-16 07:00 | 2017-11-30 08:00 | 2017-07-27 07:00 | 2017-11-20 08:00 | 2018-01-10 08:00 | 2021-08-15 07:00 | 2021-10-01 07:00
DESIGN | 1131526 | RSD SE PTRVSKY & 134 A SE | RSD CWP DRAINAGE PRESERVATION | Mitchell, Mark C. | Drainage | 2018-09-17 07:00 | 2018-08-21 07:00 | 2020-01-06 08:00 | 2018-08-02 07:00 | 2019-08-16 07:00 | 2020-04-15 07:00 | 2023-03-01 08:00 | 2024-10-15 23:03 | 2018-09-17 07:00 | 2018-08-21 07:00 | 2020-01-06 08:00 | 2018-08-02 07:00 | 2019-08-16 07:00 | 2021-09-01 07:00 | 2023-03-01 08:00 | 2023-10-02 07:00
IMPLEMENT | 1131557 | RSD 17-18 SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | Brown, Keith | Traffic Control
IMPLEMENT | 1131582 | RSD NE WD/DVL CULVERT REPL | RSD QUICK RESPONSE | Shular, Ryan | Contingencies |  |  | 2017-09-27 07:00 |  |  |  |  | 2017-10-11 07:00
DESIGN | 1131671 | RSD SE PTRVSKY @ 151ST A SE | RSD CWP DRAINAGE PRESERVATION | Mitchell, Mark C. | Drainage | 2018-09-17 07:00 | 2018-05-21 07:00 | 2019-06-19 07:00 | 2018-05-21 07:00 | 2019-08-16 19:14 | 2020-04-30 07:00 | 2024-02-01 22:26 | 2024-04-15 22:08 | 2018-09-17 07:00 | 2018-05-21 07:00 | 2019-06-19 07:00 | 2018-05-21 07:00 | 2019-08-16 19:14 | 2021-07-15 07:00 | 2024-02-01 22:26 | 2024-04-15 22:08
DESIGN | 1131672 | RSD SE PTRVSKY @20300BLK | RSD CWP DRAINAGE PRESERVATION | Mitchell, Mark C. | Drainage | 2018-09-17 07:00 | 2018-05-21 07:00 | 2020-05-15 07:00 | 2018-05-21 07:00 | 2019-08-16 19:25 | 2020-04-30 07:00 | 2024-02-01 23:12 | 2020-09-01 07:00 | 2018-09-17 07:00 | 2018-05-21 07:00 | 2020-05-15 07:00 | 2018-05-21 07:00 | 2019-08-16 19:25 | 2021-09-01 07:00 | 2024-02-01 23:12 | 2020-09-01 07:00
CLOSEOUT | 1131693 | RSD UNION HILL@225 BOXCULVRT | RSD CWP DRAINAGE PRESERVATION | Truong, Trinh | Drainage |  |  | 2017-07-26 07:00 |  |  |  |  | 2017-09-12 07:00 |  |  | 2017-07-26 07:00 |  |  |  |  | 2017-09-12 07:00
PLANNING | 1132446 | RSD S LANGSTN RD@132ST DRG IMP | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage | 2020-09-15 07:00 | 2020-10-01 07:00 | 2020-10-09 07:00 | 2020-10-08 07:00 |  |  |  | 2021-12-31 08:00 | 2020-09-15 07:00 | 2020-10-01 07:00 | 2020-10-09 07:00 | 2020-10-08 07:00 |  |  |  | 2021-12-31 08:00
PREDESIGN | 1132448 | RSD SW 108ST@10 AVE SW DRG IMP | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage
DESIGN | 1132450 | RSD 177 AVE SE DRG IMP | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage | [7 empty] | 2018-12-31 08:00
PREDESIGN | 1132523 | RSD GREEN RVR RD S28728 DR IMP | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage | 2019-05-24 07:00 | 2019-06-14 07:00 |  | 2017-08-21 07:00
DESIGN | 1132710 | RSD DRAIN IMP SAHALEE-4800 | RSD CWP DRAINAGE PRESERVATION | Dulan, Lica | Drainage | 2018-11-08 08:00 | 2018-04-16 07:00 | 2018-05-01 07:00 | 2018-04-27 07:00 | 2018-07-02 07:00 | 2018-12-21 08:00 | 2022-06-01 07:00 | 2020-08-01 07:00 | 2018-11-08 08:00 | 2018-04-16 07:00 | 2018-05-01 07:00 | 2018-04-27 07:00 | 2018-07-02 07:00 | 2018-12-21 08:00 | 2022-06-01 07:00 | 2020-08-01 07:00
CLOSEOUT | 1132958 | RSD 15 MILE BRDG #1384A LOAD | RSD QUICK RESPONSE | Martin, TingTing | Contingencies | [7 empty] | 2018-06-13 07:00
CLOSEOUT | 1133219 | RSD VASHON HWY SW PAVE PRES | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway |  |  | 2018-04-05 07:00 |  |  |  |  | 2018-10-10 07:00 |  |  | 2018-04-05 07:00 |  |  |  |  | 2018-10-10 07:00 | 58.88%
CLOSEOUT | 1133220 | RSD 2018 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | Moore, Paul | Roadway |  | 2018-01-01 08:00 | 2018-01-01 08:00 | 2018-01-01 08:00 |  |  | 2018-08-13 07:00 | 2019-09-04 07:00 | [8 empty] | -4.08%
CLOSEOUT | 1133413 | RSD SE SAWYER RDG OVERLAY | RSD CW ROADWAY PRESERVATION | Moore, Paul | Roadway | [7 empty] | 2018-12-31 08:00
CLOSEOUT | 1133440 | RSD MOUNT VIEW RD REPAIR | RSD CWP QUICK RESPONSE | Shular, Ryan | Roadside
CLOSEOUT | 1133757 | RSD 2018 BITUM SURF TREATMENT | RSD CWP ROADWAY PRESERVATION | Moore, Paul | Roadway |  | 2018-01-01 08:00 | 2018-01-01 08:00 | 2018-01-01 08:00 |  |  | 2018-08-13 07:00 | 2019-09-14 07:00 | [8 empty] | -2.51%
CLOSEOUT | 1133864 | RSD NE NVLTY HILL RD TRAIL | RSD CWP QUICK RESPONSE | Sahagun, Dan | Roadside |  |  |  | 2018-01-22 08:00
PLANNING | 1134079 | RSD KENTKANGLEY LNDSBRG RNDABT |  | Linders, Jon | Traffic Control | 2020-01-03 08:00 | 2023-09-21 14:31 | 2023-10-25 07:00 | 2023-10-11 07:00 |  |  |  | 2022-09-12 07:00 | 2020-01-03 08:00 | [6 empty] | 2022-09-12 07:00
PLANNING | 1134080 | RSD WDDUV SNOQ VALLEY IMPROVE |  | Linders, Jon | Roadway | 2022-09-14 07:00 | 2023-09-21 07:00 | 2023-10-25 07:00 | 2023-10-11 07:00 |  |  |  | 2022-09-20 07:00 | 2022-09-14 07:00 | 2023-09-21 07:00 | 2023-10-25 07:00 | 2023-10-11 07:00 |  |  |  | 2022-09-20 07:00
DESIGN | 1134081 | RSD REDMOND RIDGE DR NE RNDABT |  | Karinen, Martin | Traffic Control | 2019-02-13 08:00 |  | 2019-11-06 08:00 | 2019-06-19 07:00 | 2019-08-29 07:00 | 2019-11-06 08:00 | 2022-07-06 07:00 | 2022-10-01 07:00 | 2019-02-13 08:00 |  | 2019-11-06 08:00 | 2019-06-19 07:00 | 2019-08-29 07:00 | 2019-11-06 08:00 | 2022-05-06 07:00 | 2022-08-01 07:00 | 156.2%
IMPLEMENT | 1134082 | RSD FACILITIES LED CONVERSION |  | Kosai-Eng, Joann | Maintenance Facilities |  |  | 2019-03-15 07:00 | [7 empty] | 2019-03-15 07:00
PREDESIGN | 1134083 | RSD COVINGTON WAY SE IMPROVE |  | Linders, Jon | Roadway | 2020-08-17 07:00 | 2021-06-21 07:00 | [6 empty] | 2020-08-17 07:00 | 2021-06-21 07:00
IMPLEMENT | 1134093 | RSD CWP TRAFFIC SAFETY | RSD CWP TRAFFIC SAFETY | Brown, Keith | Traffic Control
LAND | 1135042 | RSD VASHON MAINT FACILITY REPL |  | Kosai-Eng, Joann | Maintenance Facilities
LAND | 1135043 | RSD NE MAINT FACILITY REPL |  | Kosai-Eng, Joann | Maintenance Facilities
PLANNING | 1135044 | RSD PRSTN MAINT FACILTY BLDOUT |  | Kosai-Eng, Joann | Maintenance Facilities
IMPLEMENT | 1135045 | RSD CWP CLVRT RPLCMT FISH PASS | RSD CWP CLVRT RPLCMT FISH PASS | Cassidy, Jon | Drainage
DESIGN | 1135046 | RSD MAINT HDQTRS BLDG D REHAB |  | Ho, Alex | Maintenance Facilities | 2016-11-03 07:00 | 2017-01-10 08:00 | 2017-06-12 07:00 | 2017-03-03 08:00 | 2017-07-17 07:00 | 2017-10-27 07:00 | 2020-01-05 08:00 | 2021-12-31 08:00 | 2016-11-03 07:00 | 2017-01-10 08:00 | 2017-06-12 07:00 | 2017-03-03 08:00 | 2017-07-17 07:00 | 2017-10-27 07:00 | 2020-01-05 08:00 | 2021-12-31 08:00 | -3.089%
IMPLEMENT | 1135073 | RSD CWP 2019-20 BRIDGE SAFETY | RSD CWP 2019-20 BRIDGE SAFETY | Truong, Trinh | Bridges & Structures | [7 empty] | 2026-12-31 08:00
IMPLEMENT | 1135997 | RSD COAL CREEK BRG 3035A REPL |  | Martin, TingTing | Bridges & Structures | 2018-10-12 07:00 | 2019-06-10 07:00 | 2020-11-18 08:00 | 2019-07-15 07:00 | 2020-03-25 07:00 | 2020-09-14 07:00 | 2021-09-24 17:04 | 2022-12-30 08:00 | 2018-10-12 07:00 | 2019-06-10 07:00 | 2020-11-18 08:00 | 2019-07-15 07:00 | 2020-03-25 07:00 | 2020-09-14 07:00 | 2021-07-19 17:04 | 2022-03-31 17:04 | 6.638%
DESIGN | 1135998 | RSD AMES LK TRS BRG 1320A REPL |  | Truong, Trinh | Bridges & Structures | 2019-06-21 07:00 | 2020-06-23 07:00 | 2021-03-03 08:00 | 2020-10-15 07:00 | 2021-06-08 07:00 | 2022-03-08 08:00 | 2023-06-06 07:00 | 2024-07-30 07:00 | 2019-06-21 07:00 | 2020-06-23 07:00 | 2021-03-03 08:00 | 2020-10-15 07:00 | 2021-06-16 07:00 | 2022-02-03 08:00 | 2023-06-06 07:00 | 2024-07-30 07:00 | 0%
DESIGN | 1135999 | RSD UPR TOKUL CK BRG 271B REPL |  | Martin, TingTing | Bridges & Structures | 2019-01-09 08:00 | 2020-05-08 07:00 | 2021-04-01 07:00 | 2020-05-28 07:00 | 2021-01-14 08:00 | 2021-08-19 07:00 | 2022-04-25 07:00 | 2023-01-31 08:00 | 2019-01-09 08:00 | 2020-05-08 07:00 | 2021-04-01 07:00 | 2020-05-28 07:00 | 2021-01-14 08:00 | 2021-08-20 07:00 | 2022-04-25 07:00 | 2023-01-31 08:00 | 0%
DESIGN | 1136000 | RSD BARING BRG 509A REPL |  | Truong, Trinh | Bridges & Structures | 2018-07-18 07:00 | 2019-03-06 08:00 | 2022-01-03 08:00 | 2019-07-16 07:00 | 2020-12-01 08:00 | 2022-06-06 07:00 | 2024-04-26 07:00 | 2025-11-24 08:00 | 2018-07-18 07:00 | 2019-03-06 08:00 | 2021-04-30 07:00 | 2019-07-16 07:00 | 2020-12-25 08:00 | 2022-06-06 07:00 | 2024-04-26 07:00 | 2025-11-24 08:00
IMPLEMENT | 1136001 | RSD 277TH ST BRG 3126 REPL |  | Premachandra, Hiromal | Bridges & Structures | 2019-01-09 08:00 | 2020-02-04 08:00 | 2020-12-18 08:00 | 2020-02-25 08:00 | 2020-05-18 07:00 | 2020-08-20 07:00 | 2021-07-23 07:00 | 2021-11-19 08:00 | 2019-01-09 08:00 | 2020-02-04 08:00 | 2020-12-18 08:00 | 2020-02-25 08:00 | 2020-05-18 07:00 | 2020-08-20 07:00 | 2021-07-06 07:00 | 2021-11-09 08:00 | 3.06%
CLOSEOUT | 1136084 | RSD 2019-20 NEW GRDRAIL CONST | RSD CWP GUARDRAIL CONSTRUCTION | Mott, Linda | Roadside | 2019-01-22 08:00 |  | 2019-07-01 07:00 | 2019-09-11 07:00 | 2019-08-30 07:00 | 2019-10-31 07:00 | 2020-08-26 07:00 | 2021-01-20 08:00 | 2019-01-22 08:00 |  | 2019-07-01 07:00 | 2019-09-11 07:00 | 2019-08-30 07:00 | 2019-10-31 07:00 | 2020-08-26 07:00 | 2021-01-20 08:00 | 9.846%
IMPLEMENT | 1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside | 2019-01-22 08:00 |  | 2019-11-18 08:00 |  |  | 2020-05-14 07:00 | 2021-01-04 08:00 | 2021-07-30 07:00 | 2019-01-22 08:00 |  | 2019-11-18 08:00 |  |  | 2020-05-14 07:00 | 2021-01-04 08:00 | 2021-07-30 07:00 | 10.71%
DESIGN | 1136086 | RSD 218TH AV SE RECONSTRUCTION | RSD CWP ROADWAY PRESERVATION | Linders, Jon | Roadway | 2019-01-22 08:00 | 2019-02-19 17:27 | 2021-09-24 07:00 | 2020-02-20 08:00 | 2020-09-17 07:00 | 2021-03-02 08:00 | 2022-05-16 07:00 | 2022-10-10 07:00 | 2019-01-22 08:00 |  | 2021-07-05 07:00 | 2020-02-20 08:00 | 2020-09-17 07:00 | 2021-03-02 08:00 | 2022-03-25 07:00 | 2021-09-30 07:00 | 0%
DESIGN | 1136228 | RSD PET RD AT 134TH CULVERT |  | Mitchell, Mark C. | Drainage
PREDESIGN | 1136229 | RSD 180TH AT 408TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Mitchell, Mark C. | Drainage | 2020-01-20 08:00 | 2022-01-31 08:00 | 2022-03-15 07:00 | 2022-02-28 08:00 | 2022-06-15 07:00 | 2022-09-15 07:00 |  |  | 2020-01-20 08:00 | 2021-08-06 07:00 | 2021-08-20 07:00 | 2021-08-13 07:00 | 2021-10-15 07:00 | 2021-12-31 08:00
PLANNING | 1136230 | RSD FAIRWOOD E OF 151 CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Cassidy, Jon | Drainage
PREDESIGN | 1136231 | RSD 185TH AT 179TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Mitchell, Mark C. | Drainage | 2020-04-06 07:00 | 2022-01-17 08:00 | 2022-01-31 08:00 | 2022-01-28 08:00 | 2022-01-14 08:00 | 2022-04-04 07:00 | 2031-06-16 23:12 | 2131-09-17 23:12 | 2020-04-06 07:00 | 2021-07-16 07:00 | 2021-07-30 07:00 | 2021-07-26 07:00 | 2021-09-30 07:00 | 2021-11-05 07:00
DESIGN | 1136232 | RSD 18430 NE 128TH WY CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Mitchell, Mark C. | Drainage | 2020-04-13 07:00 | 2020-10-22 07:00 | 2021-07-14 07:00 | 2020-05-26 07:00 | 2020-10-22 07:00 | 2021-06-07 07:00 |  |  | 2020-04-13 07:00 | 2020-10-22 07:00 | 2021-07-15 07:00 | 2020-05-26 07:00 | 2020-10-22 07:00 | 2021-06-07 07:00
DESIGN | 1136233 | RSD LAKE JOY AT 118TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Quach, Dieu | Drainage | 2019-09-27 07:00 | 2019-09-13 07:00 | 2022-01-31 08:00 | 2019-09-13 07:00 | 2019-12-10 08:00 | 2021-04-14 07:00 | 2021-07-19 07:00 | 2021-09-30 07:00 | 2019-09-27 07:00 | 2019-09-13 07:00 | 2021-07-30 07:00 | 2019-09-13 07:00 | 2019-12-10 08:00 | 2021-04-14 07:00 | 2022-07-12 07:00 | 2022-10-17 07:00
PREDESIGN | 1136234 | RSD WD DUV AT 172ND CULVERT |  | Wang, Jun | Drainage | 2020-09-04 07:00 | 2020-11-18 08:00 | 2022-02-25 08:00 | 2021-07-01 07:00 | 2022-01-28 20:56 | 2022-03-25 07:00 | 2022-06-20 21:05 | 2022-08-26 13:45 | 2020-09-04 07:00 | 2020-11-18 08:00 | 2021-07-30 07:00 | 2021-07-01 07:00 | 2021-08-13 19:56 | 2021-11-05 07:00 | 2022-06-06 21:05 | 2022-08-26 21:05
DESIGN | 1136235 | RSD AVONDALE AND 144TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Mitchell, Mark C. | Drainage | 2020-04-16 07:00 | 2020-07-16 07:00 | 2021-04-12 07:00 | 2020-09-15 07:00 | 2020-09-30 07:00 | 2021-05-18 07:00 |  |  | 2020-04-16 07:00 | 2020-07-16 07:00 | 2021-04-12 07:00 | 2020-09-15 07:00 | 2020-09-30 07:00 | 2021-05-18 07:00
DESIGN | 1136236 | RSD 165TH AND 176TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Mitchell, Mark C. | Drainage | 2020-04-06 07:00 | 2020-10-22 07:00 | 2021-07-14 07:00 | 2020-07-15 07:00 | 2020-10-09 07:00 | 2021-05-25 07:00 |  |  | 2020-04-06 07:00 | 2020-10-22 07:00 | 2021-07-15 07:00 | 2020-07-15 07:00 | 2020-10-09 07:00 | 2021-05-25 07:00
PREDESIGN | 1136237 | RSD S 370TH ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Lyou, John | Drainage | 2020-04-06 07:00 | 2021-01-22 08:00 | 2022-07-29 07:00 | 2022-06-30 07:00 | 2022-09-30 07:00 | 2022-11-30 08:00 | 2031-07-07 07:00 | 2031-09-30 07:00 | 2020-04-06 07:00 | 2021-01-22 08:00 | 2021-08-20 07:00 | 2021-07-16 07:00 | 2021-09-30 07:00 | 2021-10-29 07:00 | 2031-07-07 07:00 | 2031-09-30 07:00
DESIGN | 1136238 | RSD 33609 NE 24TH ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Quach, Dieu | Drainage | 2021-01-29 08:00 | 2022-01-31 08:00 | 2022-01-31 08:00 | 2021-03-30 07:00 | 2021-05-31 15:35 | 2022-01-31 08:00 | 2023-07-05 22:01 | 2023-08-30 07:00 | 2021-01-29 08:00 | 2021-07-30 07:00 | 2021-08-31 07:00 | 2021-03-30 07:00 | 2021-05-31 15:35 | 2021-09-30 07:00 | 2031-07-07 22:01 | 2031-08-30 07:00
PLANNING | 1136239 | RSD 317TH AND THOMAS CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Shular, Ryan | Drainage | 2022-01-31 08:00 | 2022-03-31 07:00 | 2022-03-31 07:00 | 2022-01-31 08:00 | 2022-07-01 00:28 | 2022-10-01 00:28 |  |  | 2021-07-30 07:00 | 2021-07-30 07:00 | 2021-08-31 07:00 | 2021-07-30 07:00 | 2021-10-02 00:28 | 2021-11-20 01:28
IMPLEMENT | 1136241 | RSD 28278 GREEN RVR RD CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Shular, Ryan | Drainage | 2018-08-20 07:00 | 2018-08-27 07:00 | 2020-03-31 07:00 | 2019-02-28 08:00 |  |  | 2020-07-13 07:00 | 2020-08-27 07:00 | 2018-08-20 07:00 | 2018-08-27 07:00 | 2020-03-31 07:00 | 2019-02-28 08:00 |  |  | 2020-07-13 07:00 | 2020-08-27 07:00
IMPLEMENT | 1136351 | RSD CURB RAMP REPLACEMENT 3855 | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway | [7 empty] | 2019-08-31 07:00 | [7 empty] | 2019-08-31 07:00
IMPLEMENT | 1136352 | RSD 2019 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway | 2019-01-09 08:00 |  | 2019-04-19 07:00 | 2019-01-09 08:00 | 2019-02-19 08:00 | 2019-03-19 07:00 | 2019-07-03 07:00 | 2020-07-02 07:00 | 2019-01-09 08:00 |  | 2019-04-19 07:00 | 2019-01-09 08:00 | 2019-02-19 08:00 | 2019-03-19 07:00 | 2019-07-03 07:00 | 2020-07-02 07:00 | 0.45%
DESIGN | 1136419 | RSD SE 432ND ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Dulan, Lica | Drainage | 2019-02-01 08:00 | 2020-11-18 08:00 | 2022-01-31 08:00 | 2020-11-18 08:00 | 2020-03-01 08:00 | 2020-12-12 08:00 | 2031-12-31 20:50 | 2032-12-31 08:00 | 2019-02-01 08:00 | 2020-11-18 08:00 | 2021-07-15 07:00 | 2020-11-18 08:00 | 2020-03-01 08:00 | 2020-12-12 08:00 | 2031-12-31 20:50 | 2032-12-31 08:00
DESIGN | 1136580 | RSD S 360TH ST SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | Karinen, Martin | Traffic Control | 2019-03-18 07:00 | 2020-06-09 23:18 | 2020-12-12 08:00 | 2019-08-02 07:00 | 2020-07-15 07:00 | 2020-10-15 07:00 | 2022-05-28 07:00 | 2022-08-28 07:00 | 2019-03-18 07:00 | 2020-06-09 23:18 | 2020-12-12 08:00 | 2019-08-02 07:00 | 2020-07-15 07:00 | 2020-10-15 07:00 | 2021-09-28 07:00 | 2021-10-28 07:00 | 22.14%
DESIGN | 1136582 | RSD S 298TH ST SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | McManus, Aileen | Traffic Control | 2019-03-18 07:00 |  | 2019-08-02 07:00 | 2019-08-01 07:00 |  | 2020-01-09 08:00 | 2020-09-29 07:00 | 2020-12-14 08:00 | 2019-03-18 07:00 |  | 2019-08-02 07:00 | 2019-08-01 07:00 |  | 2020-01-09 08:00 | 2020-09-29 07:00 | 2020-12-14 08:00
CLOSEOUT | 1136631 | RSD JUDD CK BRD 3184 RPR | RSD CWP QUICK RESPONSE | O'Day, Jamie | Roadside |  |  |  | 2020-03-30 07:00 |  | 2020-05-27 07:00 |  | 2020-12-01 08:00 |  |  |  | 2020-03-30 07:00 |  | 2020-05-27 07:00 |  | 2020-12-01 08:00
DESIGN | 1136633 | RSD PATTON BRD 3015 BKT RPR | RSD CWP QUICK RESPONSE | Jiang, Stephen | Roadside |  |  |  | 2020-02-17 08:00 | 2020-04-23 07:00 | 2020-05-21 07:00 | 2021-02-15 08:00 | 2021-05-04 07:00 |  |  |  | 2020-02-17 08:00 | 2020-04-23 07:00 | 2020-05-21 07:00 | 2021-02-15 08:00 | 2021-05-04 07:00
CLOSEOUT | 1136646 | RSD 42ND AVE S SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | McManus, Aileen | Traffic Control | 2019-03-18 07:00 |  | 2019-08-01 07:00 | 2019-08-01 07:00 |  | 2019-12-24 08:00 | 2020-09-29 07:00 | 2020-12-14 08:00 | 2019-03-18 07:00 |  | 2019-08-01 07:00 | 2019-08-01 07:00 |  | 2019-12-24 08:00 | 2020-09-29 07:00 | 2020-12-14 08:00
IMPLEMENT | 1136709 | RSD TRAFFIC CALMING | RSD CWP TRAFFIC SAFETY | Mott, Linda | Traffic Control | 2019-03-18 07:00 |  | 2019-12-02 08:00 | 2019-12-01 08:00 |  |  | 2021-05-12 07:00 | 2021-07-30 07:00 | 2019-03-18 07:00 |  | 2019-12-02 08:00 | 2019-12-01 08:00 |  |  | 2021-05-12 07:00 | 2021-07-30 07:00
IMPLEMENT | 1136711 | RSD ROADWAY LIGHTING | RSD CWP TRAFFIC SAFETY | Mott, Linda | Traffic Control | 2019-02-15 08:00 | [6 empty] | 2021-09-30 07:00 | 2019-02-15 08:00 | [6 empty] | 2021-09-30 07:00
PLANNING | 1136712 | RSD RADAR SPEED SIGNS | RSD CWP TRAFFIC SAFETY | Kunihiro, Lisa | Traffic Control
IMPLEMENT | 1136715 | RSD LEFT TURN PHASING | RSD CWP TRAFFIC SAFETY | Zhen, Haiyan | Traffic Control | 2019-03-18 07:00 | [6 empty] | 2021-12-31 08:00 | 2019-03-18 07:00 | [6 empty] | 2021-12-31 08:00
IMPLEMENT | 1136716 | RSD TRANSVERSE RUMBLE SIGNS | RSD CWP TRAFFIC SAFETY | Mott, Linda | Traffic Control | 2019-03-18 07:00 |  |  | 2019-12-20 08:00 |  |  | 2021-05-12 07:00 | 2021-07-30 07:00 | 2019-03-18 07:00 |  |  | 2019-12-20 08:00 |  |  | 2021-05-12 07:00 | 2021-07-30 07:00
PLANNING | 1136931 | RSD SCALE DBASE RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | Crippen, Mike | Administrative
PLANNING | 1136932 | RSD BIZDOC MAP VLT RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | Crippen, Mike | Administrative
PLANNING | 1136933 | RSD CUTRL RES DBASE RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | Crippen, Mike | Administrative
PLANNING | 1137364 | RSD WSDE HWY SW DEGRADATN | RSD CWP QUICK RESPONSE | Posey, Norton | Roadside
HOLD | 1137577 | RSD 304 ST HAUL RD MITGN | RSD CWP QUICK RESPONSE | Daggs, Victor | Roadside
IMPLEMENT | 1137584 | RSD MIDDLE FORK RD RPR | RSD CWP QUICK RESPONSE | Cassidy, Jon | Roadside
IMPLEMENT | 1137752 | RSD FLMNG GYSR BRG 3024 PNTG | RSD CWP BRIDGE PRIORITY MAINT | Martin, TingTing | Bridges & Structures | [5 empty] | 2020-03-04 08:00 | 2020-07-10 07:00 | 2020-10-07 07:00 | [5 empty] | 2020-03-04 08:00 | 2020-07-10 07:00 | 2020-10-07 07:00
CLOSEOUT | 1137860 | RSD 2019 DVD PWLL RD RPR 36621 | RSD CWP QUICK RESPONSE | Lyou, John | Roadside
IMPLEMENT | 1137862 | RSD 2020 HGH FRCTN SFC TRTMT | RSD CWP HIGH COLLISION SAFETY | Linders, Jon | Traffic Control | 2020-01-23 08:00 | 2020-01-23 08:00 | 2020-09-22 07:00 | 2020-07-09 07:00 | 2020-09-01 07:00 | 2020-10-13 07:00 | 2021-08-26 07:00 | 2022-07-11 07:00 | 2020-01-23 08:00 | 2020-01-23 08:00 | 2020-09-22 07:00 | 2020-07-09 07:00 | 2020-09-01 07:00 | 2020-10-13 07:00 | 2021-08-23 07:00 | 2022-06-10 07:00 | 96.11%
IMPLEMENT | 1137996 | RSD 2020 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway |  |  | 2020-03-26 07:00 | 2020-01-14 08:00 | 2020-02-03 08:00 | 2020-02-24 08:00 | 2020-06-10 07:00 | 2021-02-23 08:00 |  |  | 2020-03-26 07:00 | 2020-01-14 08:00 | 2020-02-03 08:00 | 2020-02-24 08:00 | 2020-06-10 07:00 | 2021-02-23 08:00 | -39.6%
DESIGN | 1138330 | RSD CVGTN SWYR SGHTLN IMPR | RSD CWP HIGH COLLISION SAFETY | Wang, Jun | Traffic Control |  | 2021-09-27 07:00 | 2022-01-28 08:00 | 2021-12-15 08:00 | 2022-03-29 17:23 | 2022-06-22 07:00 | 2023-05-28 07:00 | 2023-06-30 07:00 |  | 2021-06-08 07:00 |  | 2021-11-30 08:00 |  |  | 2023-02-28 08:00 | 2023-06-30 07:00
HOLD | 1138337 | RSD FC FSH HTCHRY BRG 61B RPR | RSD CWP FLOOD CONTROL DISTRICT | Roark, Ben | Drainage |  |  |  | 2021-02-03 08:00 |  |  |  | 2021-11-04 07:00 |  |  |  | 2021-02-03 08:00 |  |  |  | 2021-11-04 07:00
DESIGN | 1138339 | RSD FC S 106 ST DRAINAGE IMPRV | RSD CWP FLOOD CONTROL DISTRICT | Quach, Dieu | Drainage | 2021-03-31 07:00 | 2021-12-31 08:00 | 2022-01-31 08:00 | 2019-12-27 08:00 | 2020-04-24 07:00 | 2021-05-25 07:00 | 2022-08-01 07:00 | 2022-09-15 07:00 | 2021-03-31 07:00 | 2021-07-30 07:00 | 2021-07-30 07:00 | 2019-12-27 08:00 | 2020-04-24 07:00 | 2021-05-25 07:00 | 2021-07-05 07:00 | 2021-08-13 07:00
IMPLEMENT | 1138763 | RSD 2019-20 GUARDRAL PRSRVTN 2 | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside | 2019-01-22 08:00 |  | 2019-07-01 07:00 | 2019-09-11 07:00 |  |  | 2020-08-26 07:00 | 2020-12-04 08:00 | 2019-01-22 08:00 |  | 2019-07-01 07:00 | 2019-09-11 07:00 |  |  | 2020-08-26 07:00 | 2020-12-04 08:00
PREDESIGN | 1138913 | RSD BOISE X BRDG #3055A REPL |  | Jin, Henry | Bridges & Structures | 2020-05-07 07:00 | 2021-12-08 08:00 | 2022-05-20 07:00 | 2022-04-05 07:00 | 2022-09-15 07:00 | 2023-03-23 07:00 | 2024-02-15 08:00 | 2024-10-31 07:00 | 2020-05-07 07:00 | 2021-07-29 07:00 | 2021-11-11 08:00 | 2021-11-11 08:00 | 2022-03-04 23:31 | 2022-06-20 22:31 | 2023-05-10 07:00 | 2023-09-28 07:00
DESIGN | 1138914 | RSD FIFTN MILE CRK#493C B REP |  | Jose, Jessy | Bridges & Structures | 2020-05-01 07:00 | 2020-08-26 07:00 | 2021-09-07 07:00 | 2021-06-15 07:00 | 2021-06-15 07:00 | 2021-09-23 07:00 | 2023-01-16 08:00 | 2023-09-29 07:00 | 2020-05-01 07:00 | 2020-08-26 07:00 | 2021-09-21 07:00 | 2021-06-15 07:00 | 2021-06-15 07:00 | 2021-10-17 07:00 | 2023-01-16 08:00 | 2023-09-29 07:00 | 0%
PREDESIGN | 1138918 | RSD 16TH AVE PED IMPRVMNTS |  | Mott, Linda | Roadside | 2020-09-01 23:42 |  | 2022-02-18 21:32 | 2022-04-15 07:00 | 2022-05-31 07:00 | 2022-08-31 07:00 | 2023-08-01 00:31 | 2023-12-29 08:00 | 2020-09-01 23:42 |  |  | 2021-06-30 07:00 | 2021-08-31 07:00 | 2021-11-30 08:00 | 2022-11-02 00:31 | 2023-04-28 23:17
PREDESIGN | 1138947 | RSD 284TH AVE S 46913 CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Dulan, Lica | Drainage | 2021-05-02 05:35 | 2022-01-31 08:00 | 2022-02-28 08:00 | 2022-02-15 08:00 | 2022-03-15 07:00 | 2022-03-31 07:00 | 2022-07-05 19:49 | 2022-09-01 20:37 | 2021-05-02 05:35 | 2021-09-01 05:35 | 2021-10-01 05:35 | 2021-09-16 05:35 |  |  | 2022-06-01 19:49 | 2022-09-01 20:37
PLANNING | 1139144 | RSD SE REINIG RD DRNG IMPR CUL |  |  | Drainage
PREDESIGN | 1139145 | RSD SE GRN VLLY & 218 AVE INT |  | Linders, Jon | Traffic Control | 2022-01-12 08:00 | 2022-08-17 07:00 | 2022-10-26 17:13 | 2022-10-12 17:13 | 2023-03-16 17:13 | 2023-07-05 17:13 | 2024-06-03 15:29 | 2024-09-25 17:13
PLANNING | 1139146 | RSD RAINIER S & LKRDG DR INT |  | Zhen, Haiyan | Roadway
IMPLEMENT | 1139147 | RSD CWP ADA PROGRAM | RSD CWP ADA PROGRAM | Vander Sluis, John | Roadway
CLOSEOUT | 1139236 | RSD JUDD CK BRG 3184 RECONT | RSD CWP BRIDGE PRIORITY MAINT | Jose, Jessy | Bridges & Structures | [6 empty] | 2021-03-26 23:01 | 2021-04-26 23:01 | [6 empty] | 2021-03-26 23:01 | 2021-04-26 23:01
PREDESIGN | 1139286 | RSD CWP BRIDGE LOAD UPGRD SFTY | RSD CWP BRIDGE LOAD UPGRD SFTY | Jiang, Stephen | Bridges & Structures | 2021-04-27 14:43 | [7 empty] | 2021-04-27 14:43
PREDESIGN | 1139716 | RSD S LANGSTN RD@125TH DRG IM | RSD CWP DRAINAGE PRESERVATION | Mitchell, Mark C. | Drainage | 2022-01-07 08:00 | 2022-01-10 08:00 | 2022-01-31 08:00 | 2022-01-28 08:00 | 2022-05-20 23:08 | 2022-08-01 07:00 | 2023-02-14 00:07 | 2023-06-15 23:07 | 2021-07-30 07:00 | 2021-07-15 07:00 | 2021-07-30 07:00 | 2021-07-23 07:00 | 2021-08-16 23:08 | 2021-10-15 07:00 | 2022-05-13 23:07 | 2022-11-16 00:07
IMPLEMENT | 1139744 | RSD 4-CREEK-RANCH 5044 DECK | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1139749 | RSD MMS REPLACEMENT |  | Murata, Kathi | Administrative
NOT SET | 1139810 | RSD BEALL RD SW RESTOR CULVERT |  |  | Drainage
PLANNING | 1139811 | RSD SE384TH DRNG IMPRV CULVERT |  | Lyou, John | Drainage | 2021-09-24 18:09 | 2022-02-28 08:00 | 2022-05-20 21:40 | 2022-04-15 07:00
IMPLEMENT | 1139815 | RSD 356TH DR SE WINTER 2020 | RSD CWP QUICK RESPONSE | Truong, Trinh | Roadside | [7 empty] | 2020-12-21 19:35
PREDESIGN | 1140858 | RSD 244TH AVE NE WINTER 2020 | RSD CWP QUICK RESPONSE | Wang, Jun | Roadside | 2020-09-01 21:14 | 2022-01-14 08:00 | 2022-02-28 08:00 | 2022-02-25 08:00 | 2022-04-29 21:14 | 2022-07-01 21:14 | 2023-06-23 07:00 | 2023-09-18 07:00
PREDESIGN | 1140905 | RSD 17401 SE 240 ST SE CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Dulan, Lica | Drainage | 2021-05-01 07:00 | 2022-08-01 07:00 | 2022-10-31 07:00 | 2022-09-30 07:00 | 2023-01-31 08:00 | 2023-04-15 07:00 |  |  | 2021-05-01 07:00 | 2022-02-28 08:00 | 2022-05-31 07:00 | 2022-05-01 07:00 | 2022-09-01 02:14 | 2022-12-01 03:14
PLANNING | 1140906 | RSD 156TH SE- SE 240TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | Dulan, Lica | Drainage | 2021-05-01 19:49 | 2022-02-28 20:49 | 2022-05-31 07:00 | 2022-05-01 19:49 | 2022-08-31 23:29 | 2022-12-01 00:29 | 2031-12-31 20:49 |  | 2021-05-01 19:49 | 2022-02-28 20:49 | 2022-05-31 07:00 | 2022-05-01 19:49 | 2022-08-31 23:29 | 2022-12-01 00:29 | 2031-12-31 20:49
PLANNING | 1141001 | RSD NETOLT RD RP WINTER2020 | RSD CWP QUICK RESPONSE | Martin, TingTing | Roadside | 2020-09-01 22:50 | 2022-01-25 08:00 | 2022-03-31 22:50 | 2022-03-14 07:00 |  | 2022-05-13 07:00 | 2023-03-27 15:26 | 2023-06-30 15:26 | 2020-09-01 22:50 | 2021-12-30 23:50 | 2022-03-31 22:50 | 2022-02-28 23:50 |  | 2022-05-10 23:51 | 2023-03-27 15:26 | 2023-06-30 15:26
IMPLEMENT | 1141044 | RSD 2021 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway |  |  | 2021-06-21 07:00 | 2021-02-01 19:46 |  | 2021-02-26 20:44 | 2021-07-07 19:41 | 2022-05-02 19:41 |  |  | 2021-06-21 07:00 | 2021-02-01 19:46 |  | 2021-02-26 20:44 | 2021-07-06 19:41 | 2022-05-02 19:41 | 0%
DESIGN | 1141111 | RSD 2019-20 GUARDRAL PRSRVTN 3 | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside |  |  | 2022-01-14 08:00 |  | 2020-11-05 08:00 | 2021-01-21 08:00 | 2022-04-15 07:00 | 2022-07-29 07:00 | [6 empty] | 2021-10-19 07:00 | 2022-04-29 07:00
IMPLEMENT | 1141250 | RSD 21-22 SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | Hafele, Brendan | Traffic Control | 2021-03-31 07:00 | 2021-03-26 19:47 | 2021-03-26 19:47 | [5 empty] | 2021-03-31 07:00 | 2021-03-26 19:47 | 2021-03-26 19:47
DESIGN | 1141401 | RSD ROADWAY LIGHTING 2 | RSD CWP TRAFFIC SAFETY | Mott, Linda | Traffic Control |  |  |  | 2021-06-24 22:05 | 2020-08-19 07:00 | 2020-09-15 07:00 | 2022-01-04 08:00 | 2022-04-29 07:00
NOT SET | 1141464 | RSD BRG LD UP SFTY FSBLTY STDY | RSD CWP BRIDGE LOAD UPGRD SFTY | Jiang, Stephen | Bridges & Structures
NOT SET | 1141505 | RSD 21 BPM RAGNGRVBR1008G RAIL | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1141507 | RSD 21 BPM WHITNEYBR2025 OVRLY | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1141509 | RSD 21 BPM CEDAR RIVER BRIDGES | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
IMPLEMENT | 1141580 | RSD 21 HRP AMES LK CARNATION F | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway
IMPLEMENT | 1141581 | RSD 21 HRP ALPENTAL ACCESS RD | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway
DESIGN | 1141625 | RSD SE KENT-KANGLEY @LANDSBURG | RSD CWP HIGH COLLISION SAFETY | Linders, Jon | Traffic Control | 2021-07-23 14:35 | 2021-08-18 07:00 | 2021-08-31 07:00 | 2021-06-24 07:00 | 2021-09-09 15:09 | 2021-11-18 16:09 | 2022-07-18 15:09 | 2022-09-12 15:09 | 2021-07-12 07:00 | 2021-07-01 07:00 | 2021-07-12 07:00 | 2021-06-24 07:00 | 2021-09-10 15:09 | 2021-11-22 16:09 | 2022-07-18 15:09 | 2022-09-12 15:09 | 0%
NOT SET | 1142030 | RSD CW ADA RAMPS |  |  | Roadside
PLANNING | 1142035 | RSD ECE CW UKC ADA RAMPS |  | McManus, Aileen | Roadside
NOT SET | 1142289 | RSD 2021 HRP SE 368TH & 236TH | RSD CWP ROADWAY PRESERVATION | Mott, Linda | Roadway
NOT SET | 1142293 | RSD 21 BPM ISQH CRK BR 83D RPR | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142294 | RSD 21 BPM BOISE CR B 3052 RPR | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142384 | RSD 21 BPM BR 122L:122K JOINTS | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142385 | RSD 21 BPM BR 920A:BR 3109 APP | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
DESIGN | 1142478 | RSD 218TH AV SE RECONST DRNAGE | RSD CWP DRAINAGE PRESERVATION | Linders, Jon | Drainage
PREDESIGN | 1142502 | RSD AVONDALE & COTTAGE LK ELEM | RSD CWP TRAFFIC SAFETY | Hafele, Brendan | Traffic Control |  | 2021-10-15 07:00 | 2021-12-10 08:00 | 2021-12-03 08:00
NOT SET | 1142615 | RSD SE LAKE FRANCIS ROAD HAUL | RSD CWP QUICK RESPONSE |  | Roadside
NOT SET | 1142691 | RSD 21 BPM SPB MISC REPAIRS | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142848 | RSD 21 BPM GR RVR 3216 DCK RPR | RSD CWP BRIDGE PRIORITY MAINT |  | Bridges & Structures
NOT SET | 1142850 | RSD 21 FBLP DUVALL SLOUGH #113 | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142876 | RSD 21 BPM 3035A FLOOR BEAM RR | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures
NOT SET | 1142993 | RSD 2022 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | Mott, Linda | Roadway
IMPLEMENT | 2020-001 | DRN DIV DRN | RSD CWP DRAINAGE PRESERVATION | Shular, Ryan | Drainage
IMPLEMENT | 2020-002 | DRN DIV SHOULDER | RSD CWP DRAINAGE PRESERVATION | Kosai-Eng, Joann | Drainage
PLANNING | 2020-003 | PAV Pres Sub | RSD CWP ROADWAY PRESERVATION | Moore, Paul | Roadway
PLANNING | 2020-004 | BRG BPM list | RSD CWP BRIDGE PRIORITY MAINT | Roark, Ben | Bridges & Structures | [7 empty] | 2020-12-31 08:00
PLANNING | 2020-005 | HIGH COLLISION | RSD CWP HIGH COLLISION SAFETY | Dovey, Dan | Traffic Control | [7 empty] | 2020-12-31 08:00
PLANNING | 2020-006 | SCHOOL SAFETY | RSD CWP SCHOOL ZONE SAFETY | McManus, Aileen | Traffic Control | [7 empty] | 2020-12-31 08:00
PLANNING | 2020-007 | TRAFFIC SAFETY | RSD CWP TRAFFIC SAFETY | Brown, Keith | Traffic Control | [7 empty] | 2020-12-31 08:00
PLANNING | 2021001 | RSD AVONDALE RD COTTG LK ELEMT | RSD CWP TRAFFIC SAFETY | Hafele, Brendan | Traffic Control |  | 2021-10-15 07:00 | 2021-12-10 08:00 | 2021-12-03 08:00 |  |  |  |  | 2021-08-31 07:00 | 2021-09-30 23:31 | 2021-10-15 23:31 | 2021-11-01 23:31
PLANNING | 2021002 | RSD 21 HRP PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway
PLANNING | 2021003 | RSD 22 HRP PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | Daggs, Victor | Roadway
PLANNING | 2021004 | RSD 218 AVE RECON PLACEHOLDER | RSD CWP DRAINAGE PRESERVATION | Quach, Dieu | Drainage
DESIGN | 2021005 | RSD 2022 CNTYWDE PAVE PRES PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | Mott, Linda | Roadway |  |  | 2022-02-18 16:27
PLANNING | 2021006 | RSD 21 GUARDRAIL PRES PLACEHOLDER | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside
PLANNING | 2021007 | RSD 22 GUARDRAIL PRES PLACEHOLDER | RSD CWP GUARDRAIL PRESERVATION | Mott, Linda | Roadside |  | 2021-12-23 17:20 | 2022-02-15 17:20 | 2022-01-31 17:20
PLANNING | 2021008 | RSD BPM 2021 UNALLOCATED | RSD CWP BRIDGE PRIORITY MAINT | Mitchell, Patricia | Bridges & Structures
CLOSEOUT | Test-RSD | Test |  | Siemens, Amara | Roadway | 2020-08-17 17:31 | 2021-06-30 07:00 | 2021-07-30 23:56 | 2021-07-15 07:00