## ag-grid
PROJECT |  |  |  |  | TEAM | DETAILS | FINANCIALS (Status) |  |  | REPORTING (Quarterly Progress/MPA)
Phase | Number | Name | Program | Master | Project Manager | Portfolio Category | Forecast | Budget | Capital/Operating | Key Activities - Current Quarter | Key Activities - Next Quarter | Closely Monitored Issues and Key Risks
PLANNING | 1026798 | RSD EMRGNT NEED-EXISTING PRJ |  | No | Mitchell, Patricia | Quick Response | No | No | Capital Project
PLANNING | 1026799 | RSD CIP GRANT CONTIGENCY |  | No | Mitchell, Patricia | Contingencies | No | No | Capital Project
OPERATIONS | 1026800 | RSD CAP PROJ O S FUND 3860 |  | No | Mitchell, Patricia | Administrative | No | No | Capital Project
PREDESIGN | 1027163 | RSD QUICK RESPONSE | RSD QUICK RESPONSE | Yes | Mitchell, Patricia | Contingencies | No | No | Capital Project
IMPLEMENT | 1111819 | RSD C W DRAINAGE PRESERVATION | RSD C W DRAINAGE PRESERVATION | Yes | Shular, Ryan | Drainage | No | No | Capital Project
OPERATIONS | 1114792 | RSD ROADS-COUNTY ROAD CONST |  | No | Mitchell, Patricia | Administrative | No | No | Capital Project
CLOSEOUT | 1116885 | RSD WOODINVILLE DUVALL ITS |  | No | McManus, Aileen | Traffic Control | No | No | Capital Project
CLOSEOUT | 1124986 | RSD CW HRRRP | RSD CW HRRRP | Yes |  | Roadway | No | No | Capital Project
IMPLEMENT | 1125758 | RSD W SNOQ VLY RD/NE124-W/D RD |  | No | Shular, Ryan | Roadway | No | No | Capital Project
DESIGN | 1127271 | RSD PRESTON MAINT FACILITY |  | No | Sugui, Rey | Maintenance Facilities | Yes | No | Capital Project
IMPLEMENT | 1127273 | RSD FAILED ENV & HVAC REHAB |  | No | Knauer, Jennifer | Maintenance Facilities | Yes | No | Capital Project
DESIGN | 1127589 | RSD 165 ST FLD RSK RDUCTN | RSD C W DRAINAGE PRESERVATION | No | Karinen, Martin | Drainage | Yes | No | Capital Project | Determine if schedule for Const. will be 2022 or 2023 for Baseline of project. Obtain additional ROE from private property parcel and proceed with pick up survey to identify the areas suitable for compensatory storage. Work with R/W team to acquire flood easements for effected properties if compensatory storage is to proceed. |  | Completion of a basemap for use in estimating volume of compensatory storage
CLOSEOUT | 1127590 | RSD 212 AV SE FLD RSK RDUCTN | RSD C W DRAINAGE PRESERVATION | No | Bleasdale, Don | Drainage | No | No | Capital Project
IMPLEMENT | 1129582 | RSD EMERGENT NEED 3855 |  | No | Foote, Mark | Administrative | No | No | Capital Project
IMPLEMENT | 1129583 | RSD GRANT CONTINGENCY 3855 |  | No | Foote, Mark | Administrative | No | No | Capital Project
IMPLEMENT | 1129584 | RSD CWP QUICK RESPONSE | RSD CWP QUICK RESPONSE | Yes | Mitchell, Patricia | Roadside | No | No | Capital Project
IMPLEMENT | 1129585 | RSD CWP ROADWAY PRESERVATION | RSD CWP ROADWAY PRESERVATION | Yes | Moore, Paul | Roadway | No | No | Capital Project
IMPLEMENT | 1129586 | RSD CWP DRAINAGE PRESERVATION | RSD CWP DRAINAGE PRESERVATION | Yes | Shular, Ryan | Drainage | No | No | Capital Project | 12/29/2021 Report for January 4, 2022 meeting Complete drainage design plans for drainage crew construction. Drainage crews will continue to work on permitted drainage projects: #5-46835 75 Ave SW @ #25613 There are signed plans ready for construction: #3-148801 80th Avenue South B/T South 114th Street and South 113th Street. Plans signed on December 10, 2021. #3-148891 SE 145th Street @ 167th Avenue SE locations on SE 145th Street. Plans were signed on October 15, 2021. #2-135814 Preston Fall City Road SE 1,000 FT SW of D/W #7831,plans signed on 2/8/2021. #4-46516 (#4-2131) SE 322nd Street @ 194th Avenue SE. Plans signed on September 3, 2021. #5-159949: 93rd Avenue SW @ #16402. Plans signed on September 3, 2021 #3-45723 (3-2228) Renton Ave S @ 74 Ave S, plans signed on 3/25/2021 #4-46516 (#4-2131) 194 AV SE @ SE 322 ST, plans signed on 9/3/2021 |  | 12/28/2021 report for January 4, 2022 meeting: Snow occurred on December 25, 2021 12/2/2021 Report for December 2021: 1) new design staff and the fact that we have lack of utility laborers and now there is only one drainage crew instead of two drainage crews where we got two crews for the first half of the year 2) there's a lack of utility laborers and because only one crew that means we spend less budget and then we may have some carryover budget that's a result of that.
PLANNING | 1129587 | RSD CWP GUARDRAIL PRESERVATION | RSD CWP GUARDRAIL PRESERVATION | Yes | Mott, Linda | Roadside | No | No | Capital Project
IMPLEMENT | 1129588 | RSD CWP BRIDGE PRIORITY MAINT | RSD CWP BRIDGE PRIORITY MAINT | Yes | Roark, Ben | Bridges & Structures | No | No | Capital Project | Jan 1 2022 Update 122i North Fork: install headers at joints 55 bear creek: install emergency repair to stabilize pier. 3179 SPB: remove log jam 3035a coal creek: install urgent floor beam repair Begin 2022 project site investigations with Ross. October Update 3052 Boise Creek: Finish patching unfinished edges around edges main spall repair. 3165a cedar ramp: begin construction 122i North fork: install headers at joints, install compression seals. 122k Norman: procure new rubber joint seals 1008g Raging river: Added additional scope to project: concrete spall repairs on pier caps 920a Rutherford Creek: begin approach repair 3109 Soos Creek: begin approach repair 3179 South Park bridge: finish repair plan, submit project number 2022: put together bridge washing plans for permitting |  | Jan 1 2022. 5044 4 Creek Ranch: ponding on deck. Ask Broch if we received any calls from the community during last snow event. October Update 122i N Fork: Paving crew informed us they could not place new asphalt on deck to blend in new joints to match existing asphalt (steel joints stick up slightly at fog line). Going to install silspec headers instead, but might create too much of a bump. If we leave just the steel joints sticking up it is fine for cars but could get caught on snow plow blade. 5044 4 Creek ranch: 2020 project completed in early 2021, ponding on deck due to lack on crown in new deck pavement. Likely needs to be grinded some and repaved with a crown. Lindy is concerned that the paving crew does not have the needed expertise and equipment to do a project with tight tolerances such as this, she recommends not trying to repave this with our in-house crew
IMPLEMENT | 1129590 | RSD CWP HIGH COLLISION SAFETY | RSD CWP HIGH COLLISION SAFETY | Yes | Mott, Linda | Traffic Control | No | No | Capital Project
IMPLEMENT | 1129591 | RSD CWP SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | Yes | Hafele, Brendan | Traffic Control | No | No | Capital Project
IMPLEMENT | 1129592 | RSD EMERGENT NEED 3865 |  | No | Foote, Mark | Administrative | No | No | Capital Project
IMPLEMENT | 1129593 | RSD GRANT CONTINGENCY 3865 |  | No | Foote, Mark | Administrative | No | No | Capital Project
PLANNING | 1129594 | RSD CWP GUARDRAIL CONSTRUCTION | RSD CWP GUARDRAIL CONSTRUCTION | Yes | Mott, Linda | Roadside | No | No | Capital Project
DESIGN | 1129595 | RSD OLD CASCADE/MILLER BR WEST |  | No | Lyou, John | Bridges & Structures | Yes | No | Capital Project |  |  | 1. US Forest Services property right acquisition condition. 2. BNSF property right issues.
DESIGN | 1129596 | RSD OLD CASCADE/MILLER BR EAST |  | No | Lyou, John | Bridges & Structures | Yes | No | Capital Project |  |  | 1. US Forest Services property right acquisition condition. 2. BNSF property right issues.
PREDESIGN | 1129598 | RSD ISS HBRT RD@MAY VLLY IMPRV |  | No | Wang, Jun | Roadway | Yes | No | Capital Project | Jan 2022 - Negotiation phase 1. Conducting SOW Negotiation with selected Consultant (Transpo). 2. Schedule Consultant on board about middle of April ********************************************************************** December 2021 - Evaluation Phase 1. Proposal Evaluation meeting on 12/09/2021 2. Consultants Interviews on 12/16/2021 ********************************************************************** November 2021: Procurement - Solicitation Phase 11/1/2021 Ad on Seattle Times (ALREADY Shown on Seattle Times) - TWO Weeks 11/8/2021 Pre-proposed meeting 11/22/2021 Consultants submit Proposals. | Feb 2022, Negotiation Phase 1. Complete SOW and Start LOE Negotiation. 2. Consultant may be on board In middle April | Jan 2022 No issue, on schedule Nov. 2021 None ************************************************ Oct. 2021 None
DESIGN | 1129599 | RSD RENTON AVE PH III SIDEWALK |  | No | Linders, Jon | Roadside | Yes | No | Capital Project | January: - Resubmitted plans on 1/4 to permitting for C&G permitting. Requesting comments needed by 1/18. Received C&G Permit on 1/25. - Sent Project Specific Special Provisions and 100% Engineer's Estimate to Jerry for PS&E package assembly on 1/10. | - Continue ROW appraisal and negotiation (to be completed by end of February 2022) - Send completed ROW instruments to KC Permitting when received. - Continue Communication Plan - Start Spec Package | - Received SDOT SIP for construction bid. Once we have contractor on board, initiate permit amendment with precon materials.
IMPLEMENT | 1129714 | RSD NE STILLWATER HILL RD | RSD CWP ROADWAY PRESERVATION | No | Linders, Jon | Roadway | Yes | No | Capital Project | January: - Completing mulch and hydroseeding on 1/18. - ICI requested Physical Completion
IMPLEMENT | 1129716 | RSD DIVISION 1 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129717 | RSD DIVISION 2 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129718 | RSD DIVISION 3 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129720 | RSD DIVISION 4 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129721 | RSD DIVISION 5 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129722 | RSD DIVISION 6 DRAINAGE | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129723 | RSD DIVISION 1 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129724 | RSD DIVISION 2 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129725 | RSD DIVISION 3 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129726 | RSD DIVISION 4 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129727 | RSD DIVISION 5 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129728 | RSD DIVISION 6 SHOULDERING | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | Yes | No | Capital Project
IMPLEMENT | 1129841 | RSD CIP OVERSIGHT 3855 |  | No | Foote, Mark | Administrative | Yes | No | Capital Project
IMPLEMENT | 1130303 | RSD CIP OVERSIGHT 3865 |  | No | Foote, Mark | Administrative | Yes | No | Capital Project
PLANNING | 1130705 | RSD FC SNQ VLY MJR FL MIT STDY | RSD CWP FLOOD CONTROL DISTRICT | No | Truong, Trinh | Drainage | Yes | No | Capital Project
PLANNING | 1130706 | RSD FC NE8ST@ALLEN LAKE OUTLET | RSD CWP FLOOD CONTROL DISTRICT | No | Lyou, John | Drainage | Yes | No | Capital Project |  |  | 1. ROE acquisition 2. Community outreach
IMPLEMENT | 1130707 | RSD FC 162 AVE SE @ SE 166 CT | RSD CWP FLOOD CONTROL DISTRICT | No | Lyou, John | Drainage | Yes | No | Capital Project
CLOSEOUT | 1130708 | RSD FC DAVID POWELL RD RPR | RSD CWP FLOOD CONTROL DISTRICT | No | Lyou, John | Drainage | No | No | Capital Project
DESIGN | 1130710 | RSD FC 380 PL @SR-164 CDR | RSD CWP FLOOD CONTROL DISTRICT | No | Lyou, John | Drainage | Yes | No | Capital Project |  |  | 1. TCE property right acquisition. 2. No design engineer. 3. Plan preparation will be shared among available engineers
CLOSEOUT | 1130962 | RSD BLK DMND-RVNSDL RD SLD RPR | RSD QUICK RESPONSE | No | Shular, Ryan | Contingencies | No | No | Capital Project
CLOSEOUT | 1131132 | RSD 2017-18 NEW GRDL CONSTRUCT | RSD CWP GUARDRAIL CONSTRUCTION | No | Bleasdale, Don | Roadside | No | No | Capital Project
DESIGN | 1131157 | RSD HGH COLLSN SIGHTLINE IMPV | RSD CWP HIGH COLLISION SAFETY | No | Karinen, Martin | Traffic Control | Yes | No | Capital Project | Revise plans for removal of fence construction. Resign plans again. Make changes to special provisions for plan revisions and ad date moving to 2022.
IMPLEMENT | 1131162 | RSD HGH COLLSN SIGNAL MOD | RSD CWP HIGH COLLISION SAFETY | No | Zhen, Haiyan | Traffic Control | No | No | Capital Project
CLOSEOUT | 1131163 | RSD HGH FRICTION SURF TMT | RSD CWP HIGH COLLISION SAFETY | No | Sahagun, Dan | Traffic Control | No | No | Capital Project
DESIGN | 1131235 | RSD S 360ST&MILITARY RD RNDABT |  | No | Karinen, Martin | Traffic Control | Yes | No | Capital Project | Get R/W plans signed. Complete TIR Addendum and continue 90% design. |  | Submit R/W plans for re-review. Complete 90% design. ROW acquisition is the critical path to meeting grant obligation date of June 2023
HOLD | 1131236 | RSD S LANGSTON RD&59 AV RNDABT |  | No | McManus, Aileen | Traffic Control | No | No | Capital Project
IMPLEMENT | 1131333 | RSD CWP FLOOD CONTROL DISTRICT | RSD CWP FLOOD CONTROL DISTRICT | Yes | Lyou, John | Drainage | No | No | Capital Project
CLOSEOUT | 1131387 | RSD 2017 CW PVMNT PRESERVATION | RSD CWP ROADWAY PRESERVATION | No | Moore, Paul | Roadway | No | No | Capital Project
CLOSEOUT | 1131508 | RSD DIV 4 FACLTY IMPRVMT 17-18 | RSD FACIL PRESERVATION C/WIDE | No | Kosai-Eng, Joann | Maintenance Facilities | No | No | Capital Project
DESIGN | 1131511 | RSD SAHALEE WY NE 46000 BLK | RSD CWP DRAINAGE PRESERVATION | No | Dulan, Lica | Drainage | Yes | No | Capital Project
DESIGN | 1131526 | RSD SE PTRVSKY & 134 A SE | RSD CWP DRAINAGE PRESERVATION | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Complete Final Scope of Work, LOE and RON for Amendment 14 January 2022 Submit Final Scope of Work, LOE and RON for Amendment 14 November 2021 Complete Scope of Work and Level of Effort for the Amendment 13 to complete the project Finalize FEMA grant documents | February 2022 Issue NTP for Amendment 14 and re-start P,S&E | processing Amendment 14 and re-start project design
IMPLEMENT | 1131557 | RSD 17-18 SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | No | Brown, Keith | Traffic Control | No | No | Capital Project
IMPLEMENT | 1131582 | RSD NE WD/DVL CULVERT REPL | RSD QUICK RESPONSE | No | Shular, Ryan | Contingencies | No | No | Capital Project
DESIGN | 1131671 | RSD SE PTRVSKY @ 151ST A SE | RSD CWP DRAINAGE PRESERVATION | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Create an in-house design team to complete projects C and D January 2022 Create an in-house design team to complete projects C and D November 2021 Complete Scope of Work and Level of Effort for the Amendment 14 to complete the project | February 2022 Have in-house design team review 90% plans and develop a schedule to complete projects C and D | December 2021 Availability of in-house design staff to complete project design
DESIGN | 1131672 | RSD SE PTRVSKY @20300BLK | RSD CWP DRAINAGE PRESERVATION | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Create an in-house design team to complete projects C and D January 2022 Create an in-house design team to complete projects C and D November 2021 Complete Scope of Work and Level of Effort for the Amendment 14 to complete the project | February 2022 Have in-house design team review 90% plans and develop a schedule to complete projects C and D | December 2021 Availability of in-house design staff to complete project design
CLOSEOUT | 1131693 | RSD UNION HILL@225 BOXCULVRT | RSD CWP DRAINAGE PRESERVATION | No | Truong, Trinh | Drainage | No | No | Capital Project
PLANNING | 1132446 | RSD S LANGSTN RD@132ST DRG IMP | RSD CWP DRAINAGE PRESERVATION | No | Shular, Ryan | Drainage | Yes | No | Capital Project | Project was terminated in May, 2015. There will be no additional charges to the project.
PREDESIGN | 1132448 | RSD SW 108ST@10 AVE SW DRG IMP | RSD CWP DRAINAGE PRESERVATION | No | Shular, Ryan | Drainage | No | No | Capital Project
DESIGN | 1132450 | RSD 177 AVE SE DRG IMP | RSD CWP DRAINAGE PRESERVATION | No | Shular, Ryan | Drainage | No | No | Capital Project
PREDESIGN | 1132523 | RSD GREEN RVR RD S28728 DR IMP | RSD CWP DRAINAGE PRESERVATION | No | Shular, Ryan | Drainage | No | No | Capital Project
DESIGN | 1132710 | RSD DRAIN IMP SAHALEE-4800 | RSD CWP DRAINAGE PRESERVATION | No | Dulan, Lica | Drainage | Yes | No | Capital Project | ROW: Continue the acquisition process. Design: Create mitigation plan.
CLOSEOUT | 1132958 | RSD 15 MILE BRDG #1384A LOAD | RSD QUICK RESPONSE | No | Martin, TingTing | Contingencies | No | No | Capital Project
CLOSEOUT | 1133219 | RSD VASHON HWY SW PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | No | No | Capital Project
CLOSEOUT | 1133220 | RSD 2018 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Moore, Paul | Roadway | No | No | Capital Project
CLOSEOUT | 1133413 | RSD SE SAWYER RDG OVERLAY | RSD CW ROADWAY PRESERVATION | No | Moore, Paul | Roadway | No | No | Capital Project
CLOSEOUT | 1133440 | RSD MOUNT VIEW RD REPAIR | RSD CWP QUICK RESPONSE | No | Shular, Ryan | Roadside | No | No | Capital Project
CLOSEOUT | 1133757 | RSD 2018 BITUM SURF TREATMENT | RSD CWP ROADWAY PRESERVATION | No | Moore, Paul | Roadway | No | No | Capital Project
CLOSEOUT | 1133864 | RSD NE NVLTY HILL RD TRAIL | RSD CWP QUICK RESPONSE | No | Sahagun, Dan | Roadside | No | No | Capital Project
PLANNING | 1134079 | RSD KENTKANGLEY LNDSBRG RNDABT |  | No | Linders, Jon | Traffic Control | Yes | No | Capital Project
PLANNING | 1134080 | RSD WDDUV SNOQ VALLEY IMPROVE |  | No | Linders, Jon | Roadway | Yes | No | Capital Project | 1. ROW Group continue discussions of roundabout layout with PAO. |  | - No CN Funding
DESIGN | 1134081 | RSD REDMOND RIDGE DR NE RNDABT |  | No | Karinen, Martin | Traffic Control | Yes | No | Capital Project | - Continue ROW appraisal and negotiation requirements -Peer review of plans and then re-sign plans - Continue utility coordination |  | Continue ROW appraisal and negotiation requirements
IMPLEMENT | 1134082 | RSD FACILITIES LED CONVERSION |  | No | Kosai-Eng, Joann | Maintenance Facilities | Yes | No | Capital Project
PREDESIGN | 1134083 | RSD COVINGTON WAY SE IMPROVE |  | No | Linders, Jon | Roadway | No | No | Capital Project
IMPLEMENT | 1134093 | RSD CWP TRAFFIC SAFETY | RSD CWP TRAFFIC SAFETY | Yes | Brown, Keith | Traffic Control | No | No | Capital Project
LAND | 1135042 | RSD VASHON MAINT FACILITY REPL |  | No | Kosai-Eng, Joann | Maintenance Facilities | No | No | Capital Project
LAND | 1135043 | RSD NE MAINT FACILITY REPL |  | No | Kosai-Eng, Joann | Maintenance Facilities | No | No | Capital Project
PLANNING | 1135044 | RSD PRSTN MAINT FACILTY BLDOUT |  | No | Kosai-Eng, Joann | Maintenance Facilities | No | No | Capital Project
IMPLEMENT | 1135045 | RSD CWP CLVRT RPLCMT FISH PASS | RSD CWP CLVRT RPLCMT FISH PASS | Yes | Cassidy, Jon | Drainage | No | No | Capital Project
DESIGN | 1135046 | RSD MAINT HDQTRS BLDG D REHAB |  | No | Ho, Alex | Maintenance Facilities | No | No | Capital Project
IMPLEMENT | 1135073 | RSD CWP 2019-20 BRIDGE SAFETY | RSD CWP 2019-20 BRIDGE SAFETY | Yes | Truong, Trinh | Bridges & Structures | No | No | Capital Project
IMPLEMENT | 1135997 | RSD COAL CREEK BRG 3035A REPL |  | No | Martin, TingTing | Bridges & Structures | Yes | No | Capital Project | Contractor submitted draft load calculations and revised temporary bridge plans. Project team currently reviewing the submittal. Maintenance completed repairs to areas identified by bridge inspection team | Plan to complete installation of temporary bridge by end of February Contractor to continue with project submittals | Construction of Replacement Bridge delayed due to fish window limitations and delay in procuring various bridge materials. Construction of new bridge planned to start Q2 2022.
DESIGN | 1135998 | RSD AMES LK TRS BRG 1320A REPL |  | No | Truong, Trinh | Bridges & Structures | Yes | No | Capital Project | Project team reviewed 90% Design Package. 90% Design Review Meeting scheduled 2/17/22. Received updated TIR from Jacobs and KC project team completed review Held field meeting 1/7/22 to discuss felled tree placement; received direction from management to have consultant proceed with hydraulic analysis for LWD placement options Received revised ROW plans from Jake, ROW team to review Utility Coordination meeting held 1/25/22 Prepared draft SOW for Environmental Services Amendment | 90% Design Review Meeting scheduled 2/17/22. Provide compiled comments on TIR to Jacobs Receive draft Hydraulic Analysis with felled tree placement options from consultant Finalize SOW and prepare LOE for Environmental Services Amendment | Fish Window : July 15 to September 30
DESIGN | 1135999 | RSD UPR TOKUL CK BRG 271B REPL |  | No | Martin, TingTing | Bridges & Structures | Yes | No | Capital Project | January 2022: Final Design - 100% - Obtain all Permits for project. - Finalize TCE agreements with property owners. - Assemble Bid package and Ready to Ad documents. - Start on Implementation phase Amendment. |  | - C&G Permit review/approval will be a critical path for meeting March 2022 advertisement. - ROW acquisition needs to be complete for C&G permit approval.
DESIGN | 1136000 | RSD BARING BRG 509A REPL |  | No | Truong, Trinh | Bridges & Structures | Yes | No | Capital Project | Executed Amendment #5 - Added work for geomorphic, geotechnical and 90% design Continued 90% design (anticipated to be complete June 2022) Continued discussion of temporary bridge in order to refine hydraulic analysis HNTB coordinated with the subconsultant to finalize SOW for amendment to add ROW Plans and additional ROW acquisition services. Currently being reviewed by KC. Informed that temporary bridge will trigger a Corps Individual Permit and a Water Quality Certificate. Both permits have a public notification and appeal process. | Continue 90% design (anticipated to be complete June 2022) Meet with permitting agency to discuss temporary flood easements needed for temporary bridge construction Continue to refine SOW for amendment to add ROW Plans and additional ROW acquisition services Update overall project schedule to accommodate longer permit timeline which will delay construction start date. | - Certification of appropriateness is dependent upon KC Landmark Commission's approval. - Bridge is in the South Fork Skykomish channel migration zone - scour caused by river migration - Continued delay of 90% Design could jeopardize permit and ROW acquisition
IMPLEMENT | 1136001 | RSD 277TH ST BRG 3126 REPL |  | No | Premachandra, Hiromal | Bridges & Structures | Yes | No | Capital Project | January 2022: Implementation/Closeout - Final Punchlist items to be completed in March 2022. - Budget Increase Request for project overruns. - As-Built plan development. |  | Project budget may be impacted by a bust in the approach slab quantity. Anticipated increase is within 15% of total approved project budget.
CLOSEOUT | 1136084 | RSD 2019-20 NEW GRDRAIL CONST | RSD CWP GUARDRAIL CONSTRUCTION | No | Mott, Linda | Roadside | Yes | No | Capital Project
IMPLEMENT | 1136085 | RSD 2019-20 GUARDRAIL PRESRVTN | RSD CWP GUARDRAIL PRESERVATION | No | Mott, Linda | Roadside | Yes | No | Capital Project | Advertise Tier 3 package (incl. 4 bridge) Signed WO for evaluation of bridges; consultant begins |  | Tracking progress by utility companies to relocate overhead and underground lines for more than 50% of the guardrail locations
DESIGN | 1136086 | RSD 218TH AV SE RECONSTRUCTION | RSD CWP ROADWAY PRESERVATION | No | Linders, Jon | Roadway | Yes | No | Capital Project | January: - Requested DBE goal from WSDOT STIP approval in mid February for CN obligation | - Complete Pre-Ad Checklist by early January. - Complete Construction Funding Obligation paper work. - Continue Communication Plan. - Advertise in January/February
DESIGN | 1136228 | RSD PET RD AT 134TH CULVERT |  | No | Mitchell, Mark C. | Drainage | No | No | Capital Project
PREDESIGN | 1136229 | RSD 180TH AT 408TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | January 2022 Reach out to Muckleshoot Planning Dept. to determine level of involvement of MIT and prepare requested information November 2021 Resume contract Coordinate with the Muckleshoot Planning Dept. to determine the decision making process to select the preferred alternative Prepare revised schedule and cost impacts due to time constraints for coordination with Muckleshoot Tribal Council |  | January 2022 Monitor response from Muckleshoot Planning Dept.
PLANNING | 1136230 | RSD FAIRWOOD E OF 151 CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Cassidy, Jon | Drainage | Yes | No | Capital Project
PREDESIGN | 1136231 | RSD 185TH AT 179TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | January 2022 Complete CDR Complete BOD Complete 30% plans Prepare and negotiate the FINAL Scope of Work and Level of Effort for Phase II (prepare 30% plans to 100% P,S&E |  | December 2021 Construction methodology to keep sole access road (185th Ave NE) open during construction
DESIGN | 1136232 | RSD 18430 NE 128TH WY CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Review Consultants SCS under usage letter and meet internally to address Consultants responses to SCS under usage letter January 2022 Review/address Consultants responses to SCS under usage letter November 2021 Complete 100% plans Consultant has indicated they will submit a request for an amendment | February 2022 Meet with Consultant to discuss SCS under usage letter | December 2021 SCS usage Amendment justification for additional work
DESIGN | 1136233 | RSD LAKE JOY AT 118TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Quach, Dieu | Drainage | Yes | No | Capital Project | 12/29/2021 Report for January 4, 2022: Mitigation (per the permit, this task has to be finished before the end of the winter: 3/20/2022) 12/2/2021 Report for December 2021: Mitigation (per the permit, this task has to be finished before the end of the winter: 3/20/2022)
PREDESIGN | 1136234 | RSD WD DUV AT 172ND CULVERT |  | No | Wang, Jun | Drainage | Yes | No | Capital Project | Q1 2022 - Final Design Phase Jan 2022: 1. Completed 60% review comments meet, KPFF started 90% PS&E package 2. Monthly and Bi-weekly design meeting 3. property sent offers to owner (12/09/2021) KPFF to continue work on the plans. 60% review comments are due. Monthly team meeting and design meeting. Work on the project baseline process. | KPFF continue on 90% PS&E package Complete Schedule revision, Baseline and DCM form reviewed and approved, | Construction moved to 2023: need coordinate with down hill intersection roundabout design, and potential need KPFF design surface water treatment facility (Out of SOW), need Consultant update BOD from Stream Sim to Roughened channel per permitting agency request. need 90% for permitting application, Completing design and environmental permitting for summer 2022 Contractor construction. Council approval of $4.3 million in new REET funding for construction occurred in December 2021.
DESIGN | 1136235 | RSD AVONDALE AND 144TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Review Consultants SCS under usage letter and meet internally to address Consultants responses to SCS under usage letter January 2022 Review/address Consultants responses to SCS under usage letter November 2021 Complete 100% plans Consultant has indicated they will submit a request for an amendment | February 2022 Meet with Consultant to discuss SCS under usage letter | December 2021 SCS usage Amendment justification for additional work
DESIGN | 1136236 | RSD 165TH AND 176TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Review Consultants SCS under usage letter and meet internally to address Consultants responses to SCS under usage letter January 2022 Review/address Consultants responses to SCS under usage letter November 2021 Complete 100% plans Consultant has indicated they will submit a request for an amendment | February 2022 Meet with Consultant to discuss SCS under usage letter | December 2021 SCS usage Amendment justification for additional work
PREDESIGN | 1136237 | RSD S 370TH ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Lyou, John | Drainage | Yes | No | Capital Project |  |  | 1. ROE 2. No Design Engineer
DESIGN | 1136238 | RSD 33609 NE 24TH ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Quach, Dieu | Drainage | Yes | No | Capital Project | 12/28/2021 report for January 4, 2022 meeting: Survey the Girls Scout Property for locating and monitoring the beaver dams at downstream Finalize BOD to complete the ACOE permit application Continue to work on CDR completion. Continue to finish the design plans and the team charter. 11/2021 November report: Survey the Girls Scout Property for locating and monitoring the beaver dams at downstream Finalize BOD to complete the ACOE permit application Continue to work on CDR completion. Continue to finish the design plans and the team charter. |  | 12/28/2021 report for January 4, 2022 meeting: Easement acquisition required from new owner of the house #33609. DCM form is being processed for schedule extension. 11/2021 November 2021 report Received $950,000 Flood Reduction Grant for construction on 9/15/2021. Construction scheduled in summer 2023
PLANNING | 1136239 | RSD 317TH AND THOMAS CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Shular, Ryan | Drainage | Yes | No | Capital Project | 12/29/2021 Report for January 4, 2021: Work on design options, proposed plan, profile, and CDR if time allowed 12/2/2021 Report for December 2021 Work on design options, proposed plan, profile, and CDR if time allowed |  | Shallow stream crossing may require the road to be raised over the new concrete box culvert. Aerial utility lines will need to be relocated for construction. Temporary Construction Easements to acquire for construction. Construction is not funded. $1,100,000 plus or minus is the likely construction cost.
IMPLEMENT | 1136241 | RSD 28278 GREEN RVR RD CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Shular, Ryan | Drainage | No | No | Capital Project
IMPLEMENT | 1136351 | RSD CURB RAMP REPLACEMENT 3855 | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | No | No | Capital Project
IMPLEMENT | 1136352 | RSD 2019 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | No | No | Capital Project
DESIGN | 1136419 | RSD SE 432ND ST CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Dulan, Lica | Drainage | Yes | No | Capital Project | Baseline project upon receiving the updated construction cost estimate. Apply for grant. |  | The construction is not yet funded. The ROW acquisition and permit applications are on hold until the construction is funded.
DESIGN | 1136580 | RSD S 360TH ST SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | No | Karinen, Martin | Traffic Control | Yes | No | Capital Project | Revise plans for removal of fence construction. Resign plans again. Make changes to special provisions for plan revisions and ad date moving to 2022.
DESIGN | 1136582 | RSD S 298TH ST SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | No | McManus, Aileen | Traffic Control | Yes | No | Capital Project
CLOSEOUT | 1136631 | RSD JUDD CK BRD 3184 RPR | RSD CWP QUICK RESPONSE | No | O'Day, Jamie | Roadside | Yes | No | Capital Project
DESIGN | 1136633 | RSD PATTON BRD 3015 BKT RPR | RSD CWP QUICK RESPONSE | No | Jiang, Stephen | Roadside | Yes | No | Capital Project
CLOSEOUT | 1136646 | RSD 42ND AVE S SCHOOL PTHWY | RSD CWP SCHOOL ZONE SAFETY | No | McManus, Aileen | Traffic Control | Yes | No | Capital Project
IMPLEMENT | 1136709 | RSD TRAFFIC CALMING | RSD CWP TRAFFIC SAFETY | No | Mott, Linda | Traffic Control | Yes | No | Capital Project
IMPLEMENT | 1136711 | RSD ROADWAY LIGHTING | RSD CWP TRAFFIC SAFETY | No | Mott, Linda | Traffic Control | Yes | No | Capital Project
PLANNING | 1136712 | RSD RADAR SPEED SIGNS | RSD CWP TRAFFIC SAFETY | No | Kunihiro, Lisa | Traffic Control | Yes | No | Capital Project
IMPLEMENT | 1136715 | RSD LEFT TURN PHASING | RSD CWP TRAFFIC SAFETY | No | Zhen, Haiyan | Traffic Control | Yes | No | Capital Project
IMPLEMENT | 1136716 | RSD TRANSVERSE RUMBLE SIGNS | RSD CWP TRAFFIC SAFETY | No | Mott, Linda | Traffic Control | Yes | No | Capital Project
PLANNING | 1136931 | RSD SCALE DBASE RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | No | Crippen, Mike | Administrative | Yes | No | Capital Project
PLANNING | 1136932 | RSD BIZDOC MAP VLT RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | No | Crippen, Mike | Administrative | No | No | Capital Project
PLANNING | 1136933 | RSD CUTRL RES DBASE RPLCMNT | RSD CWP OBSOLETE IT SYS RPLMNT | No | Crippen, Mike | Administrative | Yes | No | Capital Project
PLANNING | 1137364 | RSD WSDE HWY SW DEGRADATN | RSD CWP QUICK RESPONSE | No | Posey, Norton | Roadside | No | No | Capital Project
HOLD | 1137577 | RSD 304 ST HAUL RD MITGN | RSD CWP QUICK RESPONSE | No | Daggs, Victor | Roadside | No | No | Capital Project
IMPLEMENT | 1137584 | RSD MIDDLE FORK RD RPR | RSD CWP QUICK RESPONSE | No | Cassidy, Jon | Roadside | No | No | Capital Project
IMPLEMENT | 1137752 | RSD FLMNG GYSR BRG 3024 PNTG | RSD CWP BRIDGE PRIORITY MAINT | No | Martin, TingTing | Bridges & Structures | Yes | No | Capital Project
CLOSEOUT | 1137860 | RSD 2019 DVD PWLL RD RPR 36621 | RSD CWP QUICK RESPONSE | No | Lyou, John | Roadside | No | No | Capital Project
IMPLEMENT | 1137862 | RSD 2020 HGH FRCTN SFC TRTMT | RSD CWP HIGH COLLISION SAFETY | No | Linders, Jon | Traffic Control | Yes | No | Capital Project | January: - Requested schedule from contractor - Working on Change Order for repair of 2 concrete panels | - Need Contractor's construction schedule to see if any work will be done in Fall 2021. - Continue change order plan revisions for concrete panel replacements. | Awaiting Construction Schedule
IMPLEMENT | 1137996 | RSD 2020 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | Yes | No | Capital Project
DESIGN | 1138330 | RSD CVGTN SWYR SGHTLN IMPR | RSD CWP HIGH COLLISION SAFETY | No | Wang, Jun | Traffic Control | Yes | No | Capital Project | Jan 2022 - 60% PS&E 1. Continue 60% design (Plan and SP good shape now) 2. R/W Plan revised 3. Start to prepare Permitting plan and preapplication 4. Baseline and Design Memo under review ********************************************************************************************* December 2021 - Start 60% Design (Dec. 13, 2021) 1. Survey field work done on 12/01/2021 for additional survey. 2. Get Design Memo signed - to be reviewed by Wally, Rose and JoAnn 3. Get Baseline approved - Meeting with Pat, Aileen and Wally 4. Meeting with design team for 60% PS&E package and start to 60% ********************************************************************************************** November 2021 - 30% Design Phase (Due 11/26/2021) 1. 30% plan and EE review by project review team 2. 30% review coordination meeting on 11/18/2021 3. ESJ Working Planning meeting (11/2/2021, DONE) - Thanks to Jennifer and Betsay, and 30% Eco Charette Meeting (11/8/2021) 4. After 30% coordination meeting, will Start 60% design | Feb and March 2022 1. Complete 60% PS&E package 2. Get Baseline and Design Memo approved 3. Get R/W reviewed and ready for Acquisition. 4. Continue on Permitting | Jan 2022 No issues, on tracking December 2021 No Issues November 2021 No issues at this moment ********************************************************************** October 2021 Need additional Survey for 60% design - waiting Renewed ROE for survey field work. Maura sent emails to both owners on 10/13/21, and mailed hard copies on 11/01/2021, will reach out at end of this week if not receive ROEs. No other issues at this moment.
HOLD | 1138337 | RSD FC FSH HTCHRY BRG 61B RPR | RSD CWP FLOOD CONTROL DISTRICT | No | Roark, Ben | Drainage | Yes | No | Capital Project
DESIGN | 1138339 | RSD FC S 106 ST DRAINAGE IMPRV | RSD CWP FLOOD CONTROL DISTRICT | No | Quach, Dieu | Drainage | Yes | No | Capital Project | 12/28/2021 report for January 4, 2022 meeting: CDR to be reviewed and move forward to get approval. EU staff to continue to work on the ACOE permit application. Easement appraisal is in process. 11/2021 November report: Continue to work on CDR EU staff continue to work on the ACOE permit application Property Services continue to work on Easement appraisal process |  | Easement acquisition required from five properties. Construction scheduled for 2021 is now in summer 2022. DCM form is being processed for schedule extension. 12/28/2021 report for January 4, 2022 meeting: Easement acquisition required from five properties. Construction scheduled for 2021 is now in summer 2022. DCM form is being processed for schedule extension.
IMPLEMENT | 1138763 | RSD 2019-20 GUARDRAL PRSRVTN 2 | RSD CWP GUARDRAIL PRESERVATION | No | Mott, Linda | Roadside | Yes | No | Capital Project
PREDESIGN | 1138913 | RSD BOISE X BRDG #3055A REPL |  | No | Jin, Henry | Bridges & Structures | Yes | No | Capital Project | Key activities planned for the month of January 2022: - Continue with 30% Design - 30% Kickoff Meeting - Coordination with supporting teams |  | 1. DNRP Foothills Trail Project: Construction from 2022 - 2023. Overlapping footprint and tie ins for overlapped facilities are incorporated in design, schedule modifications and contract language additions to DNRP project reduce conflict and construction coordination. Pending final drawings and updated construction schedule from Foothills Trail Project Team. 2. Funding - Anticipating additional funding needs for implementation to be clarified at 30% design.
DESIGN | 1138914 | RSD FIFTN MILE CRK#493C B REP |  | No | Jose, Jessy | Bridges & Structures | Yes | No | Capital Project | Key activities planned for the month of January *Final Stream re-design and hydraulic analysis submittal from Consultant *99% design updates *ROW appraisal process (Cont'd) *Utility coordination (Cont'd) *Permit coordination (Cont'd) *Public outreach and website maintenance (Cont'd) *Invoice processing (Cont'd) |  | Tribe coordination ROW acquisition Public outreach and comments from public on closures
PREDESIGN | 1138918 | RSD 16TH AVE PED IMPRVMNTS |  | No | Mott, Linda | Roadside | Yes | No | Capital Project | 1. Monetization comparison - federalized vs local funds 2. Advance R/W plans; submit to WSDOT 3. Complete first round of outreach 4. Select alternative 5. Complete CDR including outreach findings 6. Complete 30% scorecard and C&D plan after preferred option is selected 7. Advance design, including drainage design by Wes Kameda |  | Public outreach: successfully reaching business, building and residents of White Center to get a consensus on selected alternative Public outreach: potential backlash to asking for businesses to pay for sign encroachments; reducing parking at 2 businesses by 2-3 spaces each Grant: spent 75% of design funds to reach 30% then paused; outreach and R/W plan development charged to another number so created appearance that work was not taking place; discussions between JoAnn and WSDOT yielded it is acceptable to request extension beyond obligation date (with 10% as county share) Languages/ESJ - will need interpreters to negotiate R/W acquisitions; increasing number of contacts
PREDESIGN | 1138947 | RSD 284TH AVE S 46913 CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Dulan, Lica | Drainage | Yes | No | Capital Project | November 2021: * Gate 2 approval * 30% design *Complete ROW Plan December 2021: *Gate 2 approval pending the CDR signing *Complete ROW Plan *Baseline project *30% design *ESJ and Eco-Charrette meetings scheduled |  | ROE request sent to Drainage District #6 for additional survey downstream of the culvert. A meeting with the district commissioner will be scheduled to provide additional information.
PLANNING | 1139144 | RSD SE REINIG RD DRNG IMPR CUL |  | No |  | Drainage | No | No | Capital Project
PREDESIGN | 1139145 | RSD SE GRN VLLY & 218 AVE INT |  | No | Linders, Jon | Traffic Control | Yes | No | Capital Project | January: - Received signed Sponsor Charter on 1/12. - PE funding setup and ready for charging on 1/14. - Identified Enviro and Materials Lead for project | - Waiting on ROEs - Request survey once ROEs received - Hold Kickoff Meeting
PLANNING | 1139146 | RSD RAINIER S & LKRDG DR INT |  | No | Zhen, Haiyan | Roadway | Yes | No | Capital Project
IMPLEMENT | 1139147 | RSD CWP ADA PROGRAM | RSD CWP ADA PROGRAM | Yes | Rettig, Brandy | Roadway | Yes | No | Capital Project
CLOSEOUT | 1139236 | RSD JUDD CK BRG 3184 RECONT | RSD CWP BRIDGE PRIORITY MAINT | No | Jose, Jessy | Bridges & Structures | Yes | No | Capital Project
PREDESIGN | 1139286 | RSD CWP BRIDGE LOAD UPGRD SFTY | RSD CWP BRIDGE LOAD UPGRD SFTY | Yes | Jiang, Stephen | Bridges & Structures | No | No | Capital Project
PREDESIGN | 1139716 | RSD S LANGSTN RD@125TH DRG IM | RSD CWP DRAINAGE PRESERVATION | No | Mitchell, Mark C. | Drainage | Yes | No | Capital Project | February 2022 Complete Final Scope of Work, LOE and RON Reviewing ROE's January 2022 Execute contract Begin Design and field work November 2021 Finalize negotiation for Level of Effort and Level of Effort Finalize remaining contract documents Review and evaluate remaining Consultant submittal's | February 2022 Execute contract Begin Design and field work | December 2021 Need right-of-entries (ROE"s) to begin survey work - no response from either group
IMPLEMENT | 1139744 | RSD 4-CREEK-RANCH 5044 DECK | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1139749 | RSD MMS REPLACEMENT |  | No | Murata, Kathi | Administrative | Yes | No | Capital Project
NOT SET | 1139810 | RSD BEALL RD SW RESTOR CULVERT |  | No |  | Drainage | No | No | Capital Project
PLANNING | 1139811 | RSD SE384TH DRNG IMPRV CULVERT |  | No | Lyou, John | Drainage | Yes | No | Capital Project
IMPLEMENT | 1139815 | RSD 356TH DR SE WINTER 2020 | RSD CWP QUICK RESPONSE | No | Truong, Trinh | Roadside | Yes | No | Capital Project
PREDESIGN | 1140858 | RSD 244TH AVE NE WINTER 2020 | RSD CWP QUICK RESPONSE | No | Wang, Jun | Roadside | Yes | No | Capital Project | Jan 2022 - Conceptual Design 1. Finalize new wall location 2. start the CDR and CD Plan **************************************************************************** December 2021: Pre Design Phase 1. Will start pre Design after receive the revised geo report, scheduled starting on 11/15/2021. ************************************************************* November 2021: Scheduled Pre design Start @ 11/15/2021 Will start Conceptual Design once receive the revised Geo technical report. |  | December 2021 No issues at this moment ********************************************************************* November 2021 waiting for revised Geo report to start pre design, holiday season, people took vacation **************************************************** October 2021 None at this moment
PREDESIGN | 1140905 | RSD 17401 SE 240 ST SE CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Dulan, Lica | Drainage | Yes | No | Capital Project | Contract: *Finish SOW and LOE ROW: * Obtain ROE to perform survey |  | The construction is not yet funded. The implementation phase date is shown as 12/31/2031.
PLANNING | 1140906 | RSD 156TH SE- SE 240TH CULVERT | RSD CWP CLVRT RPLCMT FISH PASS | No | Dulan, Lica | Drainage | Yes | No | Capital Project
PLANNING | 1141001 | RSD NETOLT RD RP WINTER2020 | RSD CWP QUICK RESPONSE | No | Martin, TingTing | Roadside | Yes | No | Capital Project | January 2022: Preliminary Design - 20% - Assemble Data from Geotechnical Explorations - Design Charette to select preferred alternative - Prepare revised scope to accelerate scheduled to meet CN Obligation deadline - Determine ROW needs for the project |  | - Need to confirm that construction obligation date of 9/20/2022 can be met to satisfy FHWA Emergency Relief funding requirements. Planning to expedite design to meet WSDOT deadlines. - ROW needs may effect project schedule. Property team planning to meet with WSDOT to obtain information.
IMPLEMENT | 1141044 | RSD 2021 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | Yes | No | Capital Project
DESIGN | 1141111 | RSD 2019-20 GUARDRAL PRSRVTN 3 | RSD CWP GUARDRAIL PRESERVATION | No | Mott, Linda | Roadside | Yes | No | Capital Project | 1. Mylar signing; spec cover signing 2. Final PS&E to Jerry in early January 3. Completion of procurement documents including SOAW, etc and submittal to Jerry 4. Funds moved into 1141111 5. Package sent to Procurement |  | Utility relocations - weekly/bi-weekly meetings to continue to keep our project at the forefront; Nadeem Mohammad to take over coordinating these efforts in January
IMPLEMENT | 1141250 | RSD 21-22 SCHOOL ZONE SAFETY | RSD CWP SCHOOL ZONE SAFETY | No | Hafele, Brendan | Traffic Control | Yes | No | Capital Project
DESIGN | 1141401 | RSD ROADWAY LIGHTING 2 | RSD CWP TRAFFIC SAFETY | No | Mott, Linda | Traffic Control | Yes | No | Capital Project
NOT SET | 1141464 | RSD BRG LD UP SFTY FSBLTY STDY | RSD CWP BRIDGE LOAD UPGRD SFTY | No | Jiang, Stephen | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1141505 | RSD 21 BPM RAGNGRVBR1008G RAIL | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1141507 | RSD 21 BPM WHITNEYBR2025 OVRLY | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1141509 | RSD 21 BPM CEDAR RIVER BRIDGES | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
IMPLEMENT | 1141580 | RSD 21 HRP AMES LK CARNATION F | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | Yes | No | Capital Project
IMPLEMENT | 1141581 | RSD 21 HRP ALPENTAL ACCESS RD | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | Yes | No | Capital Project
DESIGN | 1141625 | RSD SE KENT-KANGLEY @LANDSBURG | RSD CWP HIGH COLLISION SAFETY | No | Linders, Jon | Traffic Control | Yes | No | Capital Project | January: - Sent out 99% plans to utilities on 1/11. | - Continue Utility Coordination - Continue ROW acquisition with Parks (to be completed by March 2022) - Continue Communications Plan, meet with Ravensdale Market - Start Spec Package | Acquisition of Parks properties by March 2022.
NOT SET | 1142030 | RSD CW ADA RAMPS |  | No |  | Roadside | No | No | Capital Project
PLANNING | 1142035 | RSD ECE CW UKC ADA RAMPS |  | No | McManus, Aileen | Roadside | Yes | No | Capital Project
NOT SET | 1142289 | RSD 2021 HRP SE 368TH & 236TH | RSD CWP ROADWAY PRESERVATION | No | Mott, Linda | Roadway | Yes | No | Capital Project
NOT SET | 1142293 | RSD 21 BPM ISQH CRK BR 83D RPR | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142294 | RSD 21 BPM BOISE CR B 3052 RPR | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142384 | RSD 21 BPM BR 122L:122K JOINTS | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142385 | RSD 21 BPM BR 920A:BR 3109 APP | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
DESIGN | 1142478 | RSD 218TH AV SE RECONST DRNAGE | RSD CWP DRAINAGE PRESERVATION | No | Linders, Jon | Drainage | Yes | No | Capital Project
DESIGN | 1142502 | RSD AVONDALE & COTTAGE LK ELEM | RSD CWP TRAFFIC SAFETY | No | Hafele, Brendan | Traffic Control | Yes | No | Capital Project
NOT SET | 1142615 | RSD SE LAKE FRANCIS ROAD HAUL | RSD CWP QUICK RESPONSE | No |  | Roadside | No | No | Capital Project
NOT SET | 1142691 | RSD 21 BPM SPB MISC REPAIRS | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142848 | RSD 21 BPM GR RVR 3216 DCK RPR | RSD CWP BRIDGE PRIORITY MAINT | No |  | Bridges & Structures | No | No | Capital Project
NOT SET | 1142850 | RSD 21 FBLP DUVALL SLOUGH #113 | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142876 | RSD 21 BPM 3035A FLOOR BEAM RR | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | Yes | No | Capital Project
NOT SET | 1142993 | RSD 2022 CNTYWDE PAVE PRES | RSD CWP ROADWAY PRESERVATION | No | Mott, Linda | Roadway | Yes | No | Capital Project
IMPLEMENT | 2020-001 | DRN DIV DRN | RSD CWP DRAINAGE PRESERVATION | No | Shular, Ryan | Drainage | No | No | Capital Project
IMPLEMENT | 2020-002 | DRN DIV SHOULDER | RSD CWP DRAINAGE PRESERVATION | No | Kosai-Eng, Joann | Drainage | No | No | Capital Project
PLANNING | 2020-003 | PAV Pres Sub | RSD CWP ROADWAY PRESERVATION | No | Moore, Paul | Roadway | No | No | Capital Project
PLANNING | 2020-004 | BRG BPM list | RSD CWP BRIDGE PRIORITY MAINT | No | Roark, Ben | Bridges & Structures | No | No | Capital Project
PLANNING | 2020-005 | HIGH COLLISION | RSD CWP HIGH COLLISION SAFETY | No | Dovey, Dan | Traffic Control | No | No | Capital Project
PLANNING | 2020-006 | SCHOOL SAFETY | RSD CWP SCHOOL ZONE SAFETY | No | McManus, Aileen | Traffic Control | No | No | Capital Project
PLANNING | 2020-007 | TRAFFIC SAFETY | RSD CWP TRAFFIC SAFETY | No | Brown, Keith | Traffic Control | No | No | Capital Project
PLANNING | 2021001 | RSD AVONDALE RD COTTG LK ELEMT | RSD CWP TRAFFIC SAFETY | No | Hafele, Brendan | Traffic Control | No | No | Capital Project | - 30% design to be completed - update estimate - meet with maintenance draft schedule - update spending plan |  | Waiting for response from PSE about pole installation timeline.
PLANNING | 2021002 | RSD 21 HRP PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | No | No | Capital Project
PLANNING | 2021003 | RSD 22 HRP PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | No | Daggs, Victor | Roadway | No | No | Capital Project
PLANNING | 2021004 | RSD 218 AVE RECON PLACEHOLDER | RSD CWP DRAINAGE PRESERVATION | No | Quach, Dieu | Drainage | No | No | Capital Project
DESIGN | 2021005 | RSD 2022 CNTYWDE PAVE PRES PLACEHOLDER | RSD CWP ROADWAY PRESERVATION | No | Mott, Linda | Roadway | No | No | Capital Project
PLANNING | 2021006 | RSD 21 GUARDRAIL PRES PLACEHOLDER | RSD CWP GUARDRAIL PRESERVATION | No | Mott, Linda | Roadside | No | No | Capital Project
PLANNING | 2021007 | RSD 22 GUARDRAIL PRES PLACEHOLDER | RSD CWP GUARDRAIL PRESERVATION | No | Mott, Linda | Roadside | No | No | Capital Project
PLANNING | 2021008 | RSD BPM 2021 UNALLOCATED | RSD CWP BRIDGE PRIORITY MAINT | No | Mitchell, Patricia | Bridges & Structures | No | No | Capital Project
CLOSEOUT | Test-RSD | Test |  | No | Siemens, Amara | Roadway | No | No | Capital Project